## Pivot
Month | (All) |  | <- Filter By Month
Billable Timecode | Billable timecode
|  |  |  | Phase | Hours | Lower Bound | Upper Bound
Sum of Hours | Column Labels |  |  | Analysis | 8 - 10 | £960 | £1,200
Row Labels | Build | Grand Total |  | Build | 40 - 48 | £4,800 | £5,760
Sam Duncan | 3.5 | 3.5 |  | Project Management | 4 - 5 | £480 | £600
Anjali Salecha | 52 | 52 |  | UAT | 8 - 10 | £960 | £1,200
Dillan Landsberg | 0.5 | 0.5 |  | Production | 5 - 6.5 | £600 | £780
Shaun Barrett | 0.5 | 0.5 |  | Total | 65 - 80 | £7,800 | £9,540 | 120
Grand Total | 56.5 | 56.5
|  |  |  | Lower Bound (Hrs) | Upper Bound (Hrs) | Lower Bound (Cost) | Upper Bound (Cost)
|  |  |  | 8 | 10 | 960 | 1200
|  |  |  | 40 | 48 | 4800 | 5760
|  |  |  | 4 | 5 | 480 | 600
|  |  |  | 8 | 10 | 960 | 1200
|  |  |  | 5 | 6.5 | 600 | 780
|  |  |  | 65 | 79.5 | 7800 | 9540

## Project Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-05-22 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 250098 | Build | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 | 960 | 240 | IN08103 | GBP | Reviewed | 1. Daily standup. 2. Analysing stories 3. Understanding existing code in github 4. Discussion with Sam. | Not submitted | 5 | May
2024-05-23 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 251587 | Build | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN08103 | GBP | Reviewed | GA-3 Worked on setting up fieldsets and other new fields and prefixed github code with 'GDPR_' | Not submitted | 5 | May
2024-05-24 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 251329 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | GDPR Anonymisation - Refinement Session (OpenBox) | Not submitted | 5 | May
2024-05-27 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 251984 | Build | Billable timecode | Standard Timecode | 90 | 2.5 | 2:30 | 225 | 300 | 75 | IN08103 | GBP | Reviewed | 1. Worked on GA-3. New fields on Contact Account and Lead. Prepared list of changes. | Not submitted | 5 | May
2024-05-28 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 252496 | Build | Billable timecode | Standard Timecode | 90 | 7.5 | 7:30 | 675 | 900 | 225 | IN08103 | GBP | Reviewed | Worked on GA-3 implementation. Creating custom fields copying code from github with GDPR_ prefix. Discussion with Sam. Daily standup. | Not submitted | 5 | May
2024-05-29 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 252835 | Build | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 | 960 | 240 | IN08103 | GBP | Reviewed | Worked on GA-3. writing code for batch classes. Introduced new sequence field for chaining batch jobs. | Not submitted | 5 | May
2024-05-30 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 253547 | Build | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 | 960 | 240 | IN08103 | GBP | Reviewed | GA-3 and GA-8 implementation. Daily standup. | Not submitted | 5 | May
2024-05-31 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 253549 | Build | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 | 840 | 210 | IN08103 | GBP | Reviewed | Daily standup. GDPR session. Testing GA-8 and GA-3 | Not submitted | 5 | May
2024-06-03 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 254880 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 8 | 8:00 | 0 |  |  |  | GBP | Reviewed | Daily standup. Worked on GA-3 GA-2 GA-8 and GA-9. Testing of batch jobs. Preparations for deployment to QA environment. | Not submitted | 6 | June
2024-06-04 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 255588 | Build | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP | Reviewed | 1. Discussion with Sam. 2. Reworked story GA-3 based on feedback from Sam. 3. Deployment to QA environment. 4. Testing in QA environment. | Not submitted | 6 | June
2024-06-05 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 255599 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 7 | 7:00 | 0 |  |  |  | GBP | Reviewed | GDPR Anonymisation - Touchpoint session (Grainger/OpenBox) 2. Worked on Person Account History remover code. Deployment to QA environment and testing. | Not submitted | 6 | June
2024-06-06 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 256084 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 7 | 7:00 | 0 |  |  |  | GBP | Reviewed | Worked on story GA-4. Deployment and testing in qa environment. | Not submitted | 6 | June
2024-06-07 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 256525 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 5 | 5:00 | 0 |  |  |  | GBP | Reviewed | Daily standup. Worked on GA-5 and completed GA-9. Testing. | Not submitted | 6 | June
2024-06-10 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 257753 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 6.5 | 6:30 | 0 |  |  |  | GBP | Reviewed | 1. Test classes 2. Daily standup 3. Execution of test scenarios | Not submitted | 6 | June
2024-06-10 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 257970 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed | 1. Added ACs to Jira stories | Not submitted | 6 | June
2024-06-11 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 257752 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 8 | 8:00 | 0 |  |  |  | GBP | Reviewed | 1. Daily standup 2. Discussion wtih Dillan 3. Worked on GA-15 writing test classes | Not submitted | 6 | June
2024-06-12 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 258715 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 3.5 | 3:30 | 0 |  |  |  | GBP | Reviewed | GA-5 discussion with Dillan. Investigated the root cause for error emails not being sent out. Account record not being anonymised. | Not submitted | 6 | June
2024-06-12 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 258716 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed | Worked on writing ACs for GDPR project stories | Not submitted | 6 | June
2024-06-13 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 259863 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 5 | 5:00 | 0 |  |  |  | GBP |  | Worked on writing ACs stories. Discussion with Sam. Daily standup. | Not submitted | 6 | June
2024-06-17 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 259858 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 8 | 8:00 | 0 |  |  |  | GBP |  | 1. Daily standup. 2. Worked on writing story for GA-3. 3. Worked on GA-5 all or nothing behavior. 4. Worked on GA-16 | Not submitted | 6 | June
2024-06-18 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 260525 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 7 | 7:00 | 0 |  |  |  | GBP |  | Worked on testing GA-3 story in qa sandbox. Fixed issue related to email not being sent. Updated post deployment steps related to story GA-16. Daily standup. | Not submitted | 6 | June
2024-06-19 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 260815 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP |  | Deployment to UAT sandbox and post deployment config. | Not submitted | 6 | June
2024-05-20 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 249451 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed | Grainger GDPR kick-off & Jira check | Not submitted | 5 | May
2024-05-24 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 251387 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | refinement | Not submitted | 5 | May
2024-05-28 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 252336 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 5 | May
2024-06-05 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 255783 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Client meeting | Not submitted | 6 | June
2024-06-10 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 257333 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 6 | June
2024-06-18 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 260427 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  | Time Report | Not submitted | 6 | June
2024-05-31 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 253990 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-06-03 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 254953 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Write out test cases for GA-3 and GA-8 | Not submitted | 6 | June
2024-06-04 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 254951 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Call with Anjali for GA-3 and GA-8 | Not submitted | 6 | June
2024-06-05 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 255687 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | GDPR Anonymisation - Touchpoint session | Not submitted | 6 | June
2024-06-05 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 255688 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2.5 | 2:30 | 0 |  |  |  | GBP | Reviewed | QA on GA-238 | Not submitted | 6 | June
2024-06-07 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 256845 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | QA on GA-238 | Not submitted | 6 | June
2024-06-10 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 257213 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2.25 | 2:15 | 0 |  |  |  | GBP | Reviewed | QA GA-345 | Not submitted | 6 | June
2024-06-11 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 257683 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-12 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 258329 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.75 | 1:45 | 0 |  |  |  | GBP | Reviewed | QA GA-5 Update test cases Show me GA-5 with Anjali | Not submitted | 6 | June
2024-06-18 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 260522 | Build | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  | Update GA-3 5 16 | Not submitted | 6 | June
2024-05-20 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 249510 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-21 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 249509 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-22 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 250689 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-23 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 250690 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-24 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 251355 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-31 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 254226 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-06-03 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 255337 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-04 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 255338 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-05 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 255719 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-10 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 257502 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-11 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 257773 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-12 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 258866 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-13 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 258876 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-05-20 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 251755 | Build | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 240 | 60 | IN08103 | GBP | Reviewed | Implementation approach | Not submitted | 5 | May
2024-05-24 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 251770 | Build | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08103 | GBP | Reviewed | Refinement session | Not submitted | 5 | May
2024-06-05 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 257260 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Refinement with Grainger | Not submitted | 6 | June
2024-06-17 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 260171 | Build | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  | Meeting with Grainger backup team | Not submitted | 6 | June
2024-05-30 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 253324 | Build | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08103 | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-31 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 253305 | Build | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08103 | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-31 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 253306 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-06-03 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 254874 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 255288 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-05 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 256514 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-10 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 257351 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 257823 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-12 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 258628 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 258997 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-14 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 259540 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June