## Pivot
Month | (All) |  | <- Filter By Month | Phase | Hours | Lower Bound | Upper Bound
Billable Timecode | Billable timecode |  |  | Pre-Refresh Analysis | 20-22 | 2400 | 2640
|  |  |  | Refresh | 2-3 | 240 | 360
Sum of Hours | Column Labels |  |  | Post-refresh updates | 10-12 | 1200 | 1440
Row Labels | Planning and Executing Refresh Activities | Grand Total |  | End-to-end testing | 10-12 | 1200 | 1440
Sam Duncan | 1.75 | 1.75 |  | Project management | 2-3 | 240 | 360
Sachin Deshmukh | 20.25 | 20.25 |  | Total | 44 - 52 | 5280 | 6240
Grand Total | 22 | 22

## Project Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-05-23 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255040 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-24 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255041 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-27 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255044 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-28 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255045 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-29 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255046 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-30 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255050 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-31 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255054 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3.25 | 3:15 | 292.5 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-22 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 251771 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed | Initial analysis session | Not submitted | 5 | May
2024-05-27 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 253291 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May