## Pivot
Month | (All) |  | <- Filter By Month | Phase | Hours Lower Bound | Hours Upper Bound | Cost Lower Bound | Cost Upper Bound | Actuals
Billable Timecode | Billable timecode |  |  | Pre-Refresh Analysis | 25 | 28 | £ 3 000,00 | £ 3 360,00
|  |  |  | Refresh | 4 | 5 | £ 480,00 | £ 600,00
Sum of Hours | Column Labels |  |  | Project Admin Phase | 8 | 9 | £ 960,00 | £ 1 080,00
Row Labels | Planning and Executing Refresh Activities | Grand Total |  | Post Refresh Updates | 10 | 11 | £ 1 200,00 | £ 1 320,00
Sam Duncan | 6.75 | 6.75 |  | End-to-end Testing | 16 | 18 | £ 1 920,00 | £ 2 160,00
Anjali Salecha | 6.5 | 6.5 |  | Total | 63 | 71 | £ 7 560,00 | £ 8 520,00
Sachin Deshmukh | 48.5 | 48.5
Khonani Davhana | 9.25 | 9.25
Grand Total | 71 | 71 | Project Complete
SIT Estimates
|  |  |  | Post refresh | 5
|  |  |  | Testing | 5

## Project Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-06-05 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255598 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | spreadsheet steps review and daily standup. | Not submitted | 6 | June
2024-06-07 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 256523 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | Salesforce UAT Refresh Planning #4 | Not submitted | 6 | June
2024-06-18 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 260523 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08267 | GBP | Reviewed | Daily standup. Discussion with Sachin. Worked on external credential authentication issue. | Not submitted | 6 | June
2024-06-19 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 260818 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 4.5 | 4:30 | 405 | 540 | 135 | IN08267 | GBP | Reviewed | Smoke testing referencing callout and Website publishing functionalities and investigation of issue related to process builder not firing. | Not submitted | 6 | June
2024-06-19 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 262789 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2 | 2:00 | 0 |  |  |  | GBP | Reviewed | Smoke testing referencing callout and Website publishing functionalities and investigation of issue related to process builder not firing. | Not submitted | 6 | June
2024-06-20 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 262788 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 6 | 6:00 | 0 |  |  |  | GBP | Reviewed | Daily standup. Discussion with Khonani about issue that Janaki Pankhiyan is not able to to close task. Worked on process builders not firing. Testing Homelet integration for new add and cancel order. | Not submitted | 6 | June
2024-06-21 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 261877 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08267 | GBP | Reviewed | Discussion with Khonani and UAT refresh issues. | Not submitted | 6 | June
2024-06-19 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 260677 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | email thread catchup | Not submitted | 6 | June
2024-06-24 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 262555 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time report | Not submitted | 6 | June
2024-06-25 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 262926 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed | Time Report & util catchup with Sam | Not submitted | 6 | June
2024-06-11 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 257774 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-18 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 260226 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-19 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 261135 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-20 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 261161 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3.5 | 3:30 | 315 | 420 | 105 | IN08267 | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-20 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 261157 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2 | 2:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-21 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 261755 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 5.75 | 5:45 | 517.5 | 690 | 172.5 | IN08267 | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-24 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 262434 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-27 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 264831 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-28 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 264828 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2 | 2:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-05-23 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255040 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN08219 | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-24 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255041 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN08219 | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-27 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255044 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 240 | 60 | IN08219 | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-28 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255045 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN08219 | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-29 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255046 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN08219 | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-30 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255050 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN08219 | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-31 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 255054 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3.25 | 3:15 | 292.5 | 390 | 97.5 | IN08219 | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-06-04 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 256890 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-06 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 256895 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 4.5 | 4:30 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-07 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 256896 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 7.5 | 7:30 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-10 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 259551 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08267 | GBP | Reviewed | Getting required data from SIT before the refresh | Not submitted | 6 | June
2024-06-17 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 260459 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3.25 | 3:15 | 292.5 | 390 | 97.5 | IN08267 | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-17 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 262786 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 5 | 5:00 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-18 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 260477 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3.25 | 3:15 | 292.5 | 390 | 97.5 | IN08267 | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-18 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 262787 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 5 | 5:00 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-19 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 260446 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 | 600 | 150 | IN08267 | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-20 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 261339 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08267 | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-21 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 262120 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08267 | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-24 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 264339 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 6.5 | 6:30 | 585 | 780 | 195 | IN08267 | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-25 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 264345 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 5.5 | 5:30 | 495 | 660 | 165 | IN08267 | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-26 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 264355 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 3.25 | 3:15 | 292.5 | 390 | 97.5 | IN08267 | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-06-26 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Analysis and Delivery | 264822 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 6 | June
2024-05-22 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 251771 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 | 90 | 22.5 | IN08219 | GBP | Reviewed | Initial analysis session | Not submitted | 5 | May
2024-05-27 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 253291 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08219 | GBP | Reviewed |  | Not submitted | 5 | May
2024-06-03 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 257243 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08267 | GBP | Reviewed | Planning call | Not submitted | 6 | June
2024-06-07 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 257249 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08267 | GBP | Reviewed | Planning | Not submitted | 6 | June
2024-06-14 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 257192 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08267 | GBP | Reviewed | Planning call | Not submitted | 6 | June
2024-06-17 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 260173 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08267 | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-18 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 260174 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08267 | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-19 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 262225 | Planning and Executing Refresh Activities | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08267 | GBP | Reviewed | Touchbase on progress | Not submitted | 6 | June
2024-06-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 254877 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-05 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 256516 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-10 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 257356 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 257355 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-12 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 258630 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 258999 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-14 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 259542 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June
2024-06-28 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000660 | Salesforce UAT Refresh (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Analysis and Delivery | 265121 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 6 | June