## Pivot
Sprint 0
Month | (All) |  | <- Filter By Month
Billable Timecode | Billable timecode
Sum of Hours | Column Labels
Row Labels | Delivery | Grand Total
Nikki Papenfus | 112 | 112
Sam Duncan | 8 | 8
Grand Total | 120 | 120
Delivery |  |  |  | Project Phases | Duration | Lower Bound | Upper Bound | Lower Bound | Upper Bound
|  |  |  | Sprint 0 | 4-5 weeks | 80 | 120 | 12000 | 18000 | Complete
Month | (All) |  |  | Sprint 1 - 3 | 6-9 Weeks |  |  | 37800 | 56700 | 18 900 per sprint
Billable Timecode | Billable timecode |  |  | UAT | 2 Weeks | 40 | 40 | 3150 | 3150
|  |  |  | Production Deployment & Post-Go-Live Support | 2 Weeks | 20 | 20 | 1600 | 1600 | 800 per week
Sum of Hours | Column Labels |  |  | User Guide creation | 1 Week | 40 | 40 | 3150 | 3150 | 630 per day
Row Labels | Delivery | Grand Total
Shaun Barrett | 5.25 | 5.25 |  | Total | 4-5 weeks |  |  | 57700 | 82600
Jacob Smycz | 4 | 4
Nikki Papenfus | 18.5 | 18.5
Sam Duncan | 11 | 11
Akshat Jain | 136 | 136
Anjali Salecha | 73 | 73
Sachin Deshmukh | 112.5 | 112.5
Carami Viljoen | 0.25 | 0.25
Khonani Davhana | 18.5 | 18.5
Matthew Cornfield | 2.75 | 2.75
Sarah Jessiman | 21.25 | 21.25
Grand Total | 403 | 403

## Delivery Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-12-18 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338464 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | #NAME? | Not submitted | 12 | December
2024-12-19 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338463 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Attended CLTL Sprint 1 planning session -- Openbox setup -- Grainger understanding | Not submitted | 12 | December
2024-12-20 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338462 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Attended CLTL Sprint 2 planning session -- POC on Screen flows to introduce datatable | Not submitted | 12 | December
2024-12-23 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338353 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD | Reviewed | #NAME? | Not submitted | 12 | December
2024-12-24 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338352 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | #NAME? | Not submitted | 12 | December
2024-12-26 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338502 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | #NAME? | Not submitted | 12 | December
2024-12-27 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338580 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger Stand Up -- CLTL-22 -- Deployment for CLTL-4 from Dev to QA -- Deployment for CLTL-20 from Dev to QA -- Deployment for CLTL-21 from Dev to QA | Not submitted | 12 | December
2024-12-30 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338748 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger Stand Up -- Worked on CLTL-22 -- Verified CLTL-4 in QA | Not submitted | 12 | December
2024-12-31 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338772 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | #NAME? | Not submitted | 12 | December
2025-01-02 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 339103 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | #NAME? | Not submitted | 1 | January
2025-01-03 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 339180 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Worked on CLTL-22 A/C 5 and Made Agreement Type Multiselect picklist on screen -- Grainger Stand Up | Not submitted | 1 | January
2025-01-06 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 339750 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Discussion on 'Unique object reference' limit error. -- POC on fetching picklist values based on record type. -- Grainger Stand Up | Not submitted | 1 | January
2025-01-07 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 339751 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | #NAME? | Not submitted | 1 | January
2025-01-08 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 340452 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger Standup -- Show me to QA for CLTL-4, 20, 21 -- Worked on fetching of record type based picklist values. | Not submitted | 1 | January
2025-01-09 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 340453 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger CLTL Stand Up -- CLTL-22 Deployment -- Worked on Bug CLTL-43 | Not submitted | 1 | January
2025-01-10 | Akshat Jain | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 340585 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | #NAME? | Not submitted | 1 | January
2024-12-18 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 336999 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed | Grainger: Commercial Lead to Lease - Planning | Not submitted | 12 | December
2024-12-19 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 336998 | Delivery | Billable timecode | Standard Timecode | 115 | 4.25 | 4:15 | 488.75 |  |  |  | USD | Reviewed | Grainger: Commercial Lead to Lease - Planning 2. Stories reading and related reading. | Not submitted | 12 | December
2024-12-20 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 337758 | Delivery | Billable timecode | Standard Timecode | 115 | 4 | 4:00 | 460 |  |  |  | USD | Reviewed | Daily standup. Discussion. User stories | Not submitted | 12 | December
2024-12-23 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338319 | Delivery | Billable timecode | Standard Timecode | 115 | 5.25 | 5:15 | 603.75 |  |  |  | USD | Reviewed | Worked on CLTL-19. standup. Story allocation discussion with Sachin and Akshat. | Not submitted | 12 | December
2024-12-24 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338551 | Delivery | Billable timecode | Standard Timecode | 115 | 8 | 8:00 | 920 |  |  |  | USD |  | Worked on CLTL-19. standup. | Not submitted | 12 | December
2024-12-26 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338553 | Delivery | Billable timecode | Standard Timecode | 115 | 8 | 8:00 | 920 |  |  |  | USD |  | Worked on CLTL-19. standup. | Not submitted | 12 | December
2024-12-27 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338554 | Delivery | Billable timecode | Standard Timecode | 115 | 8 | 8:00 | 920 |  |  |  | USD |  | Worked on CLTL-19. standup. Sprint 2 discussion with Akshat and Sachin. | Not submitted | 12 | December
2025-01-06 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 339391 | Delivery | Billable timecode | Standard Timecode | 115 | 8 | 8:00 | 920 |  |  |  | USD |  | Daily standup. Discussion with Sachin and Akshat related to technical issues. Wroked on CLTL-19. Discussion with Nikki. | Not submitted | 1 | January
2025-01-07 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 340071 | Delivery | Billable timecode | Standard Timecode | 115 | 7 | 7:00 | 805 |  |  |  | USD |  | Worked on CLTL-19. Deployment package preparation. Discussion with Sachin and Akshat about technical challenges. Daily standup. | Not submitted | 1 | January
2025-01-08 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 340072 | Delivery | Billable timecode | Standard Timecode | 115 | 7.5 | 7:30 | 862.5 |  |  |  | USD |  | Daily standup, Worked on deployment issues with Sachin. | Not submitted | 1 | January
2025-01-09 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 340737 | Delivery | Billable timecode | Standard Timecode | 115 | 8 | 8:00 | 920 |  |  |  | USD |  | Tested CLTL-19 in QA sandbox. Show me with Khonani , Sarah and Nikky. Story review of CLTL-22 and discussed technical challenge of Bug 43. Investigated root cause of CLTL-53. Worked with Sachin on error when Opportunity is updated due to 'Years' in Primary Offer Term. Daily standup. | Not submitted | 1 | January
2025-01-10 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 340735 | Delivery | Billable timecode | Standard Timecode | 115 | 4 | 4:00 | 460 |  |  |  | USD |  | Daily standup. Worked on CLTL-53. Discussion with Matt C. Story review with Sachin CLTL-23. | Not submitted | 1 | January
2024-12-30 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 338684 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  | Time Report | Not submitted | 12 | December
2024-12-18 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 336808 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-19 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 336804 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-30 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338654 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  |  | Not submitted | 12 | December
2025-01-02 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 339059 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-03 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 339155 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-06 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 339344 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-07 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 339648 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-08 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 340386 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-09 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 340389 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-10 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 340777 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-07 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 339741 | Delivery | Billable timecode | Standard Timecode | 115 | 0.5 | 0:30 | 57.5 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-08 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 340474 | Delivery | Billable timecode | Standard Timecode | 115 | 6.25 | 6:15 | 718.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-09 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 340483 | Delivery | Billable timecode | Standard Timecode | 115 | 5.5 | 5:30 | 632.5 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-10 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 341263 | Delivery | Billable timecode | Standard Timecode | 115 | 6.25 | 6:15 | 718.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-08 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 340194 | Delivery | Billable timecode | Standard Timecode | 115 | 1.25 | 1:15 | 143.75 |  |  |  | USD |  | 15m team standup 30m khonani QA help 30m Show me | Not submitted | 1 | January
2025-01-09 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 340404 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  | 15m team standup | Not submitted | 1 | January
2025-01-10 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 340770 | Delivery | Billable timecode | Standard Timecode | 115 | 1.25 | 1:15 | 143.75 |  |  |  | USD |  | Morning standup 1h sandbox data fix | Not submitted | 1 | January
2024-12-09 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 336540 | Delivery | Billable timecode | Standard Timecode | 115 | 1.75 | 1:45 | 201.25 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-10 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 336539 | Delivery | Billable timecode | Standard Timecode | 115 | 0.5 | 0:30 | 57.5 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 336538 | Delivery | Billable timecode | Standard Timecode | 115 | 1.5 | 1:30 | 172.5 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-17 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 336090 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-18 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 336590 | Delivery | Billable timecode | Standard Timecode | 115 | 3.25 | 3:15 | 373.75 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-19 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 337167 | Delivery | Billable timecode | Standard Timecode | 115 | 2.25 | 2:15 | 258.75 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-20 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 337840 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2025-01-02 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 339095 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-03 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 339231 | Delivery | Billable timecode | Standard Timecode | 115 | 0.5 | 0:30 | 57.5 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-06 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 339513 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-07 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 339853 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-08 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 340245 | Delivery | Billable timecode | Standard Timecode | 115 | 0.5 | 0:30 | 57.5 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-09 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 340572 | Delivery | Billable timecode | Standard Timecode | 115 | 3.5 | 3:30 | 402.5 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-10 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Build | 340959 | Delivery | Billable timecode | Standard Timecode | 115 | 1.25 | 1:15 | 143.75 |  |  |  | USD |  |  | Not submitted | 1 | January
2024-12-18 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 337493 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed | CLTL Internal sprint planning #1 | Not submitted | 12 | December
2024-12-19 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 337494 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed | CLTL Internal sprint planning #2 | Not submitted | 12 | December
2024-12-23 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338763 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Worked on CLTL 16 | Not submitted | 12 | December
2024-12-24 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338764 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Worked on CLTL 16 | Not submitted | 12 | December
2024-12-26 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338765 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Worked on CLTL 10 | Not submitted | 12 | December
2024-12-27 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338766 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Worked on CLTL 10 -- Reviewed and Assisted to deploy CLTL 4 to QA | Not submitted | 12 | December
2024-12-30 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338770 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Worked on CLTL 10 -- Reviewed on CLTL 21 | Not submitted | 12 | December
2024-12-31 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 338771 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Worked on CLTL 10 -- Reviewed on CLTL 20, CLTL 22 | Not submitted | 12 | December
2025-01-02 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 341088 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Worked on CLTL 10 | Not submitted | 1 | January
2025-01-03 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 341089 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Worked on CLTL 10 | Not submitted | 1 | January
2025-01-06 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 341095 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Review CLTL 10 with Anjali and Nikki -- Worked on CLTL 23 | Not submitted | 1 | January
2025-01-07 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 341096 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Worked on CLTL 23 | Not submitted | 1 | January
2025-01-08 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 341097 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Worked on CLTL 23 | Not submitted | 1 | January
2025-01-09 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 341098 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Worked on CLTL 23 | Not submitted | 1 | January
2025-01-10 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Build | 341099 | Delivery | Billable timecode | Standard Timecode | 115 | 8.5 | 8:30 | 977.5 |  |  |  | USD |  | -- Grainger: CLTL Stand Up -- Reviewed CLTL 23 with Anjali -- Deployed CLTL 23 to QA | Not submitted | 1 | January
2024-12-06 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 337900 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed | Backlog sizing with Nikki (1 hour) | Not submitted | 12 | December
2024-12-09 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 337920 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed | Backlog sizing with Nikki (1 hour) | Not submitted | 12 | December
2024-12-18 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 337955 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed | Internal kickoff (1 hour) | Not submitted | 12 | December
2024-12-19 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 337956 | Delivery | Billable timecode | Standard Timecode | 115 | 4 | 4:00 | 460 |  |  |  | USD | Reviewed | Solutioning user stories (3 hours) | Not submitted | 12 | December
2024-12-20 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 337957 | Delivery | Billable timecode | Standard Timecode | 115 | 4 | 4:00 | 460 |  |  |  | USD | Reviewed | Solutioning user stories (3 hours) | Not submitted | 12 | December
2025-01-07 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 339774 | Delivery | Billable timecode | Standard Timecode | 115 | 2.5 | 2:30 | 287.5 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-08 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 339973 | Delivery | Billable timecode | Standard Timecode | 115 | 5 | 5:00 | 575 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-09 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 340611 | Delivery | Billable timecode | Standard Timecode | 115 | 6.75 | 6:45 | 776.25 |  |  |  | USD |  |  | Not submitted | 1 | January
2025-01-10 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 340884 | Delivery | Billable timecode | Standard Timecode | 115 | 7 | 7:00 | 805 |  |  |  | USD |  |  | Not submitted | 1 | January
2024-12-17 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 336419 | Delivery | Billable timecode | Standard Timecode | 115 | 1.5 | 1:30 | 172.5 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 336414 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-19 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 337668 | Delivery | Billable timecode | Standard Timecode | 115 | 1 | 1:00 | 115 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-20 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 337684 | Delivery | Billable timecode | Standard Timecode | 115 | 0.75 | 0:45 | 86.25 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-23 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 338265 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-24 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 338420 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-23 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 338265 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December
2024-12-24 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000725 | Commercial Lead to Lease - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Build | 338420 | Delivery | Billable timecode | Standard Timecode | 115 | 0.25 | 0:15 | 28.75 |  |  |  | USD | Reviewed |  | Not submitted | 12 | December

## Sprint 0 Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-11-11 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 321638 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time report | Not submitted | 11 | November
2024-11-18 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 324722 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | time report | Not submitted | 11 | November
2024-11-25 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 327721 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 11 | November
2024-12-02 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 330799 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | time report | Not submitted | 12 | December
2024-11-04 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 318682 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-06 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 319648 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-11 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 321304 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-12 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 322607 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-13 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 322601 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-18 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 324564 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2.25 | 2:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-20 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 325531 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-21 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 326175 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-25 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 327415 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.75 | 1:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-27 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 328707 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-12-02 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 331407 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-11-01 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 318298 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2.5 | 2:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-04 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 318619 | Delivery | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 | 337.5 | 135 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-05 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 319087 | Delivery | Billable timecode | Standard Timecode | 90 | 2.5 | 2:30 | 225 | 375 | 150 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-06 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 319663 | Delivery | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 225 | 90 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-07 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 320173 | Delivery | Billable timecode | Standard Timecode | 90 | 4.5 | 4:30 | 405 | 675 | 270 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-08 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 320704 | Delivery | Billable timecode | Standard Timecode | 90 | 7.25 | 7:15 | 652.5 | 1087.5 | 435 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 321468 | Delivery | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 | 600 | 240 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-12 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 322040 | Delivery | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 | 1050 | 420 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-13 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 322573 | Delivery | Billable timecode | Standard Timecode | 90 | 6.5 | 6:30 | 585 | 975 | 390 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-14 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 323022 | Delivery | Billable timecode | Standard Timecode | 90 | 4.25 | 4:15 | 382.5 | 637.5 | 255 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-15 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 323759 | Delivery | Billable timecode | Standard Timecode | 90 | 5.5 | 5:30 | 495 | 825 | 330 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-18 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 324526 | Delivery | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 | 750 | 300 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-19 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 325122 | Delivery | Billable timecode | Standard Timecode | 90 | 3.75 | 3:45 | 337.5 | 562.5 | 225 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-20 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 325597 | Delivery | Billable timecode | Standard Timecode | 90 | 7.5 | 7:30 | 675 | 1125 | 450 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-21 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 326108 | Delivery | Billable timecode | Standard Timecode | 90 | 7.25 | 7:15 | 652.5 | 1087.5 | 435 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-22 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 326754 | Delivery | Billable timecode | Standard Timecode | 90 | 4.5 | 4:30 | 405 | 675 | 270 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-25 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 327557 | Delivery | Billable timecode | Standard Timecode | 90 | 2.75 | 2:45 | 247.5 | 412.5 | 165 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-26 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 328066 | Delivery | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 | 750 | 300 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-27 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 328571 | Delivery | Billable timecode | Standard Timecode | 90 | 7.5 | 7:30 | 675 | 1125 | 450 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-12-02 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 330752 | Delivery | Billable timecode | Standard Timecode | 90 | 3.75 | 3:45 | 337.5 | 0 | 0 | IN08955 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-03 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 331283 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 0 | 0 | IN08955 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-04 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 331280 | Delivery | Billable timecode | Standard Timecode | 90 | 5.5 | 5:30 | 495 | 0 | 0 | IN08955 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-05 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 331947 | Delivery | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 | 0 | 0 | IN08955 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-06 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 332839 | Delivery | Billable timecode | Standard Timecode | 90 | 3.5 | 3:30 | 315 | 0 | 0 | IN08955 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-09 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 333066 | Delivery | Billable timecode | Standard Timecode | 90 | 3.75 | 3:45 | 337.5 | 0 | 0 | IN08955 | GBP | Reviewed |  | Not submitted | 12 | December
2024-11-04 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323698 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-06 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323711 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-11 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323726 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 150 | 60 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-12 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323737 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08887 | GBP | Reviewed | Qube discussion | Not submitted | 11 | November
2024-11-13 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323739 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-18 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 328859 | Delivery | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 300 | 120 | IN08887 | GBP | Reviewed | Internal refinement with Nikki (1 hour) External refinement session (1 hour) | Not submitted | 11 | November
2024-11-21 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 328860 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 150 | 60 | IN08887 | GBP | Reviewed | Internal refinement with Nikki (1 hour) | Not submitted | 11 | November
2024-11-25 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 328889 | Delivery | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 225 | 90 | IN08887 | GBP | Reviewed | Refinement with Nikki (1 hour) Refinement with Grainger (30 mins) | Not submitted | 11 | November
2024-11-27 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 328898 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08887 | GBP | Reviewed | Refinement session (30 mins) | Not submitted | 11 | November
2024-09-27 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 302333 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-30 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 304735 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-10-30 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 316721 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-11-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 318740 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-05 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 319240 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-06 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 319825 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-07 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 320319 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-08 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 320320 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 321660 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-12 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 322196 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 322738 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-14 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323217 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-15 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323869 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 324582 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-20 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 325824 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-21 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 326248 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-22 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 327241 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-25 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 327234 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-12-02 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 331080 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-03 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 331090 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 331742 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-05 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 332081 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December