## Pivot
Delivery
Month | (All) |  | <- Filter By Month |  |  | Phase | Lower Bound | Upper Bound | Lower Bound | Upper Bound
Billable Timecode | Billable timecode |  |  |  |  | Analysis | 8 | 10 | £960 | £1,200
[6 empty] | Build | 40 | 48 | £4,800 | £5,760
Sum of Hours | Column Labels |  |  |  |  | Project Management | 4 | 5 | £480 | £600
Row Labels | Analysis | Testing | Project Management | Development | Grand Total | UAT | 8 | 10 | £960 | £1,200
Shaun Barrett |  |  | 2.25 |  | 2.25 | Production deployment and post go-live support | 8 | 10 | £960 | £1,200
Jacob Smycz | 5 |  |  | 16.75 | 21.75 | Total | 68 | 83 | £8,160 | £9,960
Sarah Jessiman |  | 22.25 |  |  | 22.25
Sam Duncan |  |  |  | 3.5 | 3.5
Grand Total | 5 | 22.25 | 2.25 | 20.25 | 49.75

## Delivery Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-11-26 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 330336 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 6 | 6:00 | 0 |  |  |  | GBP | Reviewed | Form Assembly discussion with Sam and Jacob. Form Assembly documentation. Worked on Util class to get secure url. | Not submitted | 11 | November
2024-11-27 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 330337 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 4.5 | 4:30 | 0 |  |  |  | GBP | Reviewed | Discussion with Jacob for Form Assembly secure url. Discussion with Sam. Worked on Form Assembly secure url. - LRWFA-8 | Not submitted | 11 | November
2024-11-28 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 330338 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 8 | 8:00 | 0 |  |  |  | GBP | Reviewed | Daily standup. Form Assembly discussion with Sachin and Sam. Discussion with Jacob. Worked on updated LRWFA-8 | Not submitted | 11 | November
2024-12-18 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 336985 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 3.75 | 3:45 | 0 |  |  |  | GBP | Reviewed | Worked on test classes and deployment to QA enviornment. | Not submitted | 12 | December
2024-11-25 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 327722 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 11 | November
2024-12-02 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 330796 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | time report | Not submitted | 12 | December
2024-12-10 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 333714 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 12 | December
2024-12-17 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 337211 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | time report | Not submitted | 12 | December
2024-12-30 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 338682 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  | time report | Not submitted | 12 | December
2025-01-13 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 341580 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  | Time Report | Not submitted | 1 | January
2024-11-20 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 325460 | Analysis | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 180 | 45 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-21 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 326072 | Analysis | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 | 270 | 67.5 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-22 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 327414 | Analysis | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-25 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 327421 | Analysis | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-25 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 327485 | Development | Billable timecode | Standard Timecode | 90 | 1.75 | 1:45 | 157.5 | 210 | 52.5 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-25 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 327416 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-26 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 328006 | Development | Billable timecode | Standard Timecode | 90 | 3.5 | 3:30 | 315 | 420 | 105 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-26 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 328003 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-27 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 328702 | Development | Billable timecode | Standard Timecode | 90 | 3.75 | 3:45 | 337.5 | 450 | 112.5 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-27 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 328708 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-28 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 329615 | Analysis | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-28 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 329613 | Development | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-29 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 329816 | Development | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-29 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 329817 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-12-02 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 331412 | Development | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-03 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 331421 | Development | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-04 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 331913 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-05 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 333449 | Development | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-10 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 334502 | Development | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-11 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 334505 | Development | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-12 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 334759 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-16 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 335523 | Development | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-19 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 338044 | Development | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2025-01-15 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 342408 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP |  |  | Not submitted | 1 | January
2024-11-21 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 328871 | Development | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08888 | GBP | Reviewed | Session with Jacob (30 mins) | Not submitted | 11 | November
2024-11-25 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 328882 | Development | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08888 | GBP | Reviewed | Planning session (1 hour) | Not submitted | 11 | November
2024-11-26 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 328895 | Development | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08888 | GBP | Reviewed | Refinement session (1 hour) | Not submitted | 11 | November
2024-11-27 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 328899 | Development | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08888 | GBP | Reviewed | Review with Jacob (30 mins) | Not submitted | 11 | November
2024-11-28 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 330390 | Development | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08888 | GBP |  | Refinement with Jacob (30 mins) | Not submitted | 11 | November
2024-11-18 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 325476 | Testing | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08888 | GBP | Reviewed | Intro meeting with Jacob | Not submitted | 11 | November
2024-11-19 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 325746 | Testing | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08888 | GBP | Reviewed | R2R/leadpro standup | Not submitted | 11 | November
2024-11-20 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 325465 | Testing | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08888 | GBP | Reviewed | R2R/leadpro standup | Not submitted | 11 | November
2024-11-21 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 325938 | Testing | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08888 | GBP | Reviewed | R2R/leadpro standup + read through cards on board | Not submitted | 11 | November
2024-11-22 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 326763 | Testing | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-25 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 327547 | Testing | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 | 150 | 37.5 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-26 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 328016 | Testing | Billable timecode | Standard Timecode | 90 | 2.75 | 2:45 | 247.5 | 330 | 82.5 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-27 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 328660 | Testing | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-28 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 329490 | Testing | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 | 480 | 120 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-29 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 329493 | Testing | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 | 150 | 37.5 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-12-02 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 330916 | Testing | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-03 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 331015 | Testing | Billable timecode | Standard Timecode | 90 | 1.75 | 1:45 | 157.5 | 210 | 52.5 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-04 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 331563 | Testing | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 | 150 | 37.5 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-05 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 333982 | Testing | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-06 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 333988 | Testing | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-09 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 333996 | Testing | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-10 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 333997 | Testing | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-11 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 333998 | Testing | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-12 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 334771 | Testing | Billable timecode | Standard Timecode | 90 | 3.5 | 3:30 | 315 | 420 | 105 | IN08990 | GBP | Reviewed |  | Not submitted | 12 | December
2025-01-15 | Sarah Jessiman | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 343139 | Testing | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP |  | UAT kick off call | Not submitted | 1 | January
2024-11-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 325456 | Project Management | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 325455 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-19 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 325457 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-20 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 325454 | Project Management | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-20 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 325453 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-21 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 326249 | Project Management | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-22 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 327242 | Project Management | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-25 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 327236 | Project Management | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN08888 | GBP | Reviewed |  | Not submitted | 11 | November
2024-12-02 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 331079 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-03 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 331089 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 331744 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-05 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 332082 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-09 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 334072 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 334592 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-12 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 335029 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 335383 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-17 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 336420 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 337012 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2024-12-19 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 337672 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 12 | December
2025-01-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 341512 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP |  |  | Not submitted | 1 | January
2025-01-14 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 342067 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP |  |  | Not submitted | 1 | January
2025-01-15 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 342645 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP |  |  | Not submitted | 1 | January
2025-01-16 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 343251 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP |  |  | Not submitted | 1 | January
2025-01-17 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000766 | LeadPro Replacement (Form Assembly) (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 344170 | Overheads (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  |  | Not submitted | 1 | January