## Sheet1
Phase | Task Name | Queue Type | Expected Duration (Days) | Task Start Date | Starts After Preceding Tasks | Fields User Must Review / Update when Closing a Task | Fields Automatically Updated on Task Completion | Information Displayed to User in Task
Receive Notice | Validate Notice | Centralized PM | 1 | Void Start Date |  | Unit to be Relet; Unit to be Sold |  | In order to complete this task: • Check Tenancy to confirm notice is allowed. • Check if there is parking that needs to be processed at the same time.
Receive Notice | Confirm Notice | Centralized PM | 1 |  | Validate Notice | Reason for Vacancy; FV Date; FV Date is Confirmed; PVI Date; PVI Time | At end of Receive Notice Phase: Updates Unit's initial FV Date & Available Date; Unit Status set to 'Future Vacant'. | In order to complete this task: • Notify residents that notice has been accepted or denied via phone call and email. • Send DRI and Steps to Vacating forms to tenant for them to complete. • Update key location on Unit. • Update Qube.
Notify Stakeholders | Notify Stakeholders | Centralized PM | 1 |  | Confirm Notice |  |  | In order to complete this task: • Update Finance to amend Qube • Create MiMo tasks. • Create Work Order in Evolution for external inventory clerks. • Update British Gas Portal.
Notify Stakeholders | Check Compliance | Centralized PM | 7 |  | Confirm Notice | EPC Status; EPC Expiry Date; EICR Status; EICR Expiry Date; CP12 Status; CP12 Expiry Date. | Updates Unit: Compliance fields | In order to complete this task: • Ensure all required documents are in date. • Get up-to-date documents if required. • Save documents in correct folder.
Notify Stakeholders | Confirm PVI Date | Onsite PM | 1 |  | Check Compliance | PVI Date; PVI Time; PVI Notes for Axis; Works Type; Axis Key Location | PVI Date & Time is Confirmed
Notify Stakeholders | Amend Direct Debit | Finance | 2 |  | Confirm Notice |  |  | In order to complete this task: • Apportion final rent collection.
Notify Stakeholders | Set Rent | Letting | 3 |  | Confirm Notice | Unit Marketing Status: • On the Market Available to View • On the Market - No Access | Updates Unit: Unit Status
PVI | PVI | Onsite PM | 1 | PVI Date |  | Works Type | PVI Completed Date | In order to complete this task: • Complete PVI. • Follow up contact with tenant with details of repairs, information and deposit release.
Book Works | Approve CapEx | Asset Management | 3 |  | PVI
Book Works | Book Works | Centralized PM | 4 |  | PVI |  |  | In order to complete this task: • Confirm works required after PVI. • Collect quotes for works and repairs. • Book works in FSI and arrange contractor’s access for Vacate Date. • Book cleaning.
Move Out | Check Out | Onsite PM | 1 | FV Date |  | Actual Vacant Date; Axis Key Location | Updates Tenancy: Status = Ended & Actual Move Out Date | In order to complete this task: • Keys have been handed back. • Final inspection completed. • Update Finance to amend Qube • Confirm access with inventory clerk (if required).
Move Out | Close Down Tenancy | Finance | 5 |  | Check Out |  |  | In order to complete this task: • Close tenancy and mark relet status on Qube.
Move Out | Cancel Direct Debit | Finance | 2 |  | Check Out |  |  | In order to complete this task: • Cancel DDM after move out confirmation.
Refurb/Refresh | Review Check Out Report | Centralized PM | 3 |  | Check Unit Condition
Refurb/Refresh | Finalize Check Out | Centralized PM | 4 |  | Check Unit Condition |  |  | In order to complete this task: • Send checkout report to Tenant. • Notify Council Tax. • Notify any remaining utilities. • Diarise flushing for void unit.
Refurb/Refresh | Refresh | Onsite PM | 7 |  | Check Unit Condition
Refurb/Refresh | Refurb | Onsite PM | 15 |  | Check Unit Condition
Refurb/Refresh | Clean Unit | Onsite PM | 1 |  | Check Unit Condition, Refurb, Refresh
Move Out | Check Unit Condition | Onsite PM | 2 | FV Date |  |  | Works Start Date | In order to complete this task: • Compare PVI and final inspection, and adjust works if needed. • Save checkout report to EoT. • Compare Move-in and Move-out inventory. • Complete ROD and notify Credit Control. | Moved down the list as done at the end
Release Deposit | Deposit Release | Finance | 3 |  | Finalize Check Out | Deposit Stoppage Type, Deposit Stoppage Amount | Deposit Return Date | When RTA gets emailed to process refund, this task can be marked off as complete.