## July 24 - Oct 25 (Sprint 1-16)
Sprint Alignment | Sprint 1 UAT |  |  |  |  | Sprint 2 | [22 empty] | Sprint 2 UAT |  |  |  |  | Sprint 3 | [22 empty] | Sprint 3 UAT |  |  |  |  | Sprint 4 | [22 empty] | Sprint 4 UAT |  |  |  |  | Sprint 5 | [22 empty] | Sprint 5 UAT |  |  |  |  | Sprint 6 | [22 empty] | Sprint 6 UAT |  |  |  |  | Sprint 7 | [22 empty] | Sprint 7 | [20 empty] | Sprint 7 UAT | [6 empty] | Sprint 8 | [20 empty] | Sprint 8 UAT | [6 empty] | Sprint 9 | [20 empty] | Sprint 9 UAT | [6 empty] | Sprint 10 | [20 empty] | Sprint 10 UAT | [6 empty] | Sprint 11 | [20 empty] | Sprint 11 UAT | [6 empty] | Sprint 12 | [20 empty] | Sprint 12 UAT | [6 empty] | Sprint 13 | [27 empty] | Sprint 13 UAT | [6 empty] | Sprint 14 | [20 empty] | Sprint 14 UAT | [6 empty] | Sprint 15 | [20 empty] | Sprint 15 UAT | [6 empty] | Sprint 16 | [20 empty] | Sprint 16 UAT
 | time axis 2024-07-15 to 2025-10-12
 | time axis 2024-07-15 to 2025-10-12
Open Box | 2024-07-15: Build (Dev & Test) / UAT Feedback; 2024-07-22: Build (Dev & Test); 2024-07-29: Build (Dev & Test); 2024-08-05: Build (Dev & Test); 2024-08-12: Build (Dev & Test) / UAT Feedback; 2024-08-19: Build (Dev & Test); 2024-08-26: Build (Dev & Test); 2024-09-02: Build (Dev & Test); 2024-09-09: Build (Dev & Test) / UAT Feedback; 2024-09-16: Build (Dev & Test); 2024-09-23: Build (Dev & Test); 2024-09-30: Build (Dev & Test); 2024-10-07: Build (Dev & Test) / UAT Feedback; 2024-10-14: Build (Dev & Test); 2024-10-21: Build (Dev & Test); 2024-10-28: Build (Dev & Test); 2024-11-04: Build (Dev & Test) / UAT Feedback; 2024-11-11: Build (Dev & Test); 2024-11-18: Build (Dev & Test); 2024-11-25: Build (Dev & Test); 2024-12-02: Build (Dev & Test) / UAT Feedback; 2024-12-09: Build (Dev & Test); 2024-12-16: Build (Dev & Test); 2024-12-23: Build (Dev & Test); 2024-12-30: Build (Dev & Test); 2025-01-06: Build (Dev & Test); 2025-01-13: Build (Dev & Test); 2025-01-20: Build (Dev & Test) / UAT Feedback; 2025-01-27: Build (Dev & Test); 2025-02-03: Build (Dev & Test); 2025-02-10: Build (Dev & Test); 2025-02-17: Build (Dev & Test) / UAT Feedback; 2025-02-24: Build (Dev & Test); 2025-03-03: Build (Dev & Test); 2025-03-10: Build (Dev & Test); 2025-03-17: Build (Dev & Test) / UAT Feedback; 2025-03-24: Build (Dev & Test); 2025-03-31: Build (Dev & Test); 2025-04-07: Build (Dev & Test); 2025-04-14: Build (Dev & Test) / UAT Feedback; 2025-04-21: Build (Dev & Test); 2025-04-28: Build (Dev & Test); 2025-05-05: Build (Dev & Test); 2025-05-12: Build (Dev & Test) / UAT Feedback; 2025-05-19: Build (Dev & Test); 2025-05-26: Build (Dev & Test); 2025-06-02: Build (Dev & Test); 2025-06-09: Build (Dev & Test) / UAT Feedback; 2025-06-16: Build (Dev & Test); 2025-06-23: Build (Dev & Test); 2025-06-30: Build (Dev & Test); 2025-07-07: Build (Dev & Test); 2025-07-14: Build (Dev & Test) / UAT Feedback; 2025-07-21: Build (Dev & Test); 2025-07-28: Build (Dev & Test); 2025-08-04: Build (Dev & Test); 2025-08-11: Build (Dev & Test) / UAT Feedback; 2025-08-18: Build (Dev & Test); 2025-08-25: Build (Dev & Test); 2025-09-01: Build (Dev & Test); 2025-09-08: Build (Dev & Test) / UAT Feedback; 2025-09-15: Build (Dev & Test); 2025-09-22: Build (Dev & Test); 2025-09-29: Build (Dev & Test); 2025-10-06: Build (Dev & Test) / UAT Feedback
Grainger Business Users | 2024-07-15: Sprint 1 UAT; 2024-07-18: Final Testing+ Release Sign-off; 2024-08-12: Sprint 2 UAT; 2024-08-15: Final Testing+ Release Sign-off; 2024-08-26: UK Bank Holiday; 2024-09-09: Sprint 3 UAT; 2024-09-12: Final Testing+ Release Sign-off; 2024-10-07: Sprint 2 UAT; 2024-10-10: Final Testing+ Release Sign-off; 2024-11-04: Sprint 5 UAT; 2024-11-07: Final Testing+ Release Sign-off; 2024-12-02: Sprint 6 UAT; 2024-12-05: Final Testing+ Release Sign-off; 2025-01-20: Sprint 7 UAT; 2025-01-23: Final Testing+ Release Sign-off; 2025-02-17: Sprint 8 UAT; 2025-02-20: Final Testing+ Release Sign-off; 2025-03-17: Sprint 9 UAT; 2025-03-20: Final Testing+ Release Sign-off; 2025-04-14: Sprint 10 UAT; 2025-04-17: Final Testing+ Release Sign-off; 2025-05-12: Sprint 11 UAT; 2025-05-15: Final Testing+ Release Sign-off; 2025-06-09: Sprint 12 UAT; 2025-06-12: Final Testing+ Release Sign-off; 2025-07-14: Sprint 13 UAT; 2025-07-17: Final Testing+ Release Sign-off; 2025-08-11: Sprint 14 UAT; 2025-08-14: Final Testing+ Release Sign-off; 2025-09-08: Sprint 13 UAT; 2025-09-11: Final Testing+ Release Sign-off; 2025-10-06: Sprint 13 UAT; 2025-10-09: Final Testing+ Release Sign-off
Grainger Meetings | 2024-07-17: Last Item logged; 2024-07-18: CAB* Signoff on Sprint 2 scope + hotfixes; 2024-07-25: CAB* Signoff on hotfixes; 2024-08-01: CAB* Signoff on hotfixes; 2024-08-08: CAB* Signoff on hotfixes; 2024-08-14: Last Item logged; 2024-08-15: CAB* Signoff on Sprint 3 scope + hotfixes; 2024-08-22: CAB* Signoff on hotfixes; 2024-08-29: CAB* Signoff on hotfixes; 2024-09-05: CAB* Signoff on hotfixes; 2024-09-11: Last Item logged; 2024-09-12: CAB* Signoff on Sprint 4 scope + hotfixes; 2024-09-19: CAB* Signoff on hotfixes; 2024-09-26: CAB* Signoff on hotfixes; 2024-10-03: CAB* Signoff on hotfixes; 2024-10-09: Last Item logged; 2024-10-10: CAB* Signoff on Sprint 3 scope + hotfixes; 2024-10-17: CAB* Signoff on hotfixes; 2024-10-24: CAB* Signoff on hotfixes; 2024-10-31: CAB* Signoff on hotfixes; 2024-11-06: Last Item logged; 2024-11-07: CAB* Signoff on Sprint 6 scope + hotfixes; 2024-11-14: CAB* Signoff on hotfixes; 2024-11-21: CAB* Signoff on hotfixes; 2024-11-28: CAB* Signoff on hotfixes; 2024-12-04: Last Item logged; 2024-12-05: CAB* Signoff on Sprint 7 scope + hotfixes; 2024-12-12: CAB* Signoff on hotfixes; 2024-12-19: CAB* Signoff on hotfixes; 2024-12-26: CAB* Signoff on hotfixes; 2025-01-02: CAB* Signoff on hotfixes; 2025-01-09: CAB* Signoff on hotfixes; 2025-01-16: CAB* Signoff on hotfixes; 2025-01-22: Last Item logged; 2025-01-23: CAB* Signoff on Sprint 8 scope + hotfixes; 2025-01-30: CAB* Signoff on hotfixes; 2025-02-06: CAB* Signoff on hotfixes; 2025-02-13: CAB* Signoff on hotfixes; 2025-02-19: Last Item logged; 2025-02-20: CAB* Signoff on Sprint 9 scope + hotfixes; 2025-02-27: CAB* Signoff on hotfixes; 2025-03-06: CAB* Signoff on hotfixes; 2025-03-13: CAB* Signoff on hotfixes; 2025-03-19: Last Item logged; 2025-03-20: CAB* Signoff on Sprint 10 scope + hotfixes; 2025-03-27: CAB* Signoff on hotfixes; 2025-04-03: CAB* Signoff on hotfixes; 2025-04-10: CAB* Signoff on hotfixes; 2025-04-16: Last Item logged; 2025-04-17: CAB* Signoff on Sprint 11 scope + hotfixes; 2025-04-24: CAB* Signoff on hotfixes; 2025-05-01: CAB* Signoff on hotfixes; 2025-05-08: CAB* Signoff on hotfixes; 2025-05-14: Last Item logged; 2025-05-15: CAB* Signoff on Sprint 12 scope + hotfixes; 2025-05-22: CAB* Signoff on hotfixes; 2025-05-29: CAB* Signoff on hotfixes; 2025-06-05: CAB* Signoff on hotfixes; 2025-06-11: Last Item logged; 2025-06-12: CAB* Signoff on Sprint 13 scope + hotfixes; 2025-06-19: CAB* Signoff on hotfixes; 2025-06-26: CAB* Signoff on hotfixes; 2025-07-03: CAB* Signoff on hotfixes; 2025-07-10: CAB* Signoff on hotfixes; 2025-07-16: Last Item logged; 2025-07-17: CAB* Signoff on Sprint 14 scope + hotfixes; 2025-07-24: CAB* Signoff on hotfixes; 2025-07-31: CAB* Signoff on hotfixes; 2025-08-07: CAB* Signoff on hotfixes; 2025-08-13: Last Item logged; 2025-08-14: CAB* Signoff on Sprint 15 scope + hotfixes; 2025-08-21: CAB* Signoff on hotfixes; 2025-08-28: CAB* Signoff on hotfixes; 2025-09-04: CAB* Signoff on hotfixes; 2025-09-10: Last Item logged; 2025-09-11: CAB* Signoff on Sprint 14 scope + hotfixes; 2025-09-18: CAB* Signoff on hotfixes; 2025-09-25: CAB* Signoff on hotfixes; 2025-10-02: CAB* Signoff on hotfixes; 2025-10-08: Last Item logged; 2025-10-09: CAB* Signoff on Sprint 14 scope + hotfixes
SIT & UAT Deployments | 2024-07-15: Open Box Team; 2024-08-12: Open Box Team; 2024-09-09: Open Box Team; 2024-10-07: Open Box Team; 2024-11-04: Open Box Team; 2024-12-02: Open Box Team; 2025-01-20: Open Box Team; 2025-02-17: Open Box Team; 2025-03-17: Open Box Team; 2025-04-14: Open Box Team; 2025-05-12: Open Box Team; 2025-06-09: Open Box Team; 2025-07-14: Open Box Team; 2025-08-11: Open Box Team; 2025-09-08: Open Box Team; 2025-10-06: Open Box Team
Prod Deployments - Releases | 2024-07-22: 2024-07-22 Release; 2024-08-19: 2024-08-19 Release; 2024-09-16: 2024-09-16 Release; 2024-10-14: 2024-10-14 Release; 2024-11-11: 2024-11-11 Release; 2024-12-09: 2024-12-09 Release; 2025-01-27: 2025-01-27 Release; 2025-02-24: 2025-02-24 Release; 2025-03-24: 2024-03-24 Release; 2025-04-21: 2025-04-21 Release; 2025-05-19: 2025-05-19 Release; 2025-06-16: 2025-06-16 Release; 2025-07-21: 2025-07-21 Release; 2025-08-18: 2025-08-18 Release; 2025-09-15: 2025-09-15 Release
Client Meetings | 2024-07-15: Weekly Progress Update & UAT Kickoff; 2024-07-16: Refinement - Ad-hoc; 2024-07-18: Refinement - Ad-hoc; 2024-07-22: Sprint Review; 2024-07-23: Refinement - Ad-hoc; 2024-07-25: Refinement - Ad-hoc; 2024-07-29: Weekly Progress Update; 2024-07-30: Refinement - Ad-hoc; 2024-08-01: Refinement - Ad-hoc; 2024-08-05: Weekly Progress Update; 2024-08-06: Refinement - Ad-hoc; 2024-08-08: Refinement - Ad-hoc; 2024-08-12: Weekly Progress Update & UAT Kickoff; 2024-08-13: Refinement - Ad-hoc; 2024-08-15: Refinement - Ad-hoc; 2024-08-19: Sprint Review; 2024-08-20: Refinement - Ad-hoc; 2024-08-22: Refinement - Ad-hoc; 2024-08-27: Refinement - Ad-hoc; 2024-08-29: Refinement - Ad-hoc; 2024-09-02: Weekly Progress Update; 2024-09-03: Refinement - Ad-hoc; 2024-09-05: Refinement - Ad-hoc; 2024-09-09: Weekly Progress Update & UAT Kickoff; 2024-09-10: Refinement - Ad-hoc; 2024-09-12: Refinement - Ad-hoc; 2024-09-16: Sprint Review; 2024-09-17: Refinement - Ad-hoc; 2024-09-19: Refinement - Ad-hoc; 2024-09-23: Weekly Progress Update; 2024-09-24: Refinement - Ad-hoc; 2024-09-26: Refinement - Ad-hoc; 2024-09-30: Weekly Progress Update; 2024-10-01: Refinement - Ad-hoc; 2024-10-03: Refinement - Ad-hoc; 2024-10-07: Weekly Progress Update & UAT Kickoff; 2024-10-08: Refinement - Ad-hoc; 2024-10-10: Refinement - Ad-hoc; 2024-10-14: Sprint Review; 2024-10-15: Refinement - Ad-hoc; 2024-10-17: Refinement - Ad-hoc; 2024-10-21: Weekly Progress Update; 2024-10-22: Refinement - Ad-hoc; 2024-10-24: Refinement - Ad-hoc; 2024-10-28: Weekly Progress Update; 2024-10-29: Refinement - Ad-hoc; 2024-10-31: Refinement - Ad-hoc; 2024-11-04: Weekly Progress Update & UAT Kickoff; 2024-11-05: Refinement - Ad-hoc; 2024-11-07: Refinement - Ad-hoc; 2024-11-11: Sprint Review; 2024-11-12: Refinement - Ad-hoc; 2024-11-14: Refinement - Ad-hoc; 2024-11-18: Weekly Progress Update; 2024-11-19: Refinement - Ad-hoc; 2024-11-21: Refinement - Ad-hoc; 2024-11-25: Weekly Progress Update; 2024-11-26: Refinement - Ad-hoc; 2024-11-28: Refinement - Ad-hoc; 2024-12-02: Weekly Progress Update & UAT Kickoff; 2024-12-03: Refinement - Ad-hoc; 2024-12-05: Refinement - Ad-hoc; 2024-12-09: Sprint Review; 2024-12-10: Refinement - Ad-hoc; 2024-12-12: Refinement - Ad-hoc; 2024-12-16: Weekly Progress Update; 2024-12-17: Refinement - Ad-hoc; 2024-12-19: Refinement - Ad-hoc; 2024-12-23: Weekly Progress Update; 2024-12-24: Refinement - Ad-hoc; 2024-12-26: Refinement - Ad-hoc; 2024-12-30: Weekly Progress Update; 2024-12-31: Refinement - Ad-hoc; 2025-01-02: Refinement - Ad-hoc; 2025-01-06: Weekly Progress Update; 2025-01-07: Refinement - Ad-hoc; 2025-01-09: Refinement - Ad-hoc; 2025-01-13: Weekly Progress Update; 2025-01-14: Refinement - Ad-hoc; 2025-01-16: Refinement - Ad-hoc; 2025-01-20: Weekly Progress Update & UAT Kickoff; 2025-01-21: Refinement - Ad-hoc; 2025-01-23: Refinement - Ad-hoc; 2025-01-27: Sprint Review; 2025-01-28: Refinement - Ad-hoc; 2025-01-30: Refinement - Ad-hoc; 2025-02-03: Weekly Progress Update; 2025-02-04: Refinement - Ad-hoc; 2025-02-06: Refinement - Ad-hoc; 2025-02-10: Weekly Progress Update; 2025-02-11: Refinement - Ad-hoc; 2025-02-13: Refinement - Ad-hoc; 2025-02-17: Weekly Progress Update & UAT Kickoff; 2025-02-18: Refinement - Ad-hoc; 2025-02-20: Refinement - Ad-hoc; 2025-02-24: Sprint Review; 2025-02-25: Refinement - Ad-hoc; 2025-02-27: Refinement - Ad-hoc; 2025-03-03: Weekly Progress Update; 2025-03-04: Refinement - Ad-hoc; 2025-03-06: Refinement - Ad-hoc; 2025-03-10: Weekly Progress Update; 2025-03-11: Refinement - Ad-hoc; 2025-03-13: Refinement - Ad-hoc; 2025-03-17: Weekly Progress Update & UAT Kickoff; 2025-03-18: Refinement - Ad-hoc; 2025-03-20: Refinement - Ad-hoc; 2025-03-24: Sprint Review; 2025-03-25: Refinement - Ad-hoc; 2025-03-27: Refinement - Ad-hoc; 2025-03-31: Weekly Progress Update; 2025-04-01: Refinement - Ad-hoc; 2025-04-03: Refinement - Ad-hoc; 2025-04-07: Weekly Progress Update; 2025-04-08: Refinement - Ad-hoc; 2025-04-10: Refinement - Ad-hoc; 2025-04-14: Weekly Progress Update & UAT Kickoff; 2025-04-15: Refinement - Ad-hoc; 2025-04-17: Refinement - Ad-hoc; 2025-04-21: Sprint Review; 2025-04-22: Refinement - Ad-hoc; 2025-04-24: Refinement - Ad-hoc; 2025-04-28: Weekly Progress Update; 2025-04-29: Refinement - Ad-hoc; 2025-05-01: Refinement - Ad-hoc; 2025-05-05: Weekly Progress Update; 2025-05-06: Refinement - Ad-hoc; 2025-05-08: Refinement - Ad-hoc; 2025-05-12: Weekly Progress Update & UAT Kickoff; 2025-05-13: Refinement - Ad-hoc; 2025-05-15: Refinement - Ad-hoc; 2025-05-19: Sprint Review; 2025-05-20: Refinement - Ad-hoc; 2025-05-22: Refinement - Ad-hoc; 2025-05-26: Weekly Progress Update; 2025-05-27: Refinement - Ad-hoc; 2025-05-29: Refinement - Ad-hoc; 2025-06-02: Weekly Progress Update; 2025-06-03: Refinement - Ad-hoc; 2025-06-05: Refinement - Ad-hoc; 2025-06-09: Weekly Progress Update & UAT Kickoff; 2025-06-10: Refinement - Ad-hoc; 2025-06-12: Refinement - Ad-hoc; 2025-06-16: Sprint Review; 2025-06-17: Refinement - Ad-hoc; 2025-06-19: Refinement - Ad-hoc; 2025-06-23: Weekly Progress Update; 2025-06-24: Refinement - Ad-hoc; 2025-06-26: Refinement - Ad-hoc; 2025-06-30: Weekly Progress Update; 2025-07-01: Refinement - Ad-hoc; 2025-07-03: Refinement - Ad-hoc; 2025-07-07: Weekly Progress Update; 2025-07-08: Refinement - Ad-hoc; 2025-07-10: Refinement - Ad-hoc; 2025-07-14: Weekly Progress Update & UAT Kickoff; 2025-07-15: Refinement - Ad-hoc; 2025-07-17: Refinement - Ad-hoc; 2025-07-21: Sprint Review; 2025-07-22: Refinement - Ad-hoc; 2025-07-24: Refinement - Ad-hoc; 2025-07-28: Weekly Progress Update; 2025-07-29: Refinement - Ad-hoc; 2025-07-31: Refinement - Ad-hoc; 2025-08-04: Weekly Progress Update; 2025-08-05: Refinement - Ad-hoc; 2025-08-07: Refinement - Ad-hoc; 2025-08-11: Weekly Progress Update & UAT Kickoff; 2025-08-12: Refinement - Ad-hoc; 2025-08-14: Refinement - Ad-hoc; 2025-08-18: Sprint Review; 2025-08-19: Refinement - Ad-hoc; 2025-08-21: Refinement - Ad-hoc; 2025-08-25: Weekly Progress Update; 2025-08-26: Refinement - Ad-hoc; 2025-08-28: Refinement - Ad-hoc; 2025-09-01: Weekly Progress Update; 2025-09-02: Refinement - Ad-hoc; 2025-09-04: Refinement - Ad-hoc; 2025-09-08: Weekly Progress Update & UAT Kickoff; 2025-09-09: Refinement - Ad-hoc; 2025-09-11: Refinement - Ad-hoc; 2025-09-15: Sprint Review; 2025-09-16: Refinement - Ad-hoc; 2025-09-18: Refinement - Ad-hoc; 2025-09-22: Weekly Progress Update; 2025-09-23: Refinement - Ad-hoc; 2025-09-25: Refinement - Ad-hoc; 2025-09-29: Weekly Progress Update; 2025-09-30: Refinement - Ad-hoc; 2025-10-02: Refinement - Ad-hoc; 2025-10-06: Weekly Progress Update & UAT Kickoff; 2025-10-07: Refinement - Ad-hoc; 2025-10-09: Refinement - Ad-hoc
Internal Meetings exlc stand up | 2024-08-12: UAT depl. review; 2024-08-13: IA & Preview; 2024-08-16: Sprint Close Out Report; 2024-09-09: UAT depl. review; 2024-09-10: IA & Preview; 2024-09-13: Sprint Close Out Report; 2024-10-07: UAT depl. review; 2024-10-08: IA & Preview; 2024-10-11: Sprint Close Out Report; 2024-11-04: UAT depl. review; 2024-11-05: IA & Preview; 2024-11-08: Sprint Close Out Report; 2024-12-02: UAT depl. review; 2024-12-03: IA & Preview; 2024-12-06: Sprint Close Out Report
Grainger Hotfix Testing | 2024-07-26: Hotfix user testing Signoff; 2024-08-02: Hotfix user testing Signoff; 2024-08-09: Hotfix user testing Signoff; 2024-08-23: Hotfix user testing Signoff; 2024-08-30: Hotfix user testing Signoff; 2024-09-06: Hotfix user testing Signoff; 2024-09-20: Hotfix user testing Signoff; 2024-09-27: Hotfix user testing Signoff; 2024-10-04: Hotfix user testing Signoff; 2024-10-18: Hotfix user testing Signoff; 2024-10-25: Hotfix user testing Signoff; 2024-11-01: Hotfix user testing Signoff; 2024-11-15: Hotfix user testing Signoff; 2024-11-22: Hotfix user testing Signoff; 2024-11-29: Hotfix user testing Signoff; 2024-12-13: Hotfix user testing Signoff; 2024-12-20: Hotfix user testing Signoff; 2024-12-27: Hotfix user testing Signoff; 2025-01-03: Hotfix user testing Signoff; 2025-01-10: Hotfix user testing Signoff; 2025-01-17: Hotfix user testing Signoff; 2025-01-31: Hotfix user testing Signoff; 2025-02-07: Hotfix user testing Signoff; 2025-02-14: Hotfix user testing Signoff; 2025-02-28: Hotfix user testing Signoff; 2025-03-07: Hotfix user testing Signoff; 2025-03-14: Hotfix user testing Signoff; 2025-03-28: Hotfix user testing Signoff; 2025-04-04: Hotfix user testing Signoff; 2025-04-11: Hotfix user testing Signoff; 2025-04-25: Hotfix user testing Signoff; 2025-05-02: Hotfix user testing Signoff; 2025-05-09: Hotfix user testing Signoff; 2025-05-23: Hotfix user testing Signoff; 2025-05-30: Hotfix user testing Signoff; 2025-06-06: Hotfix user testing Signoff; 2025-06-20: Hotfix user testing Signoff; 2025-06-27: Hotfix user testing Signoff; 2025-07-04: Hotfix user testing Signoff; 2025-07-11: Hotfix user testing Signoff; 2025-07-25: Hotfix user testing Signoff; 2025-08-01: Hotfix user testing Signoff; 2025-08-08: Hotfix user testing Signoff; 2025-08-22: Hotfix user testing Signoff; 2025-08-29: Hotfix user testing Signoff; 2025-09-05: Hotfix user testing Signoff; 2025-09-19: Hotfix user testing Signoff; 2025-09-26: Hotfix user testing Signoff; 2025-10-03: Hotfix user testing Signoff
Prod Deployments - Hotfixes | 2024-07-15: Hotfix; 2024-07-29: Hotfix; 2024-08-05: Hotfix; 2024-08-12: Hotfix; 2024-08-27: Hotfix; 2024-09-02: Hotfix; 2024-09-09: Hotfix; 2024-09-23: Hotfix; 2024-09-30: Hotfix; 2024-10-07: Hotfix; 2024-10-21: Hotfix; 2024-10-28: Hotfix; 2024-11-04: Hotfix; 2024-11-18: Hotfix; 2024-11-25: Hotfix; 2024-12-02: Hotfix; 2024-12-16: Hotfix; 2024-12-23: Hotfix; 2024-12-30: Hotfix; 2025-01-06: Hotfix; 2025-01-13: Hotfix; 2025-01-20: Hotfix; 2025-02-03: Hotfix; 2025-02-10: Hotfix; 2025-02-17: Hotfix; 2025-03-03: Hotfix; 2025-03-10: Hotfix; 2025-03-17: Hotfix; 2025-03-31: Hotfix; 2025-04-07: Hotfix; 2025-04-14: Hotfix; 2025-04-28: Hotfix; 2025-05-05: Hotfix; 2025-05-12: Hotfix; 2025-05-26: Hotfix; 2025-06-02: Hotfix; 2025-06-09: Hotfix; 2025-06-23: Hotfix; 2025-06-30: Hotfix; 2025-07-07: Hotfix; 2025-07-14: Hotfix; 2025-07-28: Hotfix; 2025-08-04: Hotfix; 2025-08-11: Hotfix; 2025-08-25: Hotfix; 2025-09-01: Hotfix; 2025-09-08: Hotfix; 2025-09-22: Hotfix; 2025-09-29: Hotfix; 2025-10-06: Hotfix
Team Holiday
Jacob Smycz | 2024-10-25: Leave; 2024-12-16: Availble UK Morning Only; 2024-12-20: Leave; 2024-12-23: Leave; 2024-12-24: Leave; 2024-12-25: Leave; 2024-12-26: Leave; 2024-12-27: Leave
Note on PT2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change Freeze

## Oct 25 - Sep 26 (Sprint 17-29)
Sprint Alignment | Sprint 17 | [20 empty] | Sprint 17 UAT | [6 empty] | Sprint 18 | [20 empty] | Sprint 18 UAT | [6 empty] | Sprint 19 | [20 empty] | Leave Week | [6 empty] | Sprint 20 | [20 empty] | Sprint 20 UAT | [6 empty] | Sprint 21 | [20 empty] | Sprint 21 UAT | [6 empty] | Sprint 22 | [20 empty] | Sprint 22 UAT | [6 empty] | Sprint 23 | [20 empty] | Sprint 23 UAT | [6 empty] | Sprint 24 | [20 empty] | Sprint 24 UAT | [6 empty] | Sprint 25 | [20 empty] | Sprint 25 UAT | [6 empty] | Sprint 26 | [20 empty] | Sprint 26 UAT | [6 empty] | Sprint 27 | [20 empty] | Sprint 27 UAT
 | time axis 2025-10-13 to 2026-10-18
 | time axis 2025-10-13 to 2026-10-18
Open Box | 2025-10-13: Build (Dev & Test); 2025-10-20: Build (Dev & Test); 2025-10-27: Build (Dev & Test); 2025-11-03: Build (Dev & Test) / UAT Feedback; 2025-11-10: Build (Dev & Test); 2025-11-17: Build (Dev & Test); 2025-11-24: Build (Dev & Test); 2025-12-01: Build (Dev & Test) / UAT Feedback; 2025-12-08: Build (Dev & Test); 2025-12-15: Build (Dev & Test); 2025-12-22: Build (Dev & Test); 2025-12-29: Leave Week; 2026-01-05: Build (Dev & Test); 2026-01-12: Build (Dev & Test); 2026-01-19: Build (Dev & Test); 2026-01-26: Build (Dev & Test) / UAT Feedback; 2026-02-02: Build (Dev & Test); 2026-02-09: Build (Dev & Test); 2026-02-16: Build (Dev & Test); 2026-02-23: Build (Dev & Test) / UAT Feedback; 2026-03-02: Build (Dev & Test); 2026-03-09: Build (Dev & Test); 2026-03-16: Build (Dev & Test); 2026-03-23: Build (Dev & Test) / UAT Feedback; 2026-03-30: Build (Dev & Test); 2026-04-06: Build (Dev & Test); 2026-04-13: Build (Dev & Test); 2026-04-20: Build (Dev & Test) / UAT Feedback; 2026-04-27: Build (Dev & Test); 2026-05-04: Build (Dev & Test); 2026-05-11: Build (Dev & Test); 2026-05-18: Build (Dev & Test) / UAT Feedback; 2026-05-25: Build (Dev & Test); 2026-06-01: Build (Dev & Test); 2026-06-08: Build (Dev & Test); 2026-06-15: Build (Dev & Test) / UAT Feedback; 2026-06-22: Build (Dev & Test); 2026-06-29: Build (Dev & Test); 2026-07-06: Build (Dev & Test); 2026-07-13: Build (Dev & Test) / UAT Feedback; 2026-07-20: Build (Dev & Test); 2026-07-27: Build (Dev & Test); 2026-08-03: Build (Dev & Test); 2026-08-10: Build (Dev & Test) / UAT Feedback; 2026-08-17: Build (Dev & Test); 2026-08-24: Build (Dev & Test); 2026-08-31: Build (Dev & Test); 2026-09-07: Build (Dev & Test) / UAT Feedback; 2026-09-14: Build (Dev & Test); 2026-09-21: Build (Dev & Test); 2026-09-28: Build (Dev & Test); 2026-10-05: Build (Dev & Test) / UAT Feedback; 2026-10-12: Build (Dev & Test)
Grainger Business Users | 2025-11-03: Sprint 17 UAT; 2025-11-06: Final Testing+ Release Sign-off; 2025-12-01: Sprint 13 UAT; 2025-12-04: Final Testing+ Release Sign-off; 2026-01-26: Sprint 20 UAT; 2026-01-29: Final Testing+ Release Sign-off; 2026-02-23: Sprint 13 UAT; 2026-02-26: Final Testing+ Release Sign-off; 2026-03-23: Sprint 13 UAT; 2026-03-26: Final Testing+ Release Sign-off; 2026-04-20: Sprint 13 UAT; 2026-04-23: Final Testing+ Release Sign-off; 2026-05-18: Sprint 13 UAT; 2026-05-21: Final Testing+ Release Sign-off; 2026-06-15: Sprint 13 UAT; 2026-06-18: Final Testing+ Release Sign-off; 2026-07-13: Sprint 13 UAT; 2026-07-16: Final Testing+ Release Sign-off; 2026-08-10: Sprint 13 UAT; 2026-08-13: Final Testing+ Release Sign-off; 2026-09-07: Sprint 13 UAT; 2026-09-10: Final Testing+ Release Sign-off; 2026-10-05: Sprint 13 UAT; 2026-10-08: Final Testing+ Release Sign-off
Grainger Meetings | 2025-10-16: CAB* Signoff on hotfixes; 2025-10-23: CAB* Signoff on hotfixes; 2025-10-30: CAB* Signoff on hotfixes; 2025-11-05: Last Item logged; 2025-11-06: CAB* Signoff on Sprint 14 scope + hotfixes; 2025-11-13: CAB* Signoff on hotfixes; 2025-11-20: CAB* Signoff on hotfixes; 2025-11-27: CAB* Signoff on hotfixes; 2025-12-03: Last Item logged; 2025-12-08: CAB* Signoff on hotfixes; 2025-12-15: CAB* Signoff on hotfixes; 2025-12-19: Signoff on Sprint 20 Items; 2025-12-22: CAB* Signoff on hotfixes; 2026-01-05: CAB* Signoff on hotfixes; 2026-01-12: CAB* Signoff on hotfixes; 2026-01-19: CAB* Signoff on hotfixes; 2026-01-26: CAB* Signoff on Sprint 14 scope + hotfixes; 2026-01-28: Last Item logged; 2026-02-05: CAB* Signoff on hotfixes; 2026-02-12: CAB* Signoff on hotfixes; 2026-02-19: CAB* Signoff on hotfixes; 2026-02-25: Last Item logged; 2026-02-26: CAB* Signoff on Sprint 14 scope + hotfixes; 2026-03-05: CAB* Signoff on hotfixes; 2026-03-12: CAB* Signoff on hotfixes; 2026-03-19: CAB* Signoff on hotfixes; 2026-03-25: Last Item logged; 2026-03-26: CAB* Signoff on Sprint 14 scope + hotfixes; 2026-04-02: CAB* Signoff on hotfixes; 2026-04-09: CAB* Signoff on hotfixes; 2026-04-16: CAB* Signoff on hotfixes; 2026-04-22: Last Item logged; 2026-04-23: CAB* Signoff on Sprint 14 scope + hotfixes; 2026-04-30: CAB* Signoff on hotfixes; 2026-05-07: CAB* Signoff on hotfixes; 2026-05-14: CAB* Signoff on hotfixes; 2026-05-20: Last Item logged; 2026-05-21: CAB* Signoff on Sprint 14 scope + hotfixes; 2026-05-28: CAB* Signoff on hotfixes; 2026-06-04: CAB* Signoff on hotfixes; 2026-06-11: CAB* Signoff on hotfixes; 2026-06-17: Last Item logged; 2026-06-18: CAB* Signoff on Sprint 14 scope + hotfixes; 2026-06-25: CAB* Signoff on hotfixes; 2026-07-02: CAB* Signoff on hotfixes; 2026-07-09: CAB* Signoff on hotfixes; 2026-07-15: Last Item logged; 2026-07-16: CAB* Signoff on Sprint 14 scope + hotfixes; 2026-07-23: CAB* Signoff on hotfixes; 2026-07-30: CAB* Signoff on hotfixes; 2026-08-06: CAB* Signoff on hotfixes; 2026-08-12: Last Item logged; 2026-08-13: CAB* Signoff on Sprint 14 scope + hotfixes; 2026-08-20: CAB* Signoff on hotfixes; 2026-08-27: CAB* Signoff on hotfixes; 2026-09-03: CAB* Signoff on hotfixes; 2026-09-09: Last Item logged; 2026-09-10: CAB* Signoff on Sprint 14 scope + hotfixes; 2026-09-17: CAB* Signoff on hotfixes; 2026-09-24: CAB* Signoff on hotfixes; 2026-10-01: CAB* Signoff on hotfixes; 2026-10-07: Last Item logged; 2026-10-08: CAB* Signoff on Sprint 14 scope + hotfixes; 2026-10-15: CAB* Signoff on hotfixes
UAT Deployments | 2025-11-03: Open Box Team; 2025-12-01: Open Box Team; 2026-01-19: Open Box Team Sprint 19; 2026-01-26: Open Box Team Sprint 20; 2026-02-23: Open Box Team; 2026-03-23: Open Box Team; 2026-04-20: Open Box Team; 2026-05-18: Open Box Team; 2026-06-15: Open Box Team; 2026-07-13: Open Box Team; 2026-08-10: Open Box Team; 2026-09-07: Open Box Team; 2026-10-05: Open Box Team
Prod Deployments - Releases | 2025-10-13: 2025-10-13 Release; 2025-11-10: 2025-11-10 Release; 2025-12-08: 2025-12-08 Release; 2026-02-02: 2025-07-21 Release; 2026-03-02: 2025-07-21 Release; 2026-03-30: 2025-07-21 Release; 2026-04-27: 2025-07-21 Release; 2026-05-25: 2025-07-21 Release; 2026-06-22: 2025-07-21 Release; 2026-07-20: 2025-07-21 Release; 2026-08-17: 2025-07-21 Release; 2026-09-14: 2025-07-21 Release; 2026-10-12: 2025-07-21 Release
Client Meetings | 2025-10-13: Sprint Review; 2025-10-14: Refinement - Ad-hoc; 2025-10-16: Refinement - Ad-hoc; 2025-10-20: Weekly Progress Update; 2025-10-21: Refinement - Ad-hoc; 2025-10-23: Refinement - Ad-hoc; 2025-10-27: Weekly Progress Update; 2025-10-28: Refinement - Ad-hoc; 2025-10-30: Refinement - Ad-hoc; 2025-11-03: Weekly Progress Update & UAT Kickoff; 2025-11-04: Refinement - Ad-hoc; 2025-11-06: Refinement - Ad-hoc; 2025-11-10: Sprint Review; 2025-11-11: Refinement - Ad-hoc; 2025-11-13: Refinement - Ad-hoc; 2025-11-17: Weekly Progress Update; 2025-11-18: Refinement - Ad-hoc; 2025-11-20: Refinement - Ad-hoc; 2025-11-24: Weekly Progress Update; 2025-11-25: Refinement - Ad-hoc; 2025-11-27: Refinement - Ad-hoc; 2025-12-01: Weekly Progress Update & UAT Kickoff; 2025-12-02: Refinement - Ad-hoc; 2025-12-04: Refinement - Ad-hoc; 2025-12-08: Sprint Review; 2025-12-09: Refinement - Ad-hoc; 2025-12-11: Refinement - Ad-hoc; 2025-12-15: Weekly Progress Update; 2025-12-16: Refinement - Ad-hoc; 2025-12-18: Refinement - Ad-hoc; 2025-12-22: Weekly Progress Update; 2025-12-23: Refinement - Ad-hoc; 2025-12-25: Refinement - Ad-hoc; 2026-01-05: Sprint Review; 2026-01-06: Refinement - Ad-hoc; 2026-01-08: Refinement - Ad-hoc; 2026-01-12: Weekly Progress Update; 2026-01-13: Refinement - Ad-hoc; 2026-01-15: Refinement - Ad-hoc; 2026-01-19: Weekly Progress Update; 2026-01-20: Refinement - Ad-hoc; 2026-01-22: Refinement - Ad-hoc; 2026-01-26: Weekly Progress Update & UAT Kickoff; 2026-01-27: Refinement - Ad-hoc; 2026-01-29: Refinement - Ad-hoc; 2026-02-02: Sprint Review; 2026-02-03: Refinement - Ad-hoc; 2026-02-05: Refinement - Ad-hoc; 2026-02-09: Weekly Progress Update; 2026-02-10: Refinement - Ad-hoc; 2026-02-12: Refinement - Ad-hoc; 2026-02-16: Weekly Progress Update; 2026-02-17: Refinement - Ad-hoc; 2026-02-19: Refinement - Ad-hoc; 2026-02-23: Weekly Progress Update & UAT Kickoff; 2026-02-24: Refinement - Ad-hoc; 2026-02-26: Refinement - Ad-hoc; 2026-03-02: Sprint Review; 2026-03-03: Refinement - Ad-hoc; 2026-03-05: Refinement - Ad-hoc; 2026-03-09: Weekly Progress Update; 2026-03-10: Refinement - Ad-hoc; 2026-03-12: Refinement - Ad-hoc; 2026-03-16: Weekly Progress Update; 2026-03-17: Refinement - Ad-hoc; 2026-03-19: Refinement - Ad-hoc; 2026-03-23: Weekly Progress Update & UAT Kickoff; 2026-03-24: Refinement - Ad-hoc; 2026-03-26: Refinement - Ad-hoc; 2026-03-30: Sprint Review; 2026-03-31: Refinement - Ad-hoc; 2026-04-02: Refinement - Ad-hoc; 2026-04-06: Weekly Progress Update; 2026-04-07: Refinement - Ad-hoc; 2026-04-09: Refinement - Ad-hoc; 2026-04-13: Weekly Progress Update; 2026-04-14: Refinement - Ad-hoc; 2026-04-16: Refinement - Ad-hoc; 2026-04-20: Weekly Progress Update & UAT Kickoff; 2026-04-21: Refinement - Ad-hoc; 2026-04-23: Refinement - Ad-hoc; 2026-04-27: Sprint Review; 2026-04-28: Refinement - Ad-hoc; 2026-04-30: Refinement - Ad-hoc; 2026-05-04: Weekly Progress Update; 2026-05-05: Refinement - Ad-hoc; 2026-05-07: Refinement - Ad-hoc; 2026-05-11: Weekly Progress Update; 2026-05-12: Refinement - Ad-hoc; 2026-05-14: Refinement - Ad-hoc; 2026-05-18: Weekly Progress Update & UAT Kickoff; 2026-05-19: Refinement - Ad-hoc; 2026-05-21: Refinement - Ad-hoc; 2026-05-25: Sprint Review; 2026-05-26: Refinement - Ad-hoc; 2026-05-28: Refinement - Ad-hoc; 2026-06-01: Weekly Progress Update; 2026-06-02: Refinement - Ad-hoc; 2026-06-04: Refinement - Ad-hoc; 2026-06-08: Weekly Progress Update; 2026-06-09: Refinement - Ad-hoc; 2026-06-11: Refinement - Ad-hoc; 2026-06-15: Weekly Progress Update & UAT Kickoff; 2026-06-16: Refinement - Ad-hoc; 2026-06-18: Refinement - Ad-hoc; 2026-06-22: Sprint Review; 2026-06-23: Refinement - Ad-hoc; 2026-06-25: Refinement - Ad-hoc; 2026-06-29: Weekly Progress Update; 2026-06-30: Refinement - Ad-hoc; 2026-07-02: Refinement - Ad-hoc; 2026-07-06: Weekly Progress Update; 2026-07-07: Refinement - Ad-hoc; 2026-07-09: Refinement - Ad-hoc; 2026-07-13: Weekly Progress Update & UAT Kickoff; 2026-07-14: Refinement - Ad-hoc; 2026-07-16: Refinement - Ad-hoc; 2026-07-20: Sprint Review; 2026-07-21: Refinement - Ad-hoc; 2026-07-23: Refinement - Ad-hoc; 2026-07-27: Weekly Progress Update; 2026-07-28: Refinement - Ad-hoc; 2026-07-30: Refinement - Ad-hoc; 2026-08-03: Weekly Progress Update; 2026-08-04: Refinement - Ad-hoc; 2026-08-06: Refinement - Ad-hoc; 2026-08-10: Weekly Progress Update & UAT Kickoff; 2026-08-11: Refinement - Ad-hoc; 2026-08-13: Refinement - Ad-hoc; 2026-08-17: Sprint Review; 2026-08-18: Refinement - Ad-hoc; 2026-08-20: Refinement - Ad-hoc; 2026-08-24: Weekly Progress Update; 2026-08-25: Refinement - Ad-hoc; 2026-08-27: Refinement - Ad-hoc; 2026-08-31: Weekly Progress Update; 2026-09-01: Refinement - Ad-hoc; 2026-09-03: Refinement - Ad-hoc; 2026-09-07: Weekly Progress Update & UAT Kickoff; 2026-09-08: Refinement - Ad-hoc; 2026-09-10: Refinement - Ad-hoc; 2026-09-14: Sprint Review; 2026-09-15: Refinement - Ad-hoc; 2026-09-17: Refinement - Ad-hoc; 2026-09-21: Weekly Progress Update; 2026-09-22: Refinement - Ad-hoc; 2026-09-24: Refinement - Ad-hoc; 2026-09-28: Weekly Progress Update; 2026-09-29: Refinement - Ad-hoc; 2026-10-01: Refinement - Ad-hoc; 2026-10-05: Weekly Progress Update & UAT Kickoff; 2026-10-06: Refinement - Ad-hoc; 2026-10-08: Refinement - Ad-hoc; 2026-10-12: Sprint Review; 2026-10-13: Refinement - Ad-hoc; 2026-10-15: Refinement - Ad-hoc
Internal Meetings exlc stand up | bar: 2025-10-13 to 2025-10-17; 2025-10-20 to 2025-10-24; 2025-10-27 to 2025-10-31; 2025-11-03 to 2025-11-07; 2025-11-10 to 2025-11-14; 2025-11-17 to 2025-11-21; 2025-11-24 to 2025-11-28; 2025-12-01 to 2025-12-05; 2025-12-08 to 2025-12-12; 2025-12-15 to 2025-12-19; 2025-12-22 to 2025-12-26; 2026-01-05 to 2026-01-09; 2026-01-12 to 2026-01-16; 2026-01-19 to 2026-01-23; 2026-01-26 to 2026-01-30; 2026-02-02 to 2026-02-06; 2026-02-09 to 2026-02-13; 2026-02-16 to 2026-02-20; 2026-02-23 to 2026-02-27; 2026-03-02 to 2026-03-06; 2026-03-09 to 2026-03-13; 2026-03-16 to 2026-03-20; 2026-03-23 to 2026-03-27; 2026-03-30 to 2026-04-03; 2026-04-06 to 2026-04-10; 2026-04-13 to 2026-04-17; 2026-04-20 to 2026-04-24; 2026-04-27 to 2026-05-01; 2026-05-04 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-19; 2026-06-22 to 2026-06-26; 2026-06-29 to 2026-07-03; 2026-07-06 to 2026-07-10; 2026-07-13 to 2026-07-17; 2026-07-20 to 2026-07-24; 2026-07-27 to 2026-07-31; 2026-08-03 to 2026-08-07; 2026-08-10 to 2026-08-14; 2026-08-17 to 2026-08-21; 2026-08-24 to 2026-08-28; 2026-08-31 to 2026-09-04; 2026-09-07 to 2026-09-11; 2026-09-14 to 2026-09-18; 2026-09-21 to 2026-09-25; 2026-09-28 to 2026-10-02; 2026-10-05 to 2026-10-09; 2026-10-12 to 2026-10-16
Grainger Action | 2025-10-17: Hotfix user testing Signoff; 2025-10-24: Hotfix user testing Signoff; 2025-10-31: Hotfix user testing Signoff; 2025-11-14: Hotfix user testing Signoff; 2025-11-21: Hotfix user testing Signoff; 2025-11-28: Hotfix user testing Signoff; 2025-12-12: Hotfix user testing Signoff; 2025-12-19: Hotfix user testing Signoff; 2025-12-26: Hotfix user testing Signoff; 2026-01-09: Hotfix user testing Signoff; 2026-01-16: Hotfix user testing Signoff; 2026-01-23: Hotfix user testing Signoff; 2026-02-06: Hotfix user testing Signoff; 2026-02-13: Hotfix user testing Signoff; 2026-02-20: Hotfix user testing Signoff; 2026-03-06: Hotfix user testing Signoff; 2026-03-13: Hotfix user testing Signoff; 2026-03-20: Hotfix user testing Signoff; 2026-04-03: Hotfix user testing Signoff; 2026-04-10: Hotfix user testing Signoff; 2026-04-17: Hotfix user testing Signoff; 2026-05-01: Hotfix user testing Signoff; 2026-05-08: Hotfix user testing Signoff; 2026-05-15: Hotfix user testing Signoff; 2026-05-29: Hotfix user testing Signoff; 2026-06-05: Hotfix user testing Signoff; 2026-06-12: Hotfix user testing Signoff; 2026-06-26: Hotfix user testing Signoff; 2026-07-03: Hotfix user testing Signoff; 2026-07-10: Hotfix user testing Signoff; 2026-07-24: Hotfix user testing Signoff; 2026-07-31: Hotfix user testing Signoff; 2026-08-07: Hotfix user testing Signoff; 2026-08-21: Hotfix user testing Signoff; 2026-08-28: Hotfix user testing Signoff; 2026-09-04: Hotfix user testing Signoff; 2026-09-18: Hotfix user testing Signoff; 2026-09-25: Hotfix user testing Signoff; 2026-10-02: Hotfix user testing Signoff; 2026-10-16: Hotfix user testing Signoff
Release | 2025-10-20: Hotfix; 2025-10-27: Hotfix; 2025-11-03: Hotfix; 2025-11-17: Hotfix; 2025-11-24: Hotfix; 2025-12-01: Hotfix; 2025-12-15: Hotfix; 2025-12-22: Hotfix; 2026-01-12: Hotfix; 2026-01-19: Hotfix; 2026-01-26: Hotfix; 2026-02-09: Hotfix; 2026-02-16: Hotfix; 2026-02-23: Hotfix; 2026-03-09: Hotfix; 2026-03-16: Hotfix; 2026-03-23: Hotfix; 2026-04-06: Hotfix; 2026-04-13: Hotfix; 2026-04-20: Hotfix; 2026-05-04: Hotfix; 2026-05-11: Hotfix; 2026-05-18: Hotfix; 2026-06-01: Hotfix; 2026-06-08: Hotfix; 2026-06-15: Hotfix; 2026-06-29: Hotfix; 2026-07-06: Hotfix; 2026-07-13: Hotfix; 2026-07-27: Hotfix; 2026-08-03: Hotfix; 2026-08-10: Hotfix; 2026-08-24: Hotfix; 2026-08-31: Hotfix; 2026-09-07: Hotfix; 2026-09-21: Hotfix; 2026-09-28: Hotfix; 2026-10-05: Hotfix

## 2025 (hidden)
Sprint Alignment | Sprint 7 UAT |  |  |  |  | Sprint 8 | [22 empty] | Sprint 8 UAT |  |  |  |  | Sprint 9 | [22 empty] | Sprint 9 UAT |  |  |  |  | Sprint 10 | [22 empty] | Sprint 10 UAT
 | time axis 2025-01-06 to 2025-04-07
 | time axis 2025-01-06 to 2025-04-07
Open Box | 2025-01-06: Build (Dev & Test) / UAT Feedback; 2025-01-13: Build (Dev & Test); 2025-01-20: Build (Dev & Test); 2025-01-27: Build (Dev & Test); 2025-02-03: Build (Dev & Test) / UAT Feedback; 2025-02-10: Build (Dev & Test); 2025-02-17: Build (Dev & Test); 2025-02-24: Build (Dev & Test); 2025-03-03: Build (Dev & Test) / UAT Feedback; 2025-03-10: Build (Dev & Test); 2025-03-17: Build (Dev & Test); 2025-03-24: Build (Dev & Test); 2025-03-31: Build (Dev & Test) / UAT Feedback; 2025-04-07: Build (Dev & Test) |  |  |  | Build (Dev & Test) |  |  |  | Build (Dev & Test)
Grainger Business Users | 2025-01-06: Sprint 7 UAT; 2025-01-09: Final Testing+ Release Sign-off; 2025-02-03: Sprint 8 UAT; 2025-02-06: Final Testing+ Release Sign-off; 2025-03-03: Sprint 9 UAT; 2025-03-06: Final Testing+ Release Sign-off; 2025-03-31: Sprint 10 UAT; 2025-04-03: Final Testing+ Release Sign-off
Grainger Meetings | 2025-01-08: Last Item logged; 2025-01-09: CAB* Signoff on Sprint 8 scope + hotfixes; 2025-01-16: CAB* Signoff on hotfixes; 2025-01-23: CAB* Signoff on hotfixes; 2025-01-30: CAB* Signoff on hotfixes; 2025-02-05: Last Item logged; 2025-02-06: CAB* Signoff on Sprint 9 scope + hotfixes; 2025-02-13: CAB* Signoff on hotfixes; 2025-02-20: CAB* Signoff on hotfixes; 2025-02-27: CAB* Signoff on hotfixes; 2025-03-05: Last Item logged; 2025-03-06: CAB* Signoff on Sprint 10 scope + hotfixes; 2025-03-13: CAB* Signoff on hotfixes; 2025-03-20: CAB* Signoff on hotfixes; 2025-03-27: CAB* Signoff on hotfixes; 2025-04-02: Last Item logged; 2025-04-03: CAB* Signoff on Sprint 11 scope + hotfixes |  | CAB* Signoff on hotfixes |  |  |  | CAB* Signoff on hotfixes |  |  |  | CAB* Signoff on hotfixes
SIT & UAT Deployments | 2025-01-06: Open Box Team; 2025-02-03: Open Box Team; 2025-03-03: Open Box Team; 2025-03-31: Open Box Team
Prod Deployments - Releases | 2025-01-13: 2024-01-13 Release; 2025-02-10: 2024-02-10 Release; 2025-03-10: 2024-03-10 Release; 2025-04-07: 2024-04-07 Release
Client Meetings | 2025-01-06: Weekly Progress Update & UAT Kickoff; 2025-01-07: Refinement - Ad-hoc; 2025-01-09: Refinement - Ad-hoc; 2025-01-13: Sprint Review; 2025-01-14: Refinement - Ad-hoc; 2025-01-16: Refinement - Ad-hoc; 2025-01-20: Weekly Progress Update; 2025-01-21: Refinement - Ad-hoc; 2025-01-23: Refinement - Ad-hoc; 2025-01-27: Weekly Progress Update; 2025-01-28: Refinement - Ad-hoc; 2025-01-30: Refinement - Ad-hoc; 2025-02-03: Weekly Progress Update & UAT Kickoff; 2025-02-04: Refinement - Ad-hoc; 2025-02-06: Refinement - Ad-hoc; 2025-02-10: Sprint Review; 2025-02-11: Refinement - Ad-hoc; 2025-02-13: Refinement - Ad-hoc; 2025-02-17: Weekly Progress Update; 2025-02-18: Refinement - Ad-hoc; 2025-02-20: Refinement - Ad-hoc; 2025-02-24: Weekly Progress Update; 2025-02-25: Refinement - Ad-hoc; 2025-02-27: Refinement - Ad-hoc; 2025-03-03: Weekly Progress Update & UAT Kickoff; 2025-03-04: Refinement - Ad-hoc; 2025-03-06: Refinement - Ad-hoc; 2025-03-10: Sprint Review; 2025-03-11: Refinement - Ad-hoc; 2025-03-13: Refinement - Ad-hoc; 2025-03-17: Weekly Progress Update; 2025-03-18: Refinement - Ad-hoc; 2025-03-20: Refinement - Ad-hoc; 2025-03-24: Weekly Progress Update; 2025-03-25: Refinement - Ad-hoc; 2025-03-27: Refinement - Ad-hoc; 2025-03-31: Weekly Progress Update & UAT Kickoff; 2025-04-01: Refinement - Ad-hoc; 2025-04-03: Refinement - Ad-hoc; 2025-04-07: Sprint Review | Refinement - Ad-hoc | Refinement - Ad-hoc |  | Weekly Progress Update | Refinement - Ad-hoc | Refinement - Ad-hoc |  | Weekly Progress Update | Refinement - Ad-hoc | Refinement - Ad-hoc
Internal Meetings exlc stand up | bar: 2025-01-06 to 2025-01-10; 2025-01-13 to 2025-01-17; 2025-01-20 to 2025-01-24; 2025-01-27 to 2025-01-31; 2025-02-03 to 2025-02-07; 2025-02-10 to 2025-02-14; 2025-02-17 to 2025-02-21; 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14; 2025-03-17 to 2025-03-21; 2025-03-24 to 2025-03-28; 2025-03-31 to 2025-04-04; 2025-04-07
Grainger Hotfix Testing | 2025-01-17: Hotfix user testing Signoff; 2025-01-24: Hotfix user testing Signoff; 2025-01-31: Hotfix user testing Signoff; 2025-02-14: Hotfix user testing Signoff; 2025-02-21: Hotfix user testing Signoff; 2025-02-28: Hotfix user testing Signoff; 2025-03-14: Hotfix user testing Signoff; 2025-03-21: Hotfix user testing Signoff; 2025-03-28: Hotfix user testing Signoff |  |  | Hotfix user testing Signoff |  |  |  | Hotfix user testing Signoff |  |  |  | Hotfix user testing Signoff
Prod Deployments - Hotfixes | 2025-01-06: Hotfix; 2025-01-20: Hotfix; 2025-01-27: Hotfix; 2025-02-03: Hotfix; 2025-02-17: Hotfix; 2025-02-24: Hotfix; 2025-03-03: Hotfix; 2025-03-17: Hotfix; 2025-03-24: Hotfix; 2025-03-31: Hotfix |  |  |  | Hotfix |  |  |  | Hotfix

## Sheet1
Sprint Alignment | Sprint 2 | [27 empty] | Sprint 3 | [27 empty] | Sprint 4 | [27 empty] | Sprint 5 | [27 empty] | Sprint 6
| Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
 | time axis 2024-07-29 to 2024-12-31
Open Box | 2024-07-29: Build (Dev & Test); 2024-08-05: Build (Dev & Test); 2024-08-12: Build (Dev & Test) / UAT Feedback; 2024-08-19: Next Release to CAB; 2024-08-26: Build (Dev & Test); 2024-09-02: Build (Dev & Test); 2024-09-09: Build (Dev & Test) / UAT Feedback; 2024-09-16: Next Release to CAB; 2024-09-23: Build (Dev & Test); 2024-09-30: Build (Dev & Test); 2024-10-07: Build (Dev & Test) / UAT Feedback; 2024-10-14: Next Release to CAB; 2024-10-21: Build (Dev & Test); 2024-10-28: Build (Dev & Test); 2024-11-04: Build (Dev & Test) / UAT Feedback; 2024-11-11: Next Release to CAB; 2024-11-18: Build (Dev & Test); 2024-11-25: Build (Dev & Test); 2024-12-02: Build (Dev & Test) / UAT Feedback; 2024-12-09: Next Release to CAB
Grainger Business Users | 2024-08-12: Sprint 2 UAT; 2024-08-15: Final Testing/Sign-off; 2024-09-09: Sprint 3 UAT; 2024-09-12: Final Testing/Sign-off; 2024-10-07: Sprint 4 UAT; 2024-10-10: Final Testing/Sign-off; 2024-11-04: Sprint 5 UAT; 2024-11-07: Final Testing/Sign-off; 2024-12-02: Sprint 6 UAT; 2024-12-05: Final Testing/Sign-off
Grainger Meetings | 2024-08-01: CAB*; 2024-08-08: CAB*; 2024-08-14: Last Item logged; 2024-08-15: CAB*; 2024-08-22: CAB*; 2024-08-29: CAB*; 2024-09-05: CAB*; 2024-09-11: Last Item logged; 2024-09-12: CAB*; 2024-09-19: CAB*; 2024-09-26: CAB*; 2024-10-03: CAB*; 2024-10-09: Last Item logged; 2024-10-10: CAB*; 2024-10-17: CAB*; 2024-10-24: CAB*; 2024-10-31: CAB*; 2024-11-06: Last Item logged; 2024-11-07: CAB*; 2024-11-14: CAB*; 2024-11-21: CAB*; 2024-11-28: CAB*; 2024-12-04: Last Item logged; 2024-12-05: CAB*; 2024-12-12: CAB*
UAT Deployments | 2024-08-12: Open Box Team; 2024-09-09: Open Box Team; 2024-10-07: Open Box Team; 2024-11-04: Open Box Team; 2024-12-02: Open Box Team
Prod Deployments - Releases | 2024-08-19: 2024-08-19 Release; 2024-09-16: Open Box Team; 2024-10-14: Open Box Team; 2024-11-11: Open Box Team; 2024-12-09: Open Box Team
Client Meetings | 2024-07-29: Weekly Progress Update; 2024-08-05: Weekly Progress Update; 2024-08-09: Deployment Decision; 2024-08-12: Weekly Progress Update & UAT Kickoff; 2024-08-16: Deployment Decision; 2024-08-19: Sprint Review; 2024-08-20: Refinement - Ad-hoc; 2024-08-21: Refinement - Ad-hoc; 2024-08-22: Refinement - Ad-hoc; 2024-08-23: Refinement - Ad-hoc; 2024-08-26: Weekly Progress Update; 2024-09-02: Weekly Progress Update; 2024-09-06: Deployment Decision; 2024-09-09: Weekly Progress Update & UAT Kickoff; 2024-09-13: Deployment Decision; 2024-09-16: Sprint Review; 2024-09-17: Refinement - Ad-hoc; 2024-09-18: Refinement - Ad-hoc; 2024-09-19: Refinement - Ad-hoc; 2024-09-20: Refinement - Ad-hoc; 2024-09-23: Weekly Progress Update; 2024-09-30: Weekly Progress Update; 2024-10-04: Deployment Decision; 2024-10-07: Weekly Progress Update & UAT Kickoff; 2024-10-11: Deployment Decision; 2024-10-14: Sprint Review; 2024-10-15: Refinement - Ad-hoc; 2024-10-16: Refinement - Ad-hoc; 2024-10-17: Refinement - Ad-hoc; 2024-10-18: Refinement - Ad-hoc; 2024-10-21: Weekly Progress Update; 2024-10-28: Weekly Progress Update; 2024-11-01: Deployment Decision; 2024-11-04: Weekly Progress Update & UAT Kickoff; 2024-11-08: Deployment Decision; 2024-11-11: Sprint Review; 2024-11-12: Refinement - Ad-hoc; 2024-11-13: Refinement - Ad-hoc; 2024-11-14: Refinement - Ad-hoc; 2024-11-15: Refinement - Ad-hoc; 2024-11-18: Weekly Progress Update; 2024-11-25: Weekly Progress Update; 2024-11-29: Deployment Decision; 2024-12-02: Weekly Progress Update & UAT Kickoff; 2024-12-06: Deployment Decision; 2024-12-09: Sprint Review; 2024-12-10: Refinement - Ad-hoc; 2024-12-11: Refinement - Ad-hoc; 2024-12-12: Refinement - Ad-hoc; 2024-12-13: Refinement - Ad-hoc
Internal Meetings exlc stand up | bar: 2024-07-29 to 2024-08-02; 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-30; 2024-09-02 to 2024-09-06; 2024-09-09 to 2024-09-13; 2024-09-16 to 2024-09-20; 2024-09-23 to 2024-09-27; 2024-09-30 to 2024-10-04; 2024-10-07 to 2024-10-11; 2024-10-14 to 2024-10-18; 2024-10-21 to 2024-10-25; 2024-10-28 to 2024-11-01; 2024-11-04 to 2024-11-08; 2024-11-11 to 2024-11-15; 2024-11-18 to 2024-11-22; 2024-11-25 to 2024-11-29; 2024-12-02 to 2024-12-06; 2024-12-09 to 2024-12-13; 2024-12-16 to 2024-12-20; 2024-12-23 to 2024-12-27; 2024-12-30 to 2024-12-31

## Sheet2 (hidden)
Sprint Alignment (Minor/Major) | Sprint 2
| Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
| 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28
Open Box | 2024-07-10: Build (Dev & Test) / UAT Feedback; 2024-07-17: Build (Dev & Test) / UAT Feedback; 2024-07-24: Build (Dev & Test)
Grainger Business Users | 2024-07-10: Sprint 1 UAT; 2024-07-17: Sprint 1 UAT; 2024-07-19: Last Item logged; 2024-07-20: Final Testing/Sign-off
Grainger Salesforce Team | 2024-07-10: Support Dev & Test / UAT Feeback; 2024-07-17: Support Dev & Test / UAT Feeback; 2024-07-24: Support Dev & Test
UAT Deployments | 2024-07-25: Hines Team; 2024-07-26: Open Box Team
Prod Deployments - Releases
Client Meetings | 2024-07-10: Refinment; 2024-07-11: PM Meeting; 2024-07-13: Stand up; 2024-07-17: Refinment; 2024-07-18: PM Meeting; 2024-07-20: Stand up; 2024-07-24: Refinment; 2024-07-25: PM Meeting; 2024-07-27: Stand up; 2024-07-28: Demo / Planning
Internal Meetings exlc stand up | 2024-07-11: IAs; 2024-07-18: IAs; 2024-07-25: IAs Complete; 2024-07-27: Planning & Estimates; 2024-07-28: Retro