## Issues to Discuss
Item No. | Raised By | Issue | Status | Comments
1 | Helen | Once Tenancy Object is live/active - Any new lead/contact added should flag as having active tenancy to ** date | To Be Discussed | Something to flag that someone already lives with grainger, there is no way of knowing that now. This is so that we can see and notice potential subletting
2 | Helen | Ring-fencing/Priorty tag for current tenants requesting an internal move | To Be Discussed | Something to flag that someone already lives with grainger, there is no way of knowing that now. This is so that we can see and notice potential subletting
3 | Helen | Autochases to be sent to all tenants at offer stage and all non signers | To Be Discussed | Shouldnt be going to just lead tenant, everyone that is on that tenancy, needs to be getting some form of communication
4 | Helen | End of Tenancy - All open opportunities related to that unit to be closed and task sent to opportunity ower | To Be Discussed | On a renewal, when someone might be in their notice period (2m) from say month 8, and apporach at month 10, they might only have a few days left. There isnt a way for the opp to know that the person has an EoT and
5 | Helen | Remove lead tenants | To Be Discussed | If all people all got the emails the same, this might not be an issue
6 | Helen

## Drop Downs (hidden)
To Be Discussed
Discussed
Added to Backlog
Internal Resolution Required
Business Optimisation Case
Not Proceeding