## Sheet1
Phase | Min Cost | Max Cost | Min duration | Max duration
Analysis | 12000 | 18000 | 4 | 5
Development | 37800 | 56700 | 6 | 9
UAT | 3150 | 3150 | 2 | 2
PROD deployment + support | 1600 | 1600 | 2 | 2
TOTAL | 54550 | 79450 | 14 | 18

## Sheet2
cost per sprint | 18900
cost per week | 6300
cost per day | 1260
630

## Actuals
Actual | Days | 156
| Sprints | 10.4
| "Cost" for actual effort | 196560
SOW | Cost per Day | 1260
| Total Cost | 82600
| Days | 65.5556
| Cost Difference | 113960
| Actual Days | 156
| Estimated Days | 65.5556
| Util | 238%