## Sheet1
Numer | Where | Field | Request | Reason | JS Notes | Related | Grouping | Jira
1 | New Account | Pets | Field to be removed | Field not relevant for Commercial Accounts | OK |  | Page Update - Account | CLTL-209
2 | New Account | RTR Expiry Date | Text to be removed | Nothing to fill out | OK |  | Page Update - Account | CLTL-209
3 | New Account | RTR Time Limited | Text to be removed | Nothing to fill out | OK |  | Page Update - Account | CLTL-209
6 | New Account | QUERY - required information | Query | I thought we were told there were other fields other than Account Name that needed to be filled in before an account could be created? Email address in a certain format? If that's the case then can other fields be made required as appropriate. | Need to check impact - Email is required for the integrations but not necessarily to create. If the integration is wanting to make an account without an email, this could fail |  | Page Update - Account | CLTL-209
4 | New Account | Leasing Agents - Minimum Fee | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Account level | Leasing Agents can/should be captured as Accounts/Companies - Maybe need an Agent type where these are shown. When an agent is listed on a unit (Something that is raised elsewhere) then the relevant fees can pull through to the opp etc |  | Agent/Solicitor Relationships | CLTL-209 CLTL-225
5 | New Account | Leasing Agents - Terms of Engagement | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Account level | See above |  | Agent/Solicitor Relationships | CLTL-209 CLTL-225
34 | Comm Opp | VAT | Auto-populated | VAT is due depending on whether the property is opted for tax, this should be updated at the property or unit level by our finance team and just pull through to show us whether VAT is applicable or not. | This needs to be captured on the unit. Currently not a place for this to be stored, and then to be mass uploaded/integrated from qube? |  | New Fields - Unit | CLTL-210
21 | Comm Offer | Agent Fee Information | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit. | Mentioned elsewhere | 36 | Agent/Solicitor Relationships | CLTL-211
36 | Comm Opp | Agent Fee | QUERY | Where is this pulling from? We should hold information at the unit level on: agents appointed, date of appointment, the % basis of instruction and their minimum fee. | This is set by default as 10% when the offer is created. It can be manually changed. A fee percentage could be held at a unit level (if this is set unit by unit) but there is nowhere to store this right now. For openbox, this would need to be a flow that defaults the value to what is on the unit at the time of the offer being created, but allow for it to be manuallt changed if needed. | 21 | New Fields - Unit Flow Update - Create Commercial Offer | CLTL-211 | NOT THE FLOW
18 | Comm Offer | n/a | Break Clause to be its own section | Break clauses are not incentives so should be in own section, separate to Capital Contribution. | OK |  | Page Update - Offer | CLTL-212
19 | Comm Offer | Rent Free Months | To be added to Tenant Incentives Section | Rent free periods are tenant incentives, so we might want to move this field in to the Tenant Incentives section - Commercial Team to review and confirm. | OK |  | Page Update - Offer | CLTL-212
43 | Emailed In |  |  | First Break Clause Date-this is manually entered by users. Is it possible to amend this to calculate based on lease start date = number of months/years? | Captured by Rebecca on her sheet | 22 | Duplicate | CLTL-213
22 | Comm Offer | Deposit | Field to be added | The deposit may change between offers. Happy for this to be a field we input the agree deposit in £ (could be complicated to calculate 3 or 6m deposit if there are stepped rents or if VAT is due on some properties but not others) | OK - | 32, 33 | New Fields - Offer | CLTL-213
32 | Comm Opp | Security Deposit (Override) | To be removed | To be included in the Offer section, rather than the opportunity. | OK | 22 | New Fields - Offer | CLTL-213
33 | Comm Opp | Deposit to be Paid Back | To be removed | To be included in the Offer section, rather than the opportunity. | OK | 22 | New Fields - Offer | CLTL-213
30 | Comm Opp | n/a | New tick box 'no Rent Review' | If no rent review then box to be checked - makes it clear field hasn't been missed if left empty. | Should this be on the offer? | 20 | Field Update - Populate from Primary Offer | CLTL-214
20 | Comm Offer | Rent Review fields | To be added into the Offers page | Rent Reviews will be negotiated at the offer level. | Add to offer and then fill on opp from selected primary offer | 29, 30 | New Fields - Offer | CLTL-214
29 | Comm Opp | First Rent Review Date | To be in years from lease start | Allows the RR date to be automatically recalcualted as the estimated lease completion date moves. We also negotiate based on 'RR at year 5' so is quicker to understand the offer if we can see the offer in this format. | Should this be on the offer? Calculated on the actual move in date? | 20 | Field Update - Populate from Primary Offer | CLTL-214
17 | Comm Offer | Tenant Incentives - First Break Clause Date | Add a calculation of months into years | If 18m is input then will state '1.5 years', if 36m is input then will state '3 years'. Gives clarity as to what terms have been negotiated. | have a formula for the time in years that the break clause is. | 16, 20, 29, 30 | Formula for ms of bc | CLTL-214
41 | Comm Opp | Agreement for Lease | Add 'AFL signed' field | Need a date field for when AFL completes. | OK | 47 | New Fields - Opportunity | CLTL-215
47 | Emailed In |  |  | Agreement for Lease: not all Commercial leases are subject to Agreement for Lease. AT the start of the Opportunity, user ticks Agreement for Lease if this is relevant. If this box is NOT ticked, user must still progress through AFL Workflow and Tab still appears at the top of the screen. If AFL is NOT ticked, can the AFL workflow and tab be hidden on screen as not relevant? | Can add functionality re: marking if the AFL is needed or not. Removing from the path at the top is more complicated | 41 | New Fields - Opportunity Flow Update - Create Commercial Opportunity Screen Flow | CLTL-215
37 | Comm Opp | Approval | QUERY | How will this record where IC approve one offer but then we renegotiate a new offer from the same tenant and the second offer goes for IC sign off? Which IC approval date will be shown, how will the date get updated? | Why would an offer get accepted by IC then be renegotiated? Would it not then need to be AM and IC approved again? |  | If after agreeing - need to go back and get new approvals | CLTL-216
16 | Comm Offer | Tenant Incentives - First Break Clause Date | To be number of months until the first break | Allows the break date to be automatically recalcualted as the estimated lease completion date moves. We also negotiate based on 'break at year 5' so is quicker to understand the offer if we can see the offer in this format. Months required to allow for breaks at 18m or other non whole-year negotiations. | Need to scope what the requirements of this would be - Added to Backlog | 17 | Scope | CLTL-217
48 | Emailed In |  |  | Rename the MOVE IN date on the Opportunity user Interface to “Tenancy Start Date” to avoid confusion (tenant move in date can differ from Lease start date). Do not rename the field in database as it will have been used in existing integrations and mapping etc. | Makes sense and can do | 13 | Field Update - Change Label | CLTL-218
38 | Comm Opp | Lease plan Status | Change drop-down options | Blank, Requested, Received | OK |  | Field Update - Opportunity.Lease Plan Status | CLTL-219
24 | Comm Opp | Sub Stage | Remove this field | Nothing to select | There are 3 values for Sub stage when opp is closed lost - these should be moved to lost reason. Then can remove this substage field |  | Field Update - Opportunity.Sub Stage Field Update - Opportunity.Lost Reason Page Update - Opportunity | CLTL-220
23 | Com Offer Line Item | Quantity | Make this uneditable/ remove field | If this always has to be '1' then no requirement to have this as an editable field. Ensures this is not overwritten with another number. | Makes sense - need to remove from lighning page layout and ensure that it always set to one. This makes sense for all offer line items, there can only ever be one of a unit |  | Page Update - Offer Line Item | CLTL-221
14 | Comm Offer | Select Building | Limit drop-down list to only show commercial buildings | For creating commercial offers we only need to see commercial buildings. | Buildings currently are not differentiated by their use type ie. Commercial or residential. Can be done |  | New Fields - Building | CLTL-222
7 | New Comm Opp | Local Agent | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Opportunity level | Mentioned elsewhere - pull through from the unit. Issues are that if the unit is updated and changed to have different agents, then all records will be updated |  | Agent/Solicitor Relationships | CLTL-223
9 | New Comm Opp | National Agent | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Opportunity level | Mentioned elsewhere - pull through from the unit. Issues are that if the unit is updated and changed to have different agents, then all records will be updated |  | Agent/Solicitor Relationships | CLTL-223
50 | Emailed In |  |  | Local Agents are managed at a unit level. Is it possible to hold the agent on the unit so that it auto populates the opportunity rather than having to select the local agent on every opportunity. | Captured by Rebecca on her sheet - agents should be accounts with contacts and agent account can be linked to a unit |  | Agent/Solicitor Relationships | CLTL-223
8 | New Comm Opp | Local Agent Contact | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Opportunity level | Mentioned elsewhere - pull through from the unit. Issues are that if the unit is updated and changed to have different agents, then all records will be updated |  | Agent/Solicitor Relationships | CLTL-224
10 | New Comm Opp | National Agent Contact | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Opportunity level | Mentioned elsewhere - pull through from the unit. Issues are that if the unit is updated and changed to have different agents, then all records will be updated |  | Agent/Solicitor Relationships | CLTL-224
45 | Emailed In |  |  | Stepped rents: There is no option to store the stepped rents on the opportunity or offer for commercial leases. E.g. . First 6m of lease at £1k pm, next 12 m at £1.5k, Next 12m at £2k etc. Stepped rent functionality would be required to remove the dependency on the PV form (note however that not all commercial leases have stepped rents). | New Functionality - Adding to Backlog |  | New Funcitonality | CLTL-226
49 | Emailed In |  |  | The Commercial MOVE in (Tenancy start date) is not always known at the start of the journey. The tenancy start date is usually the same as the Tenancy signing date on the Lease Completion section of the opportunity (much later in the process). user has to remember to go back and amend the original estimated Move in (Tenancy start date). Is it possible to auto populate/overwrite the Move In Date (Tenancy start date) with the Tenancy signing date? Or alternatively generate an alert/remind to the user when the Tenancy signing date is entered to remind user to amend the Move in (Tenancy start date)? | New Functionality - Adding to Backlog |  | New Functionality | CLTL-227
25 | Comm Opp | Landlord Solicitor | Make a free text field | We don't need to hold this information in Qube following completion, can we just type this in as a reference field for the Commercial Team. No need to create a whole contact entry. | The solicitor should be an account as this is a relationship that grainger will want to track. |  | Agent/Solicitor Relationships | Speak to GPLC
26 | Comm Opp | Solicitor Contact | Make a free text field | We don't need to hold this information in Qube following completion, can we just type this in as a reference field for the Commercial Team. No need to create a whole contact entry. | This should be a contact as it will be a specific agent, eg Bob Smith, and is a relationship grainger will want to track |  | Agent/Solicitor Relationships | Speak to GPLC
44 | Emailed In |  |  | Asset manager approval not yet built for testing-have all the fields been identified for inclusion in the notification to Asset managers? This includes calculations fields which will rely on all data required for the calculation being held in Salesforce. | https://graingerplc.atlassian.net/browse/CLTL-11 being delivered in this sprint |  | Doing
42 | Emailed In |  |  | Remove Commercial-Let Agreement type from Salesforce as it is meaningless and not required | Done https://graingerplc.atlassian.net/browse/CLTL-195 |  | Done
15 | Comm Offer | Agreement Type | Amend drop-down list | Drop-down list to be amended/ shortened if we also amend this on 'New Commercial Opportunity' page. | Yes should be just the commercail ones |  | Field Update - Restrict Picklist
11 | New Comm Opp | Agreement Type | Amend to drop-down list | Too many options, we should provide a list of what Commercial team are likely to use. Possible list: 1. Commercial Lease (need to find out why we have Commercial Lease AND Commercial Let, not sure what the diff is?) - Ideally auto-filled as this 2. Parking Licence 3. Tenancy at Will | Have removed Commercial Let already, added in Commercial Licence. Tenancy at will is new, but can be added |  | With Grainger
12 | New Comm Opp | Use Type | QUERY | Where does this info go, where does it get reported. Need consensus on what should be input here - e.g. E class or 'Retail' or 'Café' | Up to Grainger to decide on their business rules here |  | With Grainger
27 | Comm Opp | Status | QUERY | Will this auto-update to 'accepted' and 'rejected' as the deal progresses? | Grainger to review and update |  | With Grainger
28 | Comm Opp | Rent Review | Require addtiional fields? | • Tick box for 'upwards only' • How do we record cap and collar on RPI? • Do we need to include a % field for indexed rent e.g. RPI + 2% Commercial team to review and advise. | Grainger to review and update |  | With Grainger
31 | Comm Opp | Additional Offer Details ' Required Notice (Months) | QUERY | Not sure what this relates to, could be removed? | Grainger to review and update |  | With Grainger
35 | Comm Opp | Other notes | QUERY | Commercial team to review - do we want a field specifically about parking spaces or rights to park. Might help for future reporting? | Grainger to review and update |  | With Grainger
39 | Comm Opp | Tenant Planning & Licensng | QUERY | We may want to add a tick box for both licensing and planning to tick when these have been approved - difficult to tell if the approval date is an estimated date that has passed without receiving planning, or if the date has passed and planning was received on that date. | Grainger to review and update |  | With Grainger
40 | Comm Opp | Technical Informaiton' section | QUERY | This whole section needs review - how are we reporting on this info. Not sure this is best way to track it as it currently stands. | Grainger to review and update |  | With Grainger
13 | New Comm Opp | Move In Date | QUERY | What happens with this date? Can we add text to advise e.g. 'Input estimated move-in date'# | This field is shared with resi so any help text will be seen by all people. Might be best to know in a commercial context that this can move. | 48
46 | Emailed In |  |  | What is the CLOSED DATE used for? Its currently populating as lease start date (move in date) = 1 month. Grainger never use this field. Should they be ? | Required field in Salesforce. Defaulted to 1m. Updated when Opp is closed.