## Feature Backlog (hidden)
Feature Backlog |  |  |  | Open Items / Questions
I want to | Objectives | As a | So that |  | Feature Notes on Scope
Workflow Variations
Create a void for a unit that is to be sold | sell | Renewals, Onsite PM OR Centralized PM user
Create a void for a unit that is to be refreshed & relet | refresh | Renewals, Onsite PM OR Centralized PM user
Change a unit refresh to a full refurbishment
Close a void where the tenant is retained during initial confirmation of NTQ
Close a void where the tenant is retained after initial confirmation of NTQ |  |  |  |  | Cancel future, void events where the tenant is retained
Indicate when high-level tasks & milestones are complete
Complete end-to-end high level process??
See the overall progress of a void
See the progress of a milestone & task
Complete a void
Assign tasks to a user |  | User
Tasks
See & mark completion of the detailed tasks required to: Validate Notice |  | Centralized PM
See & mark completion of the detailed tasks required to: Confirm Notice |  | Centralized PM
See & mark completion of the detailed tasks required to: Notify Stakeholders |  | Centralized PM
See & mark completion of the detailed tasks required to: Notify Stakeholders if a tenant is retained |  | Centralized PM
See & mark completion of the detailed tasks required to: Cancel Direct Debit |  | Finance
Complete the full PVI checklist in Salesforce |  | Onsite PM
See & mark completion of the detailed tasks required for: PVI Follow Up |  | Onsite PM
See & mark completion of the detailed tasks required to: Book Works |  | Centralized PM
See & mark completion of the detailed tasks required for: Move Out |  | Onsite PM
See & mark completion of the detailed tasks required to: Check Property Condition |  | Onsite PM
See & mark completion of the detailed tasks required to: Review Check Out |  | Centralized PM
See & mark completion of the detailed tasks required to: Finalize Check Out |  | Centralized PM
See & mark completion of the detailed tasks required for: Deposit Release |  | Centralized PM
See relevant information about the building and unit when working on a void (Live/Work, BTR/PRS)
Calculate Unit Available Date
See the target relet/available date for a unit being refreshed
See the target relet/available date for a unit being refurbished
See the target void completion date for a unit to be sold
Indicate where there are delays that will impact the target relet date.
Assign Responsibilities
See current & upcoming tasks for which my department is responsible
See current & upcoming tasks for which I am department is responsible
See which departments have a high number of tasks currently assigned
Calendar
Create a PVI event / reminder
Create an Inventory Check Out event / reminder
Create a Move Out event / reminder
Create a water flushing reminder where required
See void-related events happening at my property on a given day or week. |  | Onsite PM
See void-related events that I am responsible for completing on a given day or week. |  | User
Link Documents
Add / see emails from the tenant, or from other sources, that are associated to a void
Save move out Compliance Certificates & certificate dates in Salesforce
Add / see the Check Out Report for a void
Send Emails
Send a move out email to the tenant with links to web forms containing relevant information
Send a PVI follow up email to the tenant
Email the Check Out Report to the tenant
Capture Deposit Return Instructions from Tenant
Add / see the DRI form completed by a tenant for the void |  |  | Finance & PM know where to pay the deposit
A tenant can capture Deposit Return Instructions in the Tenant Portal / online |  | Tenant | I do not need to fill in the DRI form
Salesforce Account
Access void-related emails and communications with a tenant, when I view a tenant's information in Salesforce. |  |  | I have a single view of the customer
Salesforce Unit Integration
See up-to-date FV date, available date and unit status when I view a unit in Salesforce, based on the latest void information
Delays
Refurbishment
See a summhary of the latest active & complete voids when viewing a unit |  | SF user |  |  | Replace void notes?
See the latest void-related marketing/viewing arrangements & key location when viewing a unit in Salesforce |  | Lettings user
See a summary of active & complete voids when viewing a tenancy in Salesforce |  | SF user
See a history of PVI inspection outcome when viewing a unit
See void-related compliance certificates when viewing a unit
See move out meter readings when viewing a unit
Update Qube
See up-to-date FV date, available date, unit status when I view a unit in Qube, based on the latest void information |  |  | I don't have duplicate unit dates and status across systems.
Reverse any Qube updates where a tenant is retained
Update Qube unit status & available date where a full refurbishment is required
Update the Qube unit available date where there are delays
Create a void note in Qube from a void |  |  | I don't have to key void information into multiple systems. | TBD if still required?
Update the Qube diary from a void |  |  | I don't have to key void dates into multiple systems. | TBD if still required?
See up-to-date tenancy dates and status, based on the latest void information. |  |  | I don't have to record that the tenancy has ended, the resident has vacated & close the tenancy record manually in Qube
Create & Update MiMo Tasks
Complete move out tasks in Salesforce instead of the MiMo tasks
Capture meter readings on the unit / void in Salesforce instead of the MiMo tasks
Create a new MiMo task directly from a void
See up-to-date void details & dates in the MiMo task, based on the latest void information. |  |  | Any necessary information required for Move In, ICO and R&M tasks are in FSI, without needing to re-enter data.
Create a new MRI/FSI Inventory Check Out task from a void
Close any MiMo tasks where a tenant is retained.
KPIs
Manage KPIs for an overall void, milestones & tasks |  | Admin |  |  | refresh, refurb, sale variations
Manage bank holidays / working days considered in the calculation of void available dates & KPIs. |  | Admin
Visibility / Dashboards
See active voids that are behind schedule
See current milestones and tasks that are behind schedule
Visibility into completed voids that exceeded overall target turnaround times |  |  | See trends , anomolies, bottleneck properties /departments |  | Trends over time? By property/estate or region?
See average void turnaround times over a period of time for a property/estate or region
See completed milestones & tasks that significantly exceeded overall target turnaround times for a department or property
See average turnaround times for a task / milestone over a period of time
See new, confirmed voids confirmed to be relet |  | Lettings, Asset Management
See new, confirmed voids confirmed to be sold |  | Asset Management
Future Enhancements
Create a void for a garage or parking bay only |  | Renewals, Onsite PM OR Centralized PM user
Manage the Pricing Play Book in Salesforce |  | Lettings user
Maintain a key log for each unit in Salesforce |  | Onsite PM
Access void information on my mobile or tablet

## Feature Backlog (2) (hidden)
Feature Backlog |  |  |  | Open Items / Questions
A Renewals, Onsite PM or Centralized PM user can create a void for a unit that is to be sold
A Renewals, Onsite PM or Centralized PM user can create a void for a unit that is to be refreshed & relet
A user can change a unit refresh to a full refurbishment
A user can close a void where the tenant is retained during initial confirmation of NTQ
A user can close a void where the tenant is retained after initial confirmation of NTQ |  |  |  |  | Cancel future, void events where the tenant is retained
A user can see the overall progress of a void
A user can see the progress of a milestone & task
A Centralized PM user can see & mark completion of the detailed tasks required to: Validate Notice
A Centralized PM user can see & mark completion of the detailed tasks required to: Confirm Notice
A Centralized PM user can see & mark completion of the detailed tasks required to: Notify Stakeholders
A Centralized PM user can see & mark completion of the detailed tasks required to: Notify Stakeholders if a tenant is retained
A Finance user can see & mark completion of the detailed tasks required to: Cancel Direct Debit
An Onsite PM user can complete the full PVI checklist in Salesforce
See & mark completion of the detailed tasks required for: PVI Follow Up |  | Onsite PM
See & mark completion of the detailed tasks required to: Book Works |  | Centralized PM
See & mark completion of the detailed tasks required for: Move Out |  | Onsite PM
See & mark completion of the detailed tasks required to: Check Property Condition |  | Onsite PM
A Centralized PM user can see & mark completion of the detailed tasks required to: Review Check Out
A Centralized PM user can see & mark completion of the detailed tasks required to: Finalize Check Out
A Centralized PM user can see & mark completion of the detailed tasks required for: Deposit Release
A user can see relevant information about the building and unit when working on a void (Live/Work, BTR/PRS)
A user can see the target relet/available date for a unit being refreshed
A user can see the target relet/available date for a unit being refurbished
A user can see the target void completion date for a unit to be sold
A user can indicate where there are delays that will impact the target relet date.
A user can see current & upcoming tasks for which my department is responsible
A user can see current & upcoming tasks for which I am responsible
A user can see which departments have a high number of tasks currently assigned
A Centralized PM user can create a PVI event / reminder
A user can create an Inventory Check Out event / reminder
A Centralized PM user can create a Move Out event / reminder
A Centralized PM user can create a water flushing reminder where required
A Onsite PM user can see void-related events happening at my property on a given day or week.
A user can see void-related events that I am responsible for completing on a given day or week.
A user can add & see emails from the tenant, or from other sources, that are associated to a void
A Centralized PM user can save move out Compliance Certificates & certificate dates in Salesforce
Add / see the Check Out Report for a void
Send Emails
A Centralized PM user can send a move out email to the tenant with links to web forms containing relevant information
A Onsite PM user can send a PVI follow up email to the tenant
A Centralized PM user can email the Check Out Report to the tenant
Capture Deposit Return Instructions from Tenant
Add / see the DRI form completed by a tenant for the void |  |  | Finance & PM know where to pay the deposit
A tenant can capture Deposit Return Instructions in the Tenant Portal / online
Salesforce Account
Access void-related emails and communications with a tenant, when I view a tenant's information in Salesforce.
Salesforce Unit Integration
See up-to-date FV date, available date and unit status when I view a unit in Salesforce, based on the latest void information
Delays
Refurbishment
A user can see a summary of the latest active & complete voids when viewing a unit in Salesforce |  |  |  |  | Replace void notes?
A Lettings user can see the latest void-related marketing/viewing arrangements & key location when viewing a unit in Salesforce
A user can see a summary of active & complete voids when viewing a tenancy in Salesforce
A user can see a history of PVI inspection outcome when viewing a unit in Salesforce
A user can see void-related compliance certificates when viewing a unit in Salesforce
A user can see move out meter readings when viewing a unit in Salesforce
Update Qube
See up-to-date FV date, available date, unit status when I view a unit in Qube, based on the latest void information
Reverse any Qube updates where a tenant is retained
Update Qube unit status & available date where a full refurbishment is required
Update the Qube unit available date where there are delays
Create a void note in Qube from a void |  |  |  | TBD if still required?
Update the Qube diary from a void |  |  |  | TBD if still required?
See up-to-date tenancy dates and status, based on the latest void information.
Create & Update MiMo Tasks
Complete move out tasks in Salesforce instead of the MiMo tasks
Capture meter readings on the unit / void in Salesforce instead of the MiMo tasks
A user can create a new MiMo task directly from a void
A user can see up-to-date void details & dates in the MiMo task, based on the latest void information in Salesforce
A user can create a new MRI/FSI Inventory Check Out task from a void
Close any MiMo tasks where a tenant is retained.
KPIs
Manage KPIs for an overall void, milestones & tasks |  | Admin |  |  | refresh, refurb, sale variations
Manage bank holidays / working days considered in the calculation of void available dates & KPIs. |  | Admin
Visibility / Dashboards
A user can see active voids that are behind schedule
A user can see current milestones and tasks that are behind schedule
Visibility into completed voids that exceeded overall target turnaround times |  |  | See trends , anomolies, bottleneck properties /departments |  | Trends over time? By property/estate or region?
See average void turnaround times over a period of time for a property/estate or region
See completed milestones & tasks that significantly exceeded overall target turnaround times for a department or property
See average turnaround times for a task / milestone over a period of time
A Lettings user can see new, confirmed voids confirmed to be relet |  | Lettings, Asset Management
An Asset Management user can see new, confirmed voids confirmed to be sold |  | Asset Management
Future Enhancements
Create a void for a garage or parking bay only |  | Renewals, Onsite PM OR Centralized PM user
Manage the Pricing Play Book in Salesforce |  | Lettings user
Maintain a key log for each unit in Salesforce |  | Onsite PM
Access void information on my mobile or tablet

## Milestones
Void Process |  |  |  | Task Inputs |  |  |  | Task Outputs |  | Future Phase | Future Phase | Comments |  | Workflow Variations |  |  |  | KPI
Milestone | Task | Team Responsible | Prerequisites | Calculate / Source Information | Sub Tasks to be Completed / Info to be captured on Void | Task Data Type | Linked Documents | General SF Outputs (Email, Calendars) | Update Salesforce Unit | Update Qube Lease / Unit TBD | Create / Update MRI MiMo Task | Questions | Future Functionality | Std Refresh Process | Tenant Retained | Unit to be Sold | Full Refurb | Days to Complete
| Create Void Record | Renewals, Onsite PM OR Centralized PM |  |  |  |  | Optional: Upload NTQ email | [5 empty] | Void process is only a Garage / Parking Bay is vacated
[5 empty] | Future Vacate Date | Date
[5 empty] | Unit | Picklist (SF Unit)
[5 empty] | Primary Tenant / additional tenants | Picklist (SF Account)
[5 empty] | SF Tenancy / Qube Lease | Picklist | [6 empty] | When SF-Qube tenancy link is implemented (Q3/4 2023)
[5 empty] | Salesforce Opportunity? (Optional?) | Picklist
Receive Notice
| Validate Notice | Centralized PM | [11 empty] | Y | Y | Y | Y
SF Unit: 'Live Work' status
[5 empty] | Check Salesforce opportunity record | Checkbox
[5 empty] | Check parking | Checkbox
[5 empty] | Date NTQ Received | Date | [5 empty] | Currently on unit; move to void?
Optional: Upload NTQ email
| Confirm Notice | Centralized PM | Validate Notice | [5 empty] | if tenant not retained: |  |  |  |  | Y | Y | Y | Y
[5 empty] | Phone call to Resident: Acknowledge / inform process | Checkbox
[5 empty] | Follow up Email sent to Resident | Checkbox | Move Out Email (system-generated or Manual) | Generate move out email to tenant with links to web forms & online(?) DRI form.
|  |  |  | Tenant inputs DRI via webform? | Deposit return instructions | Bank details; other info? | Any email / DRI form from tenant |  |  |  |  | Keep manual DRI form for release 1? | Build into My Grainger app or tenant portal?
[5 empty] | Tenant retained | Checkbox | Any other email comms with tenant |  |  |  | Create MiMo Task? | Create simplified MiMo task to group Inventory check out & maintenance tasks together; & keep move in tasks? | FSI integration release 2+? |  | If retained Process Ends
[5 empty] | PVI Date & Time confirmed with resident | Date/Time | [5 empty] | TBD if keep FSI PVI task - or move to SF Void Process?
[5 empty] | Book PVI in calendar | Checkbox |  | Automatically add PVI date to Salesforce calendar?
[5 empty] | Marketing & viewing arrangements (access & key location) | Text Area (Long) | [5 empty] | Save a history of key location & access info on a unit-level??
|  |  |  | PRS / BTR Property | Confirm inventory process (PRS / BTR) |  |  |  | Update Tenancy 'Move Out' date. |  | PRS Property only(?): Create Inventory Check Out task
[5 empty] | Future Vacate Date - confirmed? | Date |  |  | Update unit 'Future Vacant Date' (?) | Update Vacant Due Date (if still required?) | Save / update on MiMo task: Expected Vacant Date | FV Date could subsequently be changed? Need to update other systems each time | Qube integration release 2+?
|  |  |  | SF Unit: Sale status | Unit to be sold or re-let | Picklist: Sold, Re-let |  |  | Update Unit Status | Update Lease Status; Update Lease Tenure(?) | Save on MiMo task #7
[5 empty] | Notes (optional) | Text Area (Long)
|  |  |  | Calculate Relet Date = FV date + 5 working days |  | Date |  |  | If unit to be re-let: Update 'Available Relet Date' |  |  | FV Date could subsequently be changed? Need to update other systems each time
[5 empty] | Record reason for leaving | Picklist |  |  | Update Reason & Reason Detail |  |  | Move out of MiMo task? Moved out of Notify Stakesholder task.
[5 empty] | Other reason for not viewing | Text Area (Short)
[5 empty] | >> Add other void note details | [6 empty] | Replace void note with summary view of voids from SF unit
[10 empty] | Update Diaries |  | Can the Qube diaries be replaced by SF calendar?
Update Stakeholders
| Set Rent | Letting | Confirm Notice | [10 empty] | Y | N | N | Y
[5 empty] | Set future rent on Unit (in Salesforce): Source from Price book & in consultation with Asset Manager | Checkbox | [5 empty] | Is this not already part of the Lettings process that would now be triggered by setting the FV & Relet date on the SF unit? | Move Price Book in Excel to Salesforce. (Lettings process) Create Standard pricing play book
[5 empty] | >> Add other void note details |  |  |  | Update Marketing Rent
| Notify Stakeholders | Centralized PM | Confirm Notice | [10 empty] | Y | N | Y | Y
[5 empty] | Update Qube: Void note, FV date, & Diaries | Checkbox | [6 empty] | Replaced by Qube integration
[5 empty] | Create MiMo task in FSI | Checkbox | [6 empty] | Replaced by FSI integration
[5 empty] | PRS only(?): Create inventory check out task in FSI | Checkbox | [6 empty] | Replaced by FSI integration
[5 empty] | BTR only(?): Add inventory checkout to calendar? | Checkbox |  | Automatically add ICO to Salesforce calendar? FV date? |  |  | Source date from FSI task created
[5 empty] | Diarise move out (includes 3rd party checkout arrangements) | Checkbox |  | Automatically add Move Out (FV date) to Salesforce calendar?
[5 empty] | 3rd Party checkout arrangements (optional) | Text Area (Long)
|  |  |  | Show all / most recent compliance certificates already in SF linked to unit? | Check compliance certificates | Checkbox | Save compliance certificates in SF & capture date |  |  |  |  | Are compliance certificates valid for a period of time / would they have an expiration date?
[5 empty] | Compliance action required (if needed) -> Create custom task? | Notes | [5 empty] | What is required here?
[5 empty] | Compliance action completed (if needed) | Checkbox
[5 empty] | Notify British Gas | Checkbox | [6 empty] | Generate email?
[5 empty] | Record access arrangements for viewings on Salesforce, including key location | Notes | [5 empty] | Already in Confirm NTQ step?
| Cancel DD | Finance | Confirm Notice | [10 empty] | Y | N | Y | Y
[5 empty] | Cancel direct debit / future charges in Qube | Checkbox
Capture credit note if final month's rent already billed (in Qube).
[5 empty] | Apportion final month's rent – if required on Qube | Checkbox | [5 empty] | Can requirement to apportion rent be derived from info e.g. mid-month move out? | Future Qube integration?
Pre-Vacation Inspection
| Complete PVI | Onsite PM | Notify Stakeholders | [8 empty] | Is notify s/h a prereq or just the PVI date? |  | Y | N | Y | Y
|  |  | PVI Date |  | Tenant retained | Y/N | Upload any ad hoc email comms with tenant | Close tasks not in Tenant Retained workflow. Remove calendar events. | If tenant retained: Reverse unit updates above | If tenant retained: Reverse Qube updates above | If tenant retained: Close MiMo task & related tasks | Is this required for R1? |  |  | If retained Process Ends
[5 empty] | PVI sub tasks - TBC |  |  | PVI task displays in property 'calendar' |  |  |  | Move PVI task list from MiMo into SF? | Add in future phase?
[5 empty] | PVI Inspection outcome | Notes
| PVI Follow Up | Onsite PM | Complete PVI | [10 empty] | Y | N | Y | Y
[5 empty] | PVI Exceptions? | Notes |  | Notify internal stakeholders if exceptions - TBD |  |  |  | What defines an exception? What are requirements for notifications? |  |  |  | Y
[5 empty] | Full refurbishment required? | Y/N |  |  | Update Unit Status (?) & Reason 'Refurb Works' |  |  | Would this be part of PVI milestone or determined by another person? |  |  |  | N | Affects W/F
|  |  |  | If refurb: Re-calculate Relet Date = FV date + [x] working days |  |  |  |  | If Refurb: Update Available Relet Date = FV date + [20]? | [6 empty] | N
[5 empty] | Follow up call to resident (move-out info, deposit release, feedback.) | Checkbox | [9 empty] | Y
[5 empty] | Follow up email to resident | Checkbox |  | Generate email? | [7 empty] | Y
| Notify Stakeholders Tenant Retained | Centralized PM | Tenant retained | [10 empty] | N | Y | N | N
[5 empty] | Update Qube | Checkbox | [6 empty] | Replaced by Qube integration
[5 empty] | Close MiMo & related tasks | Checkbox | [6 empty] | Replaced by FSI integration
[5 empty] | Notify Finance if DD already cancelled. | Checkbox
[5 empty] | Notify Lettings if Set Rent Complete | Checkbox
[5 empty] | Update British Gas if already notified. | Checkbox
| Book Works | Centralized PM | PVI Follow Up | [10 empty] | Y | N | N | N?
[5 empty] | Obtain quotes for maintenance and reactive works | Checkbox
[5 empty] | Book works in FSI | Checkbox | [5 empty] | Should this be 2 milestones: quotes & book works so that approval delay doesn't affect KPI; should this be dependent on CapEx Approval or sometimes happens after?
[5 empty] | Details of works | Notes | [6 empty] | Source from FSI?
[5 empty] | CapEx approval required | Y/N | [6 empty] | Automate logic to generate approval step in future?
[5 empty] | (Optional) Delay - reason | Notes | [5 empty] | Delays could be added at any time in process? | Source from FSI?
|  |  |  | Recalculate Re-let Date | (Optional) Delay - dates (ability to add multiple over time?) | # of working days or completion date? |  |  | Update Available Relet Date |  |  |  | Source from FSI?
[5 empty] | If delay: Update Qube | Checkbox | [6 empty] | Replaced by Qube integration |  |  | N
| Approve CapEx | Asset Management | CapEx approval required | [10 empty] | Y | N | N | N?
[5 empty] | Approve CapEx | Checkbox | [5 empty] | Should this be a task in the 'Book Works' milestone that is assigned to AM?
| Refresh / Maintenance | Centralized PM | Book Works | [10 empty] | Y | N | N | N
|  |  | Approve CapEx |  | Refresh / Maintenance Process Complete | Checkbox | [5 empty] | Can only start after CapEx approved? Can milestone start before move out? | Source status from FSI maintenance tasks linked to MiMo task? |  |  |  |  | Only starts after move out?
|  |  |  | Recalculate Re-let Date | (Optional) Delay - dates (ability to add multiple over time?) | # of working days or completion date? |  |  | Update Available Relet Date
Move Out
| Move Out | Onsite PM | Notify Stakeholders | [10 empty] | Y | N | Y | Y
|  |  | Future Vacate Date |  | Complete check-out | Checkbox
[5 empty] | Keys returned | Checkbox
[5 empty] | Actual Move Out Date | Date |  |  |  | Update lease dates: Remove Vacant Due Date; Save Vacant Date - If still required? |  | Move out of MiMo task (#8)
Update lease status to 'Vacant' (or 'Refresh' or 'Under Refurbt'?
Update lease tenure to 'Vacant'?
| Check Property Condition | Onsite PM | Move Out | [10 empty] | Y | N | Y | Y
|  |  |  | PVI Inspection outcome | Adjustment to original scope of PVI works required? | Y/N | [5 empty] | Can this be combined with Move Out Milestone? |  |  |  | N
[5 empty] | Adjustments required | Notes | [9 empty] | N
[5 empty] | Book works in FSI | Checkbox | [9 empty] | N
[5 empty] | Complete Check Out Report | Checkbox | Save Check Out Report in SF | [5 empty] | Source status from Inventory check out task linked to MiMo task? |  |  | Y
[9 empty] | Update tenancy status? | Update system that tenancy has ended and resident vacates? |  | What info is updated - SF tenancy object? Should this not happen after Move Out? |  |  |  | Y
| Review Check Out | Centralized PM | Check Property Condition | [10 empty] | Y | N | Y | Y
[5 empty] | Update Qube? | Checkbox | [6 empty] | Replaced by Qube integration
|  |  |  | See Check Out Report | Review check out report (compare to PVI) | Checkbox
[5 empty] | Move Out - Vacant Electric Meter Reading 1 | Number |  |  | Save Meter Readings on Unit for reporting? |  |  | Move meter readings out of MiMo task? | Source from inventory Hive?
[5 empty] | Move Out - Vacant Electric Meter Reading 2 | Number | [5 empty] | Where should the Move In & Move Out meter readings be saved for reporting: SF, Qube?
[5 empty] | Move Out - Vacant Gas Meter Reading | Number & units of measurement | [5 empty] | Should meter readings be captured at Move Out step?
[5 empty] | Move Out - Vacant Water Meter Reading | Number
[5 empty] | Log keys / Update: Marketing & viewing arrangements (access & key location)? | Notes |  |  | Add/update latest access & key info? |  |  | Is this different to the Keys returned / key location info in the Move out step? | Create a key log
Finalize Void
| Finalize Check Out | Centralized PM | Check Property Condition | [10 empty] | Y | N | Y | Y
|  |  |  | See Check Out Report | Send check-out report to resident | Email |  | Email report from SF?
[5 empty] | Notify Council Tax of the Vacancy | Checkbox | [5 empty] | Move out of MiMo task? #14 | Generate email? Existing email from MiMo has questionable value.
[5 empty] | Notify Water Company of the Vacancy | Checkbox | [5 empty] | Move out of MiMo task? #14
[5 empty] | Diarise Water Flushing | Y/N |  | Automatically add Salesforce calendar: Acutal move out date + 7 days |  |  |  | Move out of MiMo task? #9
[9 empty] | Close tenancy record? | Close tenancy record?
| Deposit Release | Centralized PM | Finalize Check Out | [10 empty] | Y | N | Y | Y
[5 empty] | Deposit Released | Checkbox | [5 empty] | Upload Return of Deposit Form?
[5 empty] | Resolution | Dropdown | [5 empty] | Move out of MiMo task? #16
[5 empty] | Amount of Deposit Stopped | Numeric | [5 empty] | Move out of MiMo task? #17
[5 empty] | Date Deposit was Returned | Date | [5 empty] | Move out of MiMo task? #18
| Close Down Tenancy | Finance | Deposit Release | [10 empty] | Y | N | Y | Y
|  |  | Cancel DD |  | Close Down Tenancy | Checkbox | [6 empty] | Replaced / supplemented by Qube integration
Is Deposit Release step a predecessor / dependency?
Is Review Check Out step a predecessor / dependency?
Refurbishment
| Refurbishment | Refurb Team | Full refurbishment required? | [10 empty] | N | N | N | Y
[5 empty] | Update Qube (Refurb details / status) | Checkbox | [6 empty] | Replaced by Qube integration |  |  | N
[5 empty] | Refurbishment Complete | Checkbox | [5 empty] | Assume separate quote process? Notification of refurb team is via task? | Add details in future phase
|  |  |  | Recalculate Re-let Date | (Optional) Delay - dates (ability to add multiple over time) | # of working days or completion date? |  |  | Update Relet Date / Available Date
| Available to Sell/ Let |  | Refresh / Maintenance | [5 empty] | Update Unit Status: On Market (Available to View)? | If not being sold: Update Unit Status 'On Market'?? | Update MiMo: Unit is ready to market, clean, tidy with no issues that would prevent lettings viewing the unit.
Refurbishment
Check Property Condition
| End |  | All Milestones are Complete
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Currently: Renewals team check expiring leases (using Qube diary) and reach out to tenant -> notify property management Or tenant contacts Grainger 1st to notify them of move out. Notice can also be given by Grainger.
Note on N3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Separate MiMo task
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be known/estimated upfront Reply: Generally if a tenant changes their mind and decides to leave early, they will still stick to the lease end date
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Currently saved on Qube unit Reply: 2 boroughs in London have a different technical process. Is a factor to be considered when completing some of the tasks but does not affect the milestones or tasks listed. Reply: Is displayed on SF Unit currently
Note on F18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Contains PVI date, key arrangements, etc as captured on Void record
Note on I18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use Media Links (marketing documents) saved on the unit.
Note on J23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't duplicate across void & unit? Reply: Unit currently has : - Key location (check in) - Key location (post check in ) Reply: Move all void note details into void.
Note on J24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: May need to add new statuses. Reply: Should feed in from Qube Lease
Note on F25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Save on Void record & on Unit record as there is no history on the SF unit.
Note on J25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FV date on unit updates from Qube? Reply: Integration XLS shows no existing date integration. TBD if Qube unit dates should feed SF unit dates in future.
Note on J26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Statuses include: Leased Future Vacant Refurb Out for Valuation On Hold (Issues) On Market (Available to View) Reply: Does not update from Qube Reply: In theory updates from Qube per integration XLS.
Note on K26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update lease status to 'Previous' in Qube. If unit is to be sold, update status to 'Solic.Instrct'
Note on J28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updates from Qube?
Note on K28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 'Lettings Due Date'? Reply: There is no such date in Qube. Letting due date is next lease start date
Note on F42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is separate to PVI. Someone goes thru the unit with the tenant and makes notes of wear and tear on move in & move out.
Note on H45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On shared drive currently
Note on F53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Only do this where there is a tenant due to move in already before the previous lease's end date.
Note on F57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tenant could be retained after onsite meeting / PVI
Note on K57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lease Status => Tenanted
Note on J59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rather view from unit?
Note on J62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Statuses include: Leased Future Vacant Refurb Out for Valuation On Hold (Issues) On Market (Available to View)
Note on F76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BTR – Only goes to AM if capital or over £1k Reply: Over 10k -> approval
Note on C87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BTR: Inhouse Remote buildings: inventory clerk or PM
Note on C93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BTR: Inhouse; use HIVE Remote buildings: inventory clerk
Note on J98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: May need to add new statuses Reply: Should feed from Qube Lease.
Note on J102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rather create a view from the unit?
Note on J106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rather create view from the unit
Note on F113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Weekly until move in
Note on J114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updates from Qube?
Note on C115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Finance releases the payment
Note on G117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: E.g. Deposit Returned - No Stoppages
Note on J129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updates from Qube?
Note on J131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updates from Qube?

## Reporting
Requirements
Reporting / Dashboards
Property Calendar | View of daily/weekly events per property
Department-level view of tasks currently assigned/active | Use to identify departments with a high number of tasks currently assigned & manage resources
Ability to filter by any combination of department, region, property, estate
Department-level view of upcoming tasks ?
User-level view of tasks currently assigned & active tasks | Only see tasks that are ready to be worked on.
Active voids that are behind schedule | View by property/ estate, region
Active milestones / tasks that are behind schedule
Delays in overall void turnaround | Completed voids
5 working day benchmark for refresh
x working day benchmark for sell
y working day benchmark for refurbishment
Average void turnaround vs target | Filter by property / estate, region, date range
Delays by milestone or task | Filter by department, property / estate, region, date range
Individual void delays at a milestone/task | Set benchmarks for each milestone in working days
Average milestone/task days vs target | Measure from task start date
New voids | Give users (e.g. lettings, asset management) visibility into new voids that have been confirmed.
View by units to be re-let vs units to be sold
Report on meter readings to ensure there are move in and move out readings? | Where are / should meter readings be saved, against unit in SF? Keep on MiMo task?
Future functionality?
Deposits returned to tenants? | Check on deposit returned to tenant – is a key KPI
Future functionality?

## Requirements
Requirements
Additional Requirements | Notes | Questions
No one person is the owner of the void |  | Will a team or an individual be assigned a milestone? Or Both? Or will a team be assigned a milestone & then individuals are assigned to individual tasks?
Onsite PM milestones / tasks: Be able to view per property?
Lettings & Asset Management milestones / tasks: Be able to view by region (aka Grainger Group)?
Finance, Renewals, Centralized PM milestones / tasks: View across all properties & regions?
Estimated completion date = FV date + [5] working days |  | Consider bank holidays?
+ construction delays / refurb due date |  | Only operating in UK
Estimated completion date for refurb = FV date + [20] working days
+ construction delays / refurb due date |  | Only operating in UK
Save links to documents | Some documents (certificates) are on a shared drive | Documents currently saved on DocuShare? Move to SF or link to DocuShare
Create a link between void tasks & documents on DocuShare, or save documents in Salesforce directly
Or save in SF initially and when void is closed, archive documents to DocuShare (leaving links in SF void)
Mobile/tablet access | Is currently accessed
Send resident move out acknowledgement email | SF to send the email - based on template | Must the user be able to preview template?
| Currently contains: Key location; agency details | What info needs to be on email?
Email has links to webforms / info | To be designed | Where are the pages? How will they be maintained?
Property, region, PRS / BTR-specific links?
Email has links for resident inputs data required |  | What info is required: Only DRI?
| Need bank account details | What DRI data is input: Bank account details / Checkbox to use existing DD account?
| Currently: unit ID, Tenant names, Qube reference | What information needs to be prepopulated on the form?
Calculate % complete/ progress per milestone?
Calculate overall void % complete / progress?
Tasks / Milestones | Users can be assigned to a task in advance of task starting?
Milestones will only become 'active' when prerequisite steps / dates are met?
Milestones duration will only start being measured when prerequisite steps / dates are met?

## Out of Scope
Exclusions & Limitations
Overall
No difference in workflow between BTR & PRS properties
No need to generate documents
Data migration | Will operate in parallel with manual process initially until all new voids are in SF.
Notifications are limited to creating tasks that users can see | No need to generate reminder/notification emails from system
Integration with:
§ Adobe sign (existing)
§ Inventory Hive
§ Datawarehouse for reporting
§ Proactis (AP)
Initial Exclusions
Refurbishment process | Not a priority for release 1
Garage / parking bay void process | Not a priority for release 1
FSI integration to pull status of tasks

## MiMo
keep for work order
management & payment
Create from SF Void?
Update from SF Void
Keep as part of Move In process
R1- replace in SF
remove / replace in SF w/ move out email to tenant
Update from SF Void; affects MI tasks?
remove / replace with SF dashboards
remove / replace in SF
remove ??? / replace in SF
Keep linked R&M tasks (linked to MiMo) for work order management & payment
remove / replace in SF
remove / replace in SF with task
remove / replace in SF - future release
remove
remove / replace in SF
Update from SF Void; affects MI tasks

## SF Unit
Create?
Display on Void
Update from void or Qube?
Update from void or Qube

## Docs & Integration
Current State Process Flow System Updates | [5 empty] | Documents
Evolution MRI / FSI | Qube | SalesForce | Proactis | Inventory Hive | DocuShare | Document | Input/Output? | Audience | Data Included | Notes
MIMO task on unit | Void note on unit | Amend DD to zero |  | Inventory (BTR) |  | NTQ - Notice to Quit | Receive | Tenant |  |  | Save on void
Attach NTQ |  | Cancel DD charges |  |  | DRI | Move out email | Generate | Tenant | Key location; agency details | Template currently in MRI?
Expected move out date | Future vacant date | Close void note |  |  |  | DRI - Deposit Return Instruction | Generate | Tenant | unit ID, Tenant names, Qube reference | Not currently auto-pouplated
Move out date | -> update with actual date | [5 empty] | Receive response |  | Instruction (bank details?)
[5 empty] | ICO | ICO – Inventory check out | Generate | Tenant |  | Signed by tenant
Leave reason | Leave reason | Unit Status |  |  |  | ICI – Inventory check in | Generate |  |  | Template currently in MRI?
Inventory Check Reqd - Y/N | Status |  |  |  |  | Inventory checklist |  |  |  | offline
PVI Reqd - Y/N |  | Rental price change |  |  |  | Future Vacant Email | Generate |  |  | Template currently in MRI | Replaced by process
To be sold or relet |  | Approve |  |  |  | Certificates
Property vacant length (5 days) |  | Date NTQ received |  |  |  | Check out report | Generate |  | Utilities Readings
Deposit resolution - update |  | Tenancy end date |  |  |  | Internal vacant form / email | Generate |  |  | Template currently in MRI?
Deposit amount | Lettings Due Date | Available Date
Deposit return date |  |  |  |  | ROD | ROD - Return of Deposit | Generate | Tenant | Rent changes, damages | Signed by tenant
Ready to market Y/N | [5 empty] | PVI - Pre Vacation Inspection | Generate
LOC status | Diary (close) |  |  |  |  | CUA Form
Timesheet (-> updates status) | Refurb diary |  |  |  |  | Quotes
Refurb/works start date
Refresh costs / quotes | Refurb/works completion date |  |  |  |  | AMI Tracker |  |  | New tenant, new pricing | XLS
Approve | [5 empty] | Voids Report |  |  | Confirmed vacates, Qube dates, payments | XLS
Capital costs - approve | Key location? |  |  |  |  | Vals (Valuations) Report | Generate |  | Lettings price predictions
Job Auth Capex Form
PVI Task |  |  | Refurb costs |  |  | CapEx Schedule |  |  |  | XLS
Assigned Resource |  |  | Approve |  |  | Tender Report
PVI Date | PVI Date
|  |  | Work Order |  |  | Work Order
Legionella Task |  |  | Approve
Water flushing | Remove tenant from unit |  | Invoice |  |  | Invoice | Receive
Date updated |  |  | Payment |  |  | Handover Form | Generate |  |  | On practical completion of works
|  |  | Payment Certificate |  |  | Payment Certificates
Inventory Task |  |  | Penultimate Payment Certificates |  |  | Penultimate Payment Certificates
Assigned Resource |  |  | Final Payment Certificates |  |  | Final Payment Certificates
Utilities Readings
Meter Reading 1 & 2
Gas Reading
Gas Measured in
Water Reading
Notify Utilities (of readings?)
Notify Council (council tax)?
Upload ICO Report
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Statuses include: Leased / Tenanted Future Vacant Refurb Out for Valuation On Hold (Issues) On Market (Available to View)
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes: Void for Refurb
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes: MiMo - Expected Vacant

## Deliverables
Future-state process | indicate what has been optimised | o Map that to SF & how it would be implemented in existing SF solution.
| indicate Salesforce vs. external. |  | o Define process for initial & subsequent releases.
Feature backlog : User stories; no ACs | outcomes to be delivered
priority of outcomes relative to each other
proposed data model
data sharing and visibility
integration points
document/file management
reporting requirements
High level design | Sam SF
context diagram
screen mock up
data migration requirements
licensing | o (150-200 users ultimately)
Visibility
Then Automation