## Sheet1 (2)
Task | People | Hours | No Billable Hours | Notes | Non-Billable
Effort as at April 17 |  | 51.25 | 54.5 |  | Effort as at April 17 | 52.5
Qube demo: | 2 | 3 |  | Meeting
Understand the void-related information in Qube & what needs to remain vs what should be moved to a SF void process.
Understand how Qube defines leases with a future SF Tenancy object in mind.
Understand existing integration capabilities.
Documents:
Review where void-related documents should be saved &, if not in SF, understand existing integration capabilities. | 2 | 1 |  | Meeting
SF:
Deeper dive into the aspects of current functionality (unit data) that overlaps with void process & possible changes required. | 2 | 2 |  | Meeting
General Feature Creation | 2 | 16
Update Process Flow - Future State |  | 8
Project Proposal |  | 57
Integration
Data Sharing
Doc Management
Licensing
Data Model
Process Flow - Future State
Feature Backlog | 0
Costs / Timelines
Project Management
Weekly PM Calls |  | 3
General - DevOps / Account access, PW management, Team management |  | 6
147.25
Remaining Effort |  | 96
Consultancy Duration in weeks |  | 3
Deliverables
Project Proposal
Sprints
Review detailed process.
Confirm process variations required (milestones & dependencies for each): Standard refresh, unit sale, tenant is retained, refurbishment.
Unpack milestone tasks & documents required.
Understand move out acknowledgement email/webforms requirements & tenant inputs (DRI).
Discuss milestone / task ownership requirements
Review reporting / dashboard requirements, access levels, KPI/benchmarks

## Sheet1
Task | People | Hours | No Billable Hours | Notes | Non-Billable
Effort as at April 17 |  | 51.25 | 54.5 |  | Effort as at April 17 | 52.5
Qube demo: | 2 | 3 |  | Meeting
Understand the void-related information in Qube & what needs to remain vs what should be moved to a SF void process.
Understand how Qube defines leases with a future SF Tenancy object in mind.
Understand existing integration capabilities.
Documents:
Review where void-related documents should be saved &, if not in SF, understand existing integration capabilities. | 2 | 1 |  | Meeting
SF:
Deeper dive into the aspects of current functionality (unit data) that overlaps with void process & possible changes required. | 2 | 2 |  | Meeting
General Feature Creation | 2 | 16
Update Process Flow - Future State |  | 8
Project Proposal |  | 57
Integration
Data Sharing
Doc Management
Licensing
Data Model
Process Flow - Future State
Feature Backlog | 0
Costs / Timelines
Project Management
Weekly PM Calls |  | 3
General - DevOps / Account access, PW management, Team management |  | 6
147.25
Remaining Effort |  | 96
Consultancy Duration in weeks |  | 3
Deliverables
Project Proposal
Sprints
Review detailed process.
Confirm process variations required (milestones & dependencies for each): Standard refresh, unit sale, tenant is retained, refurbishment.
Unpack milestone tasks & documents required.
Understand move out acknowledgement email/webforms requirements & tenant inputs (DRI).
Discuss milestone / task ownership requirements
Review reporting / dashboard requirements, access levels, KPI/benchmarks