Project Charter

Grainger

End of Tenancy

Version 1.0

16 October 2023

Contents

1.1	Project Title and Description	3

1.2	Project Stakeholders	3

1.3	Business Case	4

1.4	Goals & Objectives	4

1.5	Scope	5

1.6	Budget	6

1.7	Delivery Milestones	7

1.8	Risks & Issues	7

1.9	Success Criteria	7

## Project Title and Description

Project Title: 	End of Tenancy

Description: 	Develop a standardized workflow solution to provide efficiencies and visibility to effectively manage the End of Tenancy process.

## Project Stakeholders

| Name | Title | Project Role | Email | Organization |
| --- | --- | --- | --- | --- |
| Jon Pitt | Director of Letting and Marketing | Project Lead | jpitt@graingerplc.co.uk | Grainger |
| Yvonne Dargavel | Project Manager | Project Manager | ydargavel@graingerplc.co.uk | Grainger |
| Jacob Smycz | Operations Manager | SME - Salesforce / Lettings | jsmycz@graingerplc.co.uk | Grainger |
| Mike Jones | On-boarding and Operations Manager | SME - MRI / Property Management | mjones@graingerplc.co.uk | Grainger |
| Anne Stephenson | Account Receivable Manager | Accounts Receivable | astephenson@graingerplc.co.uk | Grainger |
| Daisy Stuckey | Assistant Asset Manager | Asset Management | dstuckey@graingerplc.co.uk | Grainger |
| Alexa Byrne | Asset Manager | Asset Management | abyrne@graingerplc.co.uk | Grainger |
| Colette Hunter | Financial Accountant | Finance | chunter@graingerplc.co.uk | Grainger |
| Ruben Cancio | Lettings Manager | Lettings | rcancio@graingerplc.co.uk | Grainger |
| Gemma Gavin | Lettings Manager | Lettings | ggavin@graingerplc.co.uk | Grainger |
| Sarah Regan | Resident Services Manager | Property Management Build to Rent | sregan@graingerplc.co.uk | Grainger |
| Mark Weeden | Portfolio Manager | Property Management PRS | mweeden@graingerplc.co.uk | Grainger |
| Lynn Robson | Property Manager | Property Management Service Desk | lrobson2@graingerplc.co.uk | Grainger |
| Helen Douglas Teggart | Renewals Manager | Renewals | hdouglas-teggart@graingerplc.co.uk | Grainger |
| Anita Masters | Manager - Tenancy Progression | Tenancy Progression | amasters2@graingerplc.co.uk | Grainger |
| Sam Robson | Resident Services Manager | Property Management Build to Rent | lhargreaves@graingerplc.co.uk | Grainger |
| Leanne Hargreaves | Head of Resident Services Team | Property Management Build to Rent | srobson@graingerplc.co.uk | Grainger |
| Jaic George | Applications and Integrations Support Team Lead & Grep Support | IT | jgeorge@graingerplc.co.uk | Grainger |
| Saji Gunasekaran | Salesforce and MyGrainger Support | IT | sgunasekaran@graingerplc.co.uk | Grainger |
| Sam Duncan | Salesforce Director | Salesforce Architect | sduncan@openboxsoftware.com | Open Box |
| Shaun Barrett | Senior Project Manager | Project Manager/Scrum Master | sbarrett@openboxsoftware.com | Open Box |
| Nikki Papenfus | Senior Business Analyst | Business Analyst | npapenfus@openboxsoftware.com | Open Box |
| Anjali Salecha | Salesforce Developer | Developer | asalecha@openboxsoftware.com | Open Box |
| Dillan Landsberg | Salesforce Developer | Developer | dlandsberg@openboxsoftware.com | Open Box |
| Matthew Pitcairn | Salesforce Developer | Developer | mpitcairn@openboxsoftware.com | Open Box |
| Khonani Davhana | Salesforce Quality Assurance | Quality Assurer | kdavhana@openboxsoftware.com | Open Box |

## Business Case

Grainger is planning on significant expansion, looking to double their number of letting homes in the next 3-4 years. ​​

The current systems and processes used in the End of Tenancy management are not scalable to support the planned expansion.​

Leveraging the existing Salesforce platform and user licenses will help to:​

- Improve speed & efficiency​.

- Reduce errors​.

- Allow the business to scale operations without necessitating a linear increase in employee headcount​.

- Minimize the time that units remain vacant​.

- Improve customer satisfaction. Reduce the risk of not cancelling direct debits or returning deposits on time & create a single view of customer.

## Goals & Objectives

- Measure targets, timeframes & KPIs

- Visibility into progress, delays & forecasted completion

- Visibility into team workload​

- Clear responsibility​

- Standardise process while allowing for flexibility​

- Automate notifications to internal teams​

- Move towards single view of customer & property​

## Scope

Embed the End of Tenancy process within Salesforce with no integration to external systems. The backlog below has been created during multiple requirements gathering sessions and represents the anticipated functionality to be delivered for release 1.  Delivery will follow an agile methodology where new requirements may be uncovered during the project, in which case scope can be adjusted accordingly with Grainger’s approval.

| Backlog | Issue key | Story Points |
| --- | --- | --- |
| Calculate void duration | FVVP-197 |  |
| See Tasks for a Void | FVVP-190 | 8 |
| View / Update Task Details | FVVP-189 | 3 |
| Replace Internal Notification Emails | FVVP-132 | 2 |
| Reporting - See Teams with High Number of Tasks | FVVP-127 | 1 |
| Dashboard - See Active Voids Behind Schedule | FVVP-125 | 2 |
| Property Calendar - See Onsite Void Tasks | FVVP-117 | 1 |
| Detailed Tasks - Close Down Tenancy | FVVP-116 | 2 |
| Detailed Tasks - Deposit Release | FVVP-115 | 2 |
| Detailed Tasks - Finalize Check Out | FVVP-114 | 2 |
| Detailed Tasks - Review Check Out | FVVP-113 | 2 |
| Detailed Tasks - Check Property Condition | FVVP-112 | 2 |
| Detailed Tasks - Check Out | FVVP-111 | 2 |
| Detailed Tasks - Book Works | FVVP-110 | 2 |
| Detailed Tasks - Cancel Direct Debit | FVVP-109 | 2 |
| Detailed Tasks - Check Compliance | FVVP-108 | 2 |
| Detailed Tasks - Notify Stakeholders | FVVP-107 | 2 |
| Detailed Tasks - Validate Required Information is Captured | FVVP-106 | 2 |
| Detailed Tasks - Confirm Notice | FVVP-105 | 2 |
| Detailed Tasks - Validate Notice | FVVP-104 | 2 |
| See Active Voids for a Building | FVVP-101 | 1 |
| See History of Voids on a Unit | FVVP-100 | 1 |
| See Void & Task Audit History | FVVP-99 | 1 |
| Upload Void Documents | FVVP-98 | 1 |
| See Unit View Arrangements & Key Location | FVVP-97 | 2 |
| Update Salesforce Unit - Keep Available Date Up-to-Date | FVVP-96 | 2 |
| Update Salesforce Unit - Keep FV Date Up-to-Date | FVVP-95 | 2 |
| Update Salesforce Unit - Keep Unit Status Up-to-Date | FVVP-94 | 5 |
| Update Salesforce Unit - New Void | FVVP-92 | 5 |
| See Estimated Available Date & Void Completion Date | FVVP-90 | 5 |
| Create a Void with Refurb / Refresh / Clean Only-Specific Tasks | FVVP-89 | 5 |
| Update Relet Status - Update Tasks | FVVP-87 | 5 |
| Create a Void with Relet Tasks | FVVP-86 | 5 |
| Dashboard - See New Voids Confirmed for Sale | FVVP-85 | 1 |
| New Void - Default Unit Sale Status from Salesforce | FVVP-84 | 1 |
| Dashboard - Other KPIs for R1 | FVVP-82 | 10 |
| Dashboard - See Open Tasks | FVVP-80 | 2 |
| Cancel a Void | FVVP-78 | 1 |
| Close a Void | FVVP-77 | 3 |
| See Summary of Void Phases & % Completion | FVVP-76 | 3 |
| Complete Voids are Read-Only | FVVP-75 |  |
| Dashboard - KPI: Vacant Days | FVVP-72 |  |
| Complete a Phase | FVVP-71 | 5 |
| Update Timelines - Tasks Dependent on a Void Date | FVVP-66 | 8 |
| Update Void Works Type - Update Tasks | FVVP-65 |  |
| Update Timelines - Tasks Dependent on Completion of Prior Tasks | FVVP-64 | 13 |
| Detailed Tasks - PVI | FVVP-63 |  |
| Rename "Void" Terminology | FVVP-62 |  |
| Set Tasks to Not Applicable [Close] | FVVP-61 | 1 |
| Capture a Reason for Updating Key Void Information | FVVP-59 | 3 |
| New End of Tenancy - Capture End of Tenancy Details | FVVP-58 | 3 |
| See Salesforce Unit & Building Attributes in a Void | FVVP-57 | 1 |
| New Void - Calculate Estimated PVI Date | FVVP-56 | 3 |
| Data Migration - Void Queues | FVVP-54 | 3 |
| New End of Tenancy - Assign Tasks to Responsible Queues | FVVP-53 | 5 |
| Calculate Estimated Timelines - Tasks Dependent on Completion of Prior Tasks | FVVP-51 | 13 |
| Calculate Estimated Timelines - Tasks Tied to an EOT Date | FVVP-50 | 5 |
| New End of Tenancy - Generate Phases & Tasks from a Template | FVVP-49 | 13 |
| New End of Tenancy - Create an End of Tenancy | FVVP-48 | 5 |
| Total |  | 185 |

## Budget

Below are the estimated invoice milestones:

| Month | Amount |
| --- | --- |
| October 2023 | £35,100 |
| November 2023 | £35,100 |
| December 2023 | £70,200 |
| January 2024 | £3,600 |
| February 2024 | £3,600 |
| Total | £147,600 |

## Delivery Milestones

| Milestone | Date | Duration |
| --- | --- | --- |
| Sprint 1 UAT | 02 October | 1 week |
| Sprint 2 UAT | 23 October | 1 week |
| Sprint 3 UAT | 13 November | 1 week |
| End-to-End UAT | 04 December | 2 weeks |
| Go-Live | January 2024 | NA |
| Production Support | On Go-Live | 2 weeks |

## Risks & Issues

- Current process is very manual with multiple variations. It will be a big change for all actors to follow a single process in Salesforce.

Mitigate: Involve all key stakeholders in UAT after each sprint to ensure alignment

- Adoption & change management will be critical.

Mitigate: Bring in Change Management consultants who are experts in this field.

- Complex process crossing multiple teams.

Mitigate: Incremental agile deliveries to measure and assess impact after each deployment

## Success Criteria

- User adoption of single process within Salesforce​

- ​Reduced turnaround time per void​

- ​Visibility into number of voids per employee​

- ​Reduced number of onsite visits per void