## Predecessor Report Sam & Anjali
Predecessor Report Sam & Anjali
As of 2023-11-02 09:52:05 Greenwich Mean Time/GMT • Generated by Open box
Filtered By
Show: All end of tenancy tasks
End Of Tenancy: End Of Tenancy Number equals EoT-00066
End Of Tenancy Phase: Sequence ↑ | End Of Tenancy Phase: End Of Tenancy Phase Name ↑ | End Of Tenancy Task Name ↑ | Start Date | Start Date Type | Actual End Date | Target End Date | Predecessor: End Of Tenancy Task Name | Predecessor: Actual End Date | Predecessor: Target End Date
1 | Receive Notice | Confirm Notice | 24/10/2023 | End of Tenancy Start Date | 24/10/2023 | 25/10/2023
|  | Validate Notice | 24/10/2023 | End of Tenancy Start Date | 24/10/2023 | 25/10/2023
2 | Notify Stakeholders | Amend Direct Debit | 24/10/2023 | Predecessor Task | 24/10/2023 | 26/10/2023 | Confirm Notice | 24/10/2023 | 25/10/2023
|  | Check Compliance | 24/10/2023 | Predecessor Task | 24/10/2023 | 31/10/2023 | Confirm Notice | 24/10/2023 | 25/10/2023
|  | Notify Stakeholders | 24/10/2023 | Predecessor Task | 24/10/2023 | 25/10/2023 | Confirm Notice | 24/10/2023 | 25/10/2023
|  | Set Rent | 24/10/2023 | Predecessor Task | 24/10/2023 | 27/10/2023 | Confirm Notice | 24/10/2023 | 25/10/2023
3 | PVI | PVI | 05/11/2023 | PVI Date | 24/10/2023 | 06/11/2023
4 | Book Works | Approve Capex |  | Predecessor Task |  |  | PVI | 24/10/2023 | 06/11/2023
|  | Book Works | 24/10/2023 | Predecessor Task |  | 28/10/2023 | PVI | 24/10/2023 | 06/11/2023
5 | Move Out | Cancel Direct Debit | 02/01/2024 | Predecessor Task |  | 04/01/2024 | Check Out |  | 02/01/2024
|  | Check Out | 01/01/2024 | Future Vacant Date |  | 02/01/2024
|  | Check Unit Condition | 01/01/2024 | Future Vacant Date |  | 04/01/2024
6 | Refurb/Refresh | Clean Unit | 04/01/2024 | Predecessor Task |  | 05/01/2024 | Check Unit Condition |  | 04/01/2024
|  | Finalize Check Out | 04/01/2024 | Predecessor Task |  | 08/01/2024 | Check Unit Condition |  | 04/01/2024
|  | Refresh |  | Predecessor Task |  |  | Check Unit Condition |  | 04/01/2024
|  | Refurb |  | Predecessor Task |  |  | Check Unit Condition |  | 04/01/2024
|  | Review Check Out Report | 04/01/2024 | Predecessor Task |  | 07/01/2024 | Check Unit Condition |  | 04/01/2024
7 | Close Tenancy | Close Down Tenancy | 08/01/2024 | Predecessor Task |  | 13/01/2024 | Refurb
|  |  | 08/01/2024 | Predecessor Task |  | 13/01/2024 | Refresh
|  |  | 08/01/2024 | Predecessor Task |  | 13/01/2024 | Clean Unit |  | 05/01/2024
|  |  | 08/01/2024 | Predecessor Task |  | 13/01/2024 | Finalize Check Out |  | 08/01/2024
|  |  | 08/01/2024 | Predecessor Task |  | 13/01/2024 | Cancel Direct Debit |  | 04/01/2024
|  | Deposit Release | 08/01/2024 | Predecessor Task |  | 11/01/2024 | Finalize Check Out |  | 08/01/2024
Confidential Information - Do Not Distribute
Copyright © 2000-2023 salesforce.com, inc. All rights reserved.

## Test Sheet
EoT Start Date | 2023-11-02
Future Vacant Date | 2023-12-25
PVI Date | 2023-12-15
Task Name |  | Start Date Type | Expected Start Date | Actual | Expected Target End Date | Actual Target End Date | Start Date Correct? | End Date Correct?
Confirm Notice |  | End of Tenancy Start Date | 2023-11-02 | 24/10/2023 | 2023-11-03 | 25/10/2023 | FALSE | FALSE
Validate Notice |  | End of Tenancy Start Date | 2023-11-02 | 24/10/2023 |  | 25/10/2023 | FALSE | FALSE
Amend Direct Debit |  | Predecessor Task | 2023-11-03 | 24/10/2023 | 2023-11-04 | 26/10/2023 | FALSE | FALSE
Check Compliance |  | Predecessor Task |  | 24/10/2023 |  | 31/10/2023 | FALSE | FALSE
Notify Stakeholders |  | Predecessor Task |  | 24/10/2023 |  | 25/10/2023 | FALSE | FALSE
Set Rent |  | Predecessor Task |  | 24/10/2023 |  | 27/10/2023 | FALSE | FALSE
PVI |  | PVI Date |  | 05/11/2023 |  | 06/11/2023 | FALSE | FALSE
Approve Capex |  | Predecessor Task |  | 0 |  | 0 | TRUE | TRUE
Book Works |  | Predecessor Task |  | 24/10/2023 |  | 28/10/2023 | FALSE | FALSE
Cancel Direct Debit |  | Predecessor Task |  | 02/01/2024 |  | 04/01/2024 | FALSE | FALSE
Check Out |  | Future Vacant Date |  | 01/01/2024 |  | 02/01/2024 | FALSE | FALSE
Check Unit Condition |  | Future Vacant Date |  | 01/01/2024 |  | 04/01/2024 | FALSE | FALSE
Clean Unit |  | Predecessor Task |  | 04/01/2024 |  | 05/01/2024 | FALSE | FALSE
Finalize Check Out |  | Predecessor Task |  | 04/01/2024 |  | 08/01/2024 | FALSE | FALSE
Refresh |  | Predecessor Task |  | 0 |  | 0 | TRUE | TRUE
Refurb |  | Predecessor Task |  | 0 |  | 0 | TRUE | TRUE
Review Check Out Report |  | Predecessor Task |  | 04/01/2024 |  | 07/01/2024 | FALSE | FALSE
Close Down Tenancy |  | Predecessor Task |  | 08/01/2024 |  | 13/01/2024 | FALSE | FALSE
|  | Predecessor Task |  | 08/01/2024 |  | 13/01/2024 | FALSE | FALSE
|  | Predecessor Task |  | 08/01/2024 |  | 13/01/2024 | FALSE | FALSE
|  | Predecessor Task |  | 08/01/2024 |  | 13/01/2024 | FALSE | FALSE
|  | Predecessor Task |  | 08/01/2024 |  | 13/01/2024 | FALSE | FALSE
Deposit Release |  | Predecessor Task |  | 08/01/2024 |  | 11/01/2024 | FALSE | FALSE
Formulas:
Expected Target End Date = [Expected Start Date]+1