## Sheet1
Item | Estimate (days) | MVP | Notes
Additional story refinement | 1 | 1
Add data validation + mandatory requirements to Contact fields | 1 | 1
Update error logging to mark all previous logs as resolved once referencing is successful
Update error logging to link to Opportunity and Contact |  | 2
Display lead and/or co-tenant referencing error on Opportunity record page
Component on Opportunity record page to Resubmit for referencing when lead or co-tenant(s) referencing has failed | 2 | 2 | simplified to resubmit any ocr with null applicant id
Report to show all Opportunities with as yet unresolved lead tenant and/or co-tenant referencing failure
Email alert to opportunity owner when lead tenant or co-tenant referencing fails
UAT support: 5 days elapsed time @ 4 hours/day | 2.5 | 2.5
TOTAL | 6.5 | 8.5