## Grainger Implementation Plan
Task ID | Task Description | Status | Group Owner | Owner | Start Date | Start Time | End Date | End Time | Comments
1 | Deploy to Pro - API Service (Iframe - CreateReferenceWithApplicantIframe) | Complete | Barbon
2 | Deploy to Pro - API Service (Iframe - AddApplicantToTenancyWithIframe) | Complete | Barbon
3 | Grainger Ip Whitelist - Raise Whitelist Request | In Progress | Barbon | Steve F | 6th Mar | 12:00 | 6th Mar | 15:00
4 | Grainger Ip Whitelist - Apply Change to Whitelist for Grainger | Pending | Barbon | Pete Banks | 7th Mar | 9:00 | 8th Mar | 18:00
5 | Setup API Keys and Credentials for each ASN ClientID / Client Secret) | Pending | Barbon | Steve F | 6th Mar | 13:00 | 6th Mar | 17:00
6 | Provide AUTH URL to Grainger - for Generating Token using Client Key/Secret(s) | Pending | Barbon | Erica | 7th Mar | 9:00 | 7th Mar | 17:00
7 | Issue Webhook End Point / Credentials for Status updates in Live (EndPoint) | Pending | Grainger | Jaic | 8th Mar | 12:00 | 8th Mar | 12:00 | Jaic to confirm plan dates - JB assumption
8 | Confirm if Webhook end point same for all agents or different for each | Pending | Grainger | Jaic | 8th Mar | 12:00 | 8th Mar | 12:00 | Jaic to confirm plan dates - JB assumption
9 | Configure Webhook for Status Updates in Production | Pending | Barbon | Ajay | 8th Mar | 12:30 | 8th Mar | 15:00 | Dependent on details from Jaic for Webhook
10 | Barbon - IT Ready for Shakedown Test |  |  |  | 8th Mar | 16:00
11 | Go-No Go Review to agree Salesforce Prod Implementation | Pending | Grainger | Scott | 12th Mar | TBC | 12th Mar | TBC | Scott to confirm
12 | Saleforce Deployment | Pending | Saleforce | Sam | 13th Mar | TBC | 13th Mar | TBC | Sam to confirm
13 | Salesforce - IT Ready for Shakedown |  |  |  | 13th Mar | TBC
14 | Shakedown Test in Prod - Further details (Meeting, Branch/ data etc.. To be defined) | Pending | ALL | ALL | 14th Mar | 9:00 | 14th Mar | 12:00 | Scott to schedule E2E walkthrough in Zoom.