## Consulting SOW Estimate
Rates (£) |  |  |  | Timelines |  |  | Contributors | Consultancy |  |  |  | Points
Currency | £ | Discounted from: |  | Target Start Date | 2025-11-17 |  | Sam Duncan |  | Hours | # OB Attendees | Workshops | Estimated Feature Points
Sprint 0 Rate per Hour (T&M) | 126 | 163 |  | Xmas Break (days) | 14 |  | Shaun Barrett | Client Meetings | 8 | 4 | 6 x 1 for each pillar; 2 x Follow up session; IT & Data Warehouse | Unanticipated Scope
Project Rate per Hour | 97.5 | 102.38 |  |  |  |  | Nikki Papenfus | Internal Meetings | 6 | 3 |  | Unanticipated Complexity
[7 empty] | Jacob Smycz | POC | 16 |  |  | Total Points | 0
Internal | [7 empty] | Create Backlog | 24
Project Phase | FTE | Min Effort | Max Effort | Lower Bound (£) | Upper Bound (£) |  |  | Proposal Document & Estimates | 28 |  |  | Velocity
Consultancy (Hours) |  | 120 | 150 | 15120 | 18900 |  |  | Total Hours (Min) | 118 | Contingency |  | Range | Points per Dev per 3-week Sprint |  | Points per Sprint
Sprint 0 |  | 65 | 80 | 8190 | 10080 |  |  | Total Hours (Max) | 148 | 25% |  | Optimistic | 1 Senior Dev FTE |  | 0
Build (Sprints) |  | 3 | 4 | 105300 | 140400 | [7 empty] | 1 Junior Dev FTE
Final UAT (Weeks) | 0.25 | 3 | 3 | 2925 | 2925 |  |  | Sprint Zero |  |  |  | Pessimistic | % of Optimistic | 80% | 0
Deployment & Support (Weeks) | 0.25 | 2 | 2 | 1950 | 1950 |  |  | Weeks (Min) | 3
User Guide (Hours) |  | 9.01 | 12.025 | 1135.26 | 1515.15 |  |  | BA Allocation | 40% | # OB Attendees |  | Key
Total |  |  |  | 134620.26 | 175770.15 |  |  | Client Meetings per week (Hrs) | 3 | 4 |  | Enter value
[8 empty] | Internal Meetings per week (Hrs) | 1 | 3 |  | Default value across projects
External Quote | [7 empty] | Total Hours (Min) | 63 | Contingency |  | Calculated
Project Phase |  | Duration (Weeks) |  | Lower Bound (£) | Upper Bound (£) | End Date Earliest | End Date Latest | Total Hours (Max) | 76 | 20%
Consultancy |  | 4 | 4 | 15120 | 18900 | 2025-12-14 | 2025-12-14
Sprint 0 |  | 3 | 4 | 8190 | 10080 | 2026-01-18 | 2026-01-25 | Sprint Team
Build |  | 9 | 12 | 105300 | 140400 | 2026-03-22 | 2026-04-19 | Role | # People | Allocation | FTE
Final UAT |  | 3 | 3 | 2925 | 2925 | 2026-04-12 | 2026-05-10 | Dev Senior | 1 | 100% | 1
Prod Deployment & Support |  | 2 | 2 | 1950 | 1950 | 2026-04-26 | 2026-05-24 | Dev Junior | 1 | 65% | 0.65
User Guide |  | 0 | 0 | 1135.26 | 1515.15 |  |  | QA | 1 | 55% | 0.55
Total |  | 21 | 25 | 134620.26 | 175770.15 |  |  | Dev:QA |  | 33.33%
Total Months (Duration) |  | 5.3077 | 6.2308 |  |  |  |  | Jacob | 1 | 15% | 0.15
[5 empty] | Target: 177k |  | Target: May | BA | 1 | 35% | 0.35
[8 empty] | Architect | 1 | 15% | 0.15
[8 empty] | PM | 1 | 15% | 0.15
[8 empty] | Team Size |  |  | 3
[8 empty] | Weeks per Sprint |  |  | 3
[8 empty] | Cost per Sprint (£) |  |  | 35100
[8 empty] | EoT per sprint |  |  | 35100
Formulas:
Sam Duncan = [Sam Duncan, row above]+(E20)*7+G4
Sam Duncan = [Sam Duncan, row above]+E21*7
Note on W4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider the extent of discovery already completed, and knowledge of the client's business & Org.
Note on W5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider extent of custom component development, use of 3rd party apps, 3rd party integrations.
Note on X10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 point story = 5 days to dev, QA, fix bugs & deploy
Note on Z10: Nikki Papenfus: TO BE DECIDED SVOT project: Average points delivered by 1 Dev FTE in a 3 week sprint = 16.4 points

## Consulting SOW Estimate1 (hidden)
Rates (£) |  |  |  | Workshops |  | Key
Currency | £ |  |  | 6 x 1 for each pillar |  | Enter value
Sprint 0 Rate per Hour (T&M) | 163 |  |  | 2 x Follow up session |  | Default value across projects
Contingency | 30% |  |  |  |  | Calculated (formula)
CX
Consultancy |  |  |  | IT / GREP |  | People involved in Estimate
| Hours | # OB Attendees |  | Data Warehouse |  | Sam Duncan
Client Meetings / Workshops | 8 | 4 |  |  |  | Shaun Barrett
Internal Meetings | 4 | 3 |  |  |  | Nikki Papenfus
POC | 12
Create Backlog | 24
Proposal Document & Estimates | 28 |  |  |  |  | Notes
Total Hours (Min) | 108
Total Hours (Max) | 140
External Quote
Project Phase | Min Effort | Max Effort | Duration (Weeks) |  | Lower Bound (£) | Upper Bound (£)
Consultancy (Hours) | 110 | 140 |  |  | 17930 | 22820
Total |  |  |  |  | 17930 | 22820

## Proposal x Estimate
Rates (£) |  |  | Points |  | Sprint Team | [5 empty] | Key
Currency | £ |  | Estimated Feature Points |  | Role | # People | Allocation | FTE | Split | Target | Enter value
Sprint 0 Rate per Hour (T&M) | 163 |  | Unanticipated Scope |  | Dev Senior | 1 | 100% | 1 | 50% |  | Default value across projects
Project Rate per Hour | 102.375 | 105% | Unanticipated Complexity |  | Dev Junior | 1 | 0% | 0 |  |  | Calculated (formula)
Weeks per Sprint | 3 |  | Total Points | 0 | QA | 1 | 40% | 0.4 | 20%
[5 empty] | Jacob | 1 | 10% | 0.1 | 25% |  | People involved in Estimate
UAT & Production Support |  |  | Build - Sprints |  | BA | 1 | 30% | 0.3
UAT Weeks | 2 |  | Optimistic Sprint # | 0 | Architect | 1 | 10% | 0.1
Prod Support Weeks | 2 |  | Pessimistic Sprint # | 0 | PM | 1 | 10% | 0.1 | 5%
Team Size (FTEs) - UAT | 0.5 |  | Team Size (FTEs) | 2 | Team Size |  |  | 2 | 100% | 0%
Cost per Week (£) | 2047.5 |  | Cost per Sprint (£) | 24570
Velocity
Notes |  |  |  |  | Range | Points per Dev per 3-week Sprint |  |  | Points per Sprint
1 Release, must have functionality only; target cost 100-140k |  |  |  |  | Optimistic | 1 Senior Dev FTE |  | 20 | 20
[6 empty] | 1 Junior Dev FTE |  | 17
[5 empty] | Pessimistic | % of Optimistic |  | 80% | 16
Internal
Project Phase | Min Effort | Max Effort | Lower Bound (£) | Upper Bound (£) | Sprint 0 |  |  |  | Consultancy (Min)
Consultancy (Hours) |  |  | 0 | 0 | Weeks (Min) |  | 3
Sprint 0 |  |  | 0 | 0 | BA Allocation (Min) |  | 30%
Build (Sprints) |  |  | 0 | 0 | BA Allocation (Max) |  | 45% | Pax: | Backlog (Hrs) |  |  | pax
Final UAT (Weeks) 0,5 FTE | 2 | 2 | 4095 | 4095 | Client Meetings (hrs/week) |  | 3 | 4 | Client Meetings (Hrs)
Prod Deployment & Support (Weeks) 0,25 FTE | 2 | 2 | 2047.5 | 2047.5 | Internal Meetings (hrs/week) |  | 1 | 3 | Internal Meetings (Hrs)
User Guide (Hours) |  |  | 0 | 0 | Total Hours (Min) |  | 81 |  | Document (Hrs)
Total |  |  | 6142.5 | 6142.5 | Total Hours (Max) |  | 99 |  | Total Hours (min) |  | 0
External Quote |  |  |  |  | Timelines
| Duration (Weeks) |  | Lower Bound (£) | Upper Bound (£) | Target Start Date |  |  | 2025-11-01
Consultancy | 4 | 4 | 0 | 0 | Estimated End Date
Sprint 0 | 3 | 3 | 0 | 0 | Release 1 | Lower Bound |  | Upper Bound
Build | 0 | 0 | 0 | 0 | Consultancy / Sprint 0 | 2025-12-19 |  | 2025-12-19
Final UAT | 2 | 2 | 4095 | 4095 | Xmas Break (days) | 14 |  | 14
Prod Deployment & Support | 2 | 2 | 2047.5 | 2047.5 | Build | 2026-01-02 |  | 2026-01-02
User Guide | 0 | 0 | 0 | 0 | UAT/Go Live | 2026-01-16 |  | 2026-01-16
Total | 11 | 11 | 6142.5 | 6142.5 | Support | 2026-01-30 |  | 2026-01-30
Xmas | 2 | 2
Months Duration | 3 | 3
Formulas:
FTE = K32+D32*7+[FTE, row above]
FTE = [FTE, row above]+D33*7
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider the extent of discovery already completed, and knowledge of the client's business & Org.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider extent of custom component development, use of 3rd party apps, 3rd party integrations.
Note on B11: Nikki Papenfus: Seems high for support. Should we allow for different FTEs for UAT & support?
Note on I15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 point story = 5 days to dev, QA, fix bugs & deploy
Note on K15: Nikki Papenfus: TO BE DECIDED SVOT project: Average points delivered by 1 Dev FTE in a 3 week sprint = 16.4 points

## Proposal x_Features
Epic | Feature | Scope Notes | Points

## DNU_SOW v1 (hidden)
Key
Enter Value
Do not update (Formula)
Currency | £
Rates & Team |  | Velocity & Duration
Sprint 0 Rate (T&M) | 120 | Estimated Story Points | 110
Project Rate | 97 | Optimistic Velocity | 25
Team Size - Build | 3 | Pesimistic Velocity | 15
Team Size - UAT & Prod Support | 1 | Optimistic Sprint # | 5
Cost Per 3 Week Sprint | 120 | Pesimistic Sprint # | 8
Cost for UAT & Prod (per week) | 3880 | UAT Weeks | 2
|  | Prod Support Weeks | 2
Internal
Project Phase | Lower Bound Effort | Upper Bound Effort | Notes | Lower Bound | Upper Bound
Sprint 0 (hours) | 80 | 100 | 4 weeks | 9600 | 12000
Release 1: 5 to 8 Sprints | 5 | 8 |  | 600 | 960
Final UAT | 2 | 2 |  | 7760 | 7760
Production Deployment & Post Go-Live Support | 2 | 2 |  | 7760 | 7760
User guide creation | 6 | 8 | Done in parallel with sprints | 720 | 960 | `
Total Cost for Release 1 |  |  |  | 26440 | 29440
External
Project Phase | Duration | Lower Bound | Upper Bound
Sprint 0 (hours) |  | 9600 | 12000
Release 1: 5 to 8 Sprints |  | 600 | 960
Final UAT |  | 7760 | 7760
Production Deployment & Post Go-Live Support |  | 7760 | 7760
User guide creation |  | 720 | 960
Total Cost for Release 1 |  | 26440 | 29440
Note on F7: Nikki Papenfus: Need to add a contingency factor - this is a SOW / proposal-level estimate. Add a % for unknown 'must have' requirements, which may vary depending on the extent of discovery already done, knowledge of the client's business & org. Add a % for unanticipated complexity of known features, which may vary depending on extent of custom components, external plug ins, 3rd party integration.
Note on F8: Nikki Papenfus: The veloocity #s should be a formula based on number of developers / dev FTEs
Note on D9: Nikki Papenfus: this should round up to the nearerst 0,5 or 0,25
Note on D11: Nikki Papenfus: this needs to be a formula
Note on E32: Nikki Papenfus: these totals should be a sum of the above in case we change them

## DNU_Team & Velocity v1 (hidden)
Team Composition | Allocation
Architect | 100%
Dev Senior | 100%
Dev Junior | 50%
QA | 25%
BA | 12.5%
PM | 20%
Team Size | 3.075
Velocity | Story Points per Sprint
Optimistic | 25
Pessimistic | 15
Note on B1: Nikki Papenfus: Is this FTE or allocation? If allocation, then the # of resources is mising from the equation
Note on B6: Nikki Papenfus: these inputs need to go on the main page. This will vary based on project complexity / size / etc, e.g. renewals was a 75% BA allocation for the project. Other projects might not be. If this is a formula, then the inputs to the formula should be transparant and editable
Note on B11: Nikki Papenfus: This needs to be a formula based on number of devs. or this need to be the number of points for one dev? Question = do we modify the velocity depending the junior / senior dev mix? Yes - this will be updated per project and taking team into consideration

## Currency (hidden)
Dollar | $
Pound | £
Rand | R