## Estimate
Phase | Hours | Lower Bound | Upper Bound
Analysis | 8-10 | 960 | 1200
Build | 40 - 48 | 4800 | 5760
Project Management | 4-5 | 480 | 600
UAT | 8-10 | 960 | 1200
Production deployment and post go-live support | 8-10 | 960 | 1200
Total | 68 - 83 | 8160 | 9960
| 8 | 10
| 40 | 48
| 4 | 5
| 8 | 10
| 8 | 10
| 68 | 83
|  |  |  | Phase | Original | Re-Estimate
Actual Hours (up to UAT Kick-off) |  | 75 |  | Delivery (complete) | 63 | 75
UAT Reforcast |  | 22.5 |  | UAT | 10 | 22.5
- Meetings | 3 |  |  | Production Support | 6.5 | 6.5
- UAT Reports | 0.5 |  |  | Weekly backup (12 weeks) | 0 | 6
- UAT Testing Assistance | 16 |  |  | Total | 79.5 | 110
- Other | 3
Prod |  | 12.5
Prod Support | 6.5
Weekly backup prior to anonymization running (12 weeks) | 6
Total Hours |  | 110

## Actuals
Phase | Estimate | Re-Estimate | Actuals | Util (Original) | Util (Re-Estimate) | Challenges
Delivery (Analysis, Build, PM) | 63 | 75 | 235 | 373% | 313.3% | Timelines were pushed out
UAT | 10 | 22.25 | 20 | 200% | 89.89% | UAT approach required more effort
Prod Support | 6.5 | 6.5 | 0.75 | 11.54% | 11.54% | No documentation accounted for in original estimate or re-estimate
Weekly Prod BackUps |  | 6 |  |  |  | UAT identified issues that we could not pick up in QA
Total Hours | 79.5 | 110 | 255.75 | 321.7% | 232.5% | several validation rules are preventing certain lead/contact records from being updated
Cost Estimates and "Actuals" | 9540 | 13200 | 30690 |  |  | Change Control 1
Re-estimated on 23 July (due to the stop/start nature of this project, along with the additional effort needed to assist with UAT)
Phase | Estimate |  | Actuals | Util (Original)
Change Control 1 | 14 |  | 37 | 264.3%
Cost Estimates and "Actuals" | 2100 |  | 5550
Note on E8: Shaun Barrett: What we should have invoiced for our effort
Note on E12: Shaun Barrett: What we should have invoiced for our effort

## Timelines
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19
| 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-17 | 2024-06-24 | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23
SOW | 2024-05-20: Analysis
Build
UAT
Prod
|  |  |  | Hypercare | Hypercare
Actual | 2024-05-20: Analysis
|  | Build |  | Build
UAT
Prod
[16 empty] | Hypercare | Hypercare