## SOW
Project Phases | Duration | Lower Bound | Upper Bound
Sprint 0 | 2-3 weeks | £ 6,000 | £ 9,000 | 6000 | 9000
Sprint 1 - 2 | 3-6 weeks | £ 23,400 | £ 46,800 | 23400 | 46800
UAT | 2 weeks | £ 3,600 | £ 3,600 | 3600 | 3600
Production Deployment & Post Go-Live Support | 2 weeks | £ 3,600 | £ 3,600 | 3600 | 3600
User guide creation | Done in parallel with sprints | £ 3,150 | £ 3,150 | 3150 | 3150
Sub Total | 9 - 13 weeks | £ 39,750 | £ 66,150 | 39750 | 66150
Contingency for ongoing post-go live support | 40 hours | £ - | £ 4,800 |  | 4800
Total | 9 -13 weeks | £ 39,750 | £ 70,950 | 39750 | 70950

## Forecasting-Foundational
|  |  |  | Sprint 0 | Sprint 1
Scheduling
Velocity
| Total Velocity Done |  |  | 0 | #N/A
| Total Backlog Size |  |  | 17 | 17
For Bars | Optimistic Forecast |  |  | 0 | 25
| Likely Forecast |  |  | 0 | 20
| Pessimistic Forecast |  |  | 0 | 15
For T&M | Costing
| Team Sprint Cost (Actual) |  |  |  | 23400
| Cumulative Team Cost (Actual) |  |  | 0 | 23400
| Cumulative Team Cost (Forecast) |  |  | 0 | 23400
Team Metrics
Optimistic Velocity ( Best Velocity in last 3 sprints) | 25
Likely Velocity (Avg Velocity over last 3 sprints) | 20
Pessimistic Velocity (Worst Velocity in last 3 sprints) | 15
Team Composition | Hourly Rate | Allocation | Cost Per Sprint
Team cost / sprint |  |  | 23400
Dev Senior |  | 100%
Dev Junior |  | 50%
QA |  | 25%
BA |  | 12.5%
PM |  | 13%
Total |  |  | 23400
2 FTE for 3 weeks

## Forecasting-Release 1
|  |  |  | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | Sprint 23 | Sprint 24 | Sprint 25 | Sprint 26 | Sprint 27 | Sprint 28 | Sprint 29 | Sprint 30 | Sprint 31 | Sprint 32 | Sprint 33
Scheduling
Velocity
| Total Velocity Done |  |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total Backlog Size |  |  | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
For Bars | Optimistic Forecast |  |  | 0 | 25 | 50 | 75 | 100 | 125 | 150 | 175 | 200 | 225 | 250 | 275 | 300 | 325 | 350 | 375 | 400 | 425 | 450 | 475 | 500 | 525 | 550 | 575 | 600 | 625 | 650 | 675 | 700 | 725 | 750 | 775 | 800 | 825
| Likely Forecast |  |  | 0 | 20 | 40 | 60 | 80 | 100 | 120 | 140 | 160 | 180 | 200 | 220 | 240 | 260 | 280 | 300 | 320 | 340 | 360 | 380 | 400 | 420 | 440 | 460 | 480 | 500 | 520 | 540 | 560 | 580 | 600 | 620 | 640 | 660
| Pessimistic Forecast |  |  | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450 | 465 | 480 | 495
For T&M | Costing
| Team Sprint Cost (Actual) |  |  |  | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400
| Cumulative Team Cost (Actual) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Cumulative Team Cost (Forecast) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | 234000 | 257400 | 280800 | 304200 | 327600 | 351000 | 374400 | 397800 | 421200 | 444600 | 468000 | 491400 | 514800 | 538200 | 561600 | 585000 | 608400 | 631800 | 655200 | 678600 | 702000 | 725400 | 748800 | 772200
Team Metrics
Optimistic Velocity ( Best Velocity in last 3 sprints) | 25
Likely Velocity (Avg Velocity over last 3 sprints) | 20
Pessimistic Velocity (Worst Velocity in last 3 sprints) | 15
Team Composition | Hourly Rate | Allocation | Cost Per Sprint
Team cost / sprint |  |  | 23400
Dev Senior |  | 100%
Dev Junior |  | 50%
QA |  | 25%
BA |  | 12.5%
PM |  | 13%
Total |  |  | 23400
2 FTE for 3 weeks
31200
15600

## Post Sprint 0 Cost Summary
Cost per sprint | 23400
|  | Phase | Duration | Lower Bound | Upper Bound
|  | Foundational: 1 Sprint | 3 weeks | 23400 | 23400
|  | Release 1: 2 - 3 Sprints | 6 - 9 weeks | 46800 | 70200
|  | UAT | 2 weeks | 3600 | 3600
|  | Production Deployment & Post Go-Live Support | 2 weeks | 3600 | 3600
|  | User guide creation | Done in parallel with sprints | 3150 | 3150
|  | Total Cost for Foundational Changes and Release 1 | 13 - 16 | 80550 | 103950
|  | Overview | Duration | Lower Bound | Upper Bound
|  | Foundational Cost | 3 weeks | 23400 | 23400
|  | Release 1 Cost | 10 - 13 weeks | 57150 | 80550
|  | Total Cost | 13 - 16 weeks | 80550 | 103950
|  | Phase | Duration | Lower Bound | Upper Bound
|  | Backlog | 3 - 6 weeks | 23400 | 46800
|  | UAT | 2 weeks | 3600 | 3600
|  | Production Deployment & Post Go-Live Support | 2 weeks | 3600 | 3600
|  | Total | 7 - 10 weeks | 30600 | 54000

## Final Cost Estimate
Project Phases | Duration | Estimate | Upper Bound
Sprint 0 | 2-3 weeks | 6000 | 9000 | Numbers |  | Team
2 sprints | 6 weeks | 46800 | 46800 | FTEs | 2 | Dev | 1.5
UAT | 2 weeks | 3600 | 3600 | Backlog size | 37 | QA, BA, PM | 0.5
Production Deployment & Post Go-Live Support | 2 weeks | 3600 | 3600 | Estimated velocity | 20
User guide creation | Done in parallel with sprints | 3150 | 3150 | Sprints | 2
Total | 12 -13 weeks | 63150 | 66150

## Timeline
Cost per sprint | 23400
UAT | 3600 | Sprint 1 | [20 empty] | Sprint 2 | [20 empty] | UAT | [6 empty] | UAT | [6 empty] | Prod Support | [6 empty] | Prod Support
Prod support | 3600 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
User Guide | 3150 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
 | time axis 2024-10-14 to 2024-12-22
Nov (S1) | 23400
Dec (S2 + UG) | 26550
Jan | 7200
Total | 57150
SOW
Sprint 0 | 9000
Build | 57150
Total | 66150