## Backlog v1
Feature | Points | 85 | Must Have | SOW
Update /Maintain RTR Object | 11 | 12.94%
RTR-14,Update RTR Status Options | 0.5 |  | Y | Y
RTR-12,See Date Next RTR is Required | 1 |  | Y | Y
RTR-8,Update Previous RTR Records to 'Archived' | 2 |  | Y | Y
RTR-5,Validate Check Date when Capturing RTR | 1.5 |  | Y | Y
RTR-16,Close Tasks when RTR is Completed | 0.5 |  |  | N
RTR-25,Hide 'Completed By' Field on RTR | 0.5 |  |  | N
RTR-31,Close Incomplete RTR if a Tenant Vacates or an Opportunity is Lost | 5 |  |  | Y
Notify Tenants & Users when RTR is Expiring | 18 | 21.18%
RTR-1,Create RTR & Tasks Prior to Expiry | 8 |  | Y | Y
RTR-30,Send Email Requests for New RTR to Resident | 5 |  | Y | Y
RTR-13,Notify Users when Tenant Responds to an Email or Email Bounces | 5 |  | Y | N
Ensure all Tenants have RTR on New Lease or Renewal | 6 | 7.059%
RTR-4,See All Current & Outstanding RTR for Tenants when Viewing an Opportunity | 2 |  | Y | Y
RTR-3,Only Create RTR for New Tenants added to a Renewal/COS Opportunity | 2 |  | Y | Y
RTR-7,Ensure All Tenants have RTR before sending a New Lease/COS/Renewal Contract for Signing | 2 |  | Y | Y
Tenancy Data Clean Up - Once Off & Ongoing | 23 | 27.06%
RTR-2,Bulk Update - Activate & End Historical Tenancy Statuses | 8 |  | Y | N
RTR-29,[Placeholder] Incorporate Feedback/Exceptions to Updating Tenancy Status | 2.5 |  | Y | N
RTR-10,Data Extracts - Identify Tenancy Data for Manual Clean up in Salesforce | 3 |  | Y | Y
RTR-24,View List of Related Tenancies for a Unit | 0.5 |  | Y | N
RTR-19,Activate New & End Old Tenancies on COS & Renewal | 8 |  | Y | N
RTR-27,Save Effective End Date of Tenancy | 0.5 |  | Y | N
RTR-26,Only Create EOT for Active Tenancies | 0.5 |  | Y | N
RTR Data Clean Up | 13 | 15.29%
RTR-6,Bulk Update - Create RTR Records for Current Tenants with no RTR Data | 3 |  |  | N
RTR-21,Data Extracts - Permitted Occupiers to be Cleaned up in Salesforce | 2 |  | Y | N
RTR-20,Data Extracts - Identify RTR Data to be Cleaned up in Salesforce | 8 |  | Y | N
RTR Document & Record Deletions | 11 | 12.94%
RTR-11,Delete RTR Info for Former Tenants & Lost Opportunities | 8 |  | Identify | N
RTR-22,Data Extract - Identify Missing Vacate Date for Former Tenants with a RTR Document | 3 |  | Y | N
Enhance Single View of Customer | 3 | 3.529%
RTR-17,See Current RTR Status for a Tenant | 3 |  |  | N

## Backlog v2
| Story Points | 75.5 | Must Have | In SOW
Release 1 | 36.5 | 48.34%
Update/Maintain RTR Object | 5.5 | 7.285%
RTR-14: Update RTR Status Options | 0.5 |  | Y | Y
RTR-12: See Date Next RTR is Required | 1 |  | Y | Y
RTR-8: Update Previous RTR Records to 'Archived' | 2 |  | Y | Y
RTR-5: Validate Check Date when Capturing RTR | 1.5 |  | Y | Y
RTR-17: Update Existing RTR Customer Data Sync | 0.5 |  | Y | Y
Notify Tenants & Users when RTR is Expiring | 18 | 23.84%
RTR-1: Create RTR & Tasks Prior to Expiry | 8 |  | Y | Y
RTR-30: Send Email Requests for New RTR to Resident | 5 |  | Y | Y
RTR-13: Notify Users when Tenant Responds to an Email or Email Bounces | 5 |  | Y | N
Ensure all Tenants have RTR on New Lease or Renewal | 6 | 7.947%
RTR-4: See All Current & Outstanding RTR for Tenants when Viewing an Opportunity | 2 |  | Y | Y
RTR-3: Only Create RTR for New Tenants added to a Renewal/COS Opportunity | 2 |  | Y | Y
RTR-7: Ensure All Tenants have RTR before sending a New Lease/COS/Renewal Contract for Signing | 2 |  | Y | Y
RTR Data Clean Up | 7 | 9.272%
RTR-21: Data Extracts - Permitted Occupiers to be Cleaned up in Salesforce | 2 |  | Y | N
RTR-20: Data Extracts - Identify RTR Data to be Cleaned up in Salesforce | 5 |  | Y | N
Parallel Tenancy Clean Up Project | 17 | 22.52%
Tenancy Data Clean Up - Once Off Update of Historical Data | 11 | 14.57%
RTR-2: Bulk Update - Activate & End Historical Tenancy Statuses | 7.5 |  | Y | N
RTR-10: Data Extracts - Identify Tenancy Data for Manual Clean up in Salesforce | 3 |  | Y | Y
RTR-24: View List of Related Tenancies for a Unit | 0.5 |  | Y | N
Tenancy Data Clean Up - Maintain Data Quality Going Forward | 6 | 7.947%
RTR-19: Activate New & End Old Tenancies on COS & Renewal | 5 |  | Y | N
RTR-27: Save Effective End Date of Tenancy | 0.5 |  | Y | N
RTR-26: Only Create EOT for Active Tenancies | 0.5 |  | Y | N
Release 2 - New 'Must Have' Scope | 14 | 18.54%
Delete RTR Documents & Records | 11 | 14.57%
RTR-11: Delete RTR Info for Former Tenants & Lost Opportunities | 8 |  | Y | N
RTR-22: Data Extract - Identify Missing Vacate Date for Former Tenants with a RTR Document | 3 |  | Y | N
RTR Data Clean Up | 3 | 3.974%
RTR-6: Bulk Update - Create RTR Records for Current Tenants with no RTR Data | 3 |  |  | N
Backlog | 8 | 10.6%
Enhance Single View of Customer | 2.5 | 3.311%
RTR-17: See Current RTR Status for a Tenant | 2.5 |  |  | N
Maintain Tasks & RTR | 5.5 | 7.285%
RTR-16: Close Tasks when RTR is Completed | 0.5 |  |  | N
RTR-31: Close Incomplete RTR if a Tenant Vacates or an Opportunity is Lost | 5 |  |  | Y

## Backlog v3
Story Points
Release 1 | 38.5 | Changes to Story
Update/Maintain RTR Object | 7.5
RTR-14: Update RTR Status Options | 0.5 | Add: 'Moved Out' status
RTR-12: See Date Next RTR is Required | 1
RTR-8: Update Previous RTR Records to 'Archived' | 2
RTR-5: Validate Check Date when Capturing RTR | 2 | Add: Default record owner to Onsite PM team for the unit; +0,5 point
RTR-17: Update Existing RTR Customer Data Sync | 2 | Simplified; removed tenant-level flag; -1 point | SB: This has increased by 1,5 | NP: I split the scope of this in R2; was a little over-enthusiastic in moving it down to 0,5 point I think. Original estimate was 3pts
Notify Tenants & Users when RTR is Expiring | 13
Add calculated fields: If RTR needs a reminder email & Date manual follow up is required (catering for earlier follow up if there is no email address saved for the tenant) | 2 | New story; Limitation: only caters for 1 manual follow up date
RTR-30: Send Email Requests for New RTR to Resident | 5 | Stamp template name/'Follow-up Status' & date last email sent (new fields); Send based on the last email template sent
RTR-13: Notify Users when Tenant Responds to an Email or Email Bounces | 5 | Send email to record owner instead of task
Create a List View of expiring RTR Records that Require Manual follow up and new RTR records that are in progress. | 1 | New story
Ensure all Tenants have RTR on New Lease or Renewal | 6.5
RTR-4: See All Current & Outstanding RTR for Tenants when Viewing an Opportunity | 2
RTR-3: Only Create RTR for New Tenants added to a Renewal/COS Opportunity | 2.5 | Add: Default record owner to Onsite PM team when creating a new RTR record; +0,5 point
RTR-7: Ensure All Tenants have RTR before sending a New Lease/COS/Renewal Contract for Signing | 2
RTR Data Clean Up | 11.5
RTR-20: Data Extracts - Identify RTR Data to be Cleaned up in Salesforce | 5
RTR-6: Bulk Update - Create RTR Records for Current Tenants with no RTR Data | 2 | New Scope for R1; simpler logic (based on Qube list; no task required); - 1 point
Monthly Bulk Update - Update Status of RTR Records based on Qube List of Active Tenants (& active opportunities) | 2.5 | New story; effort for initial load only
Once-off Bulk Update - Populate unit & record owner (Onsite PM Team) on existing RTR records | 2 | New story; default to Renewals Team if RTR cannot be linked to a unit.
Parallel Tenancy Clean Up Project | 17
Tenancy Data Clean Up - Once Off Update of Historical Data | 11
RTR-2: Bulk Update - Activate & End Historical Tenancy Statuses | 7.5
RTR-10: Data Extracts - Identify Tenancy Data for Manual Clean up in Salesforce | 3
RTR-24: View List of Related Tenancies for a Unit | 0.5
Tenancy Data Clean Up - Maintain Data Quality Going Forward | 6
RTR-19: Activate New & End Old Tenancies on COS & Renewal | 5
RTR-27: Save Effective End Date of Tenancy | 0.5
RTR-26: Only Create EOT for Active Tenancies | 0.5
Backlog | 27.5
Notify Tenants & Users when RTR is Expiring | 8
RTR-1: Create RTR & Tasks Prior to Expiry | 8
Delete RTR Documents & Records | 11
RTR-11: Delete RTR Info for Former Tenants & Lost Opportunities | 8
RTR-22: Data Extract - Identify Missing Vacate Date for Former Tenants with a RTR Document | 3
Enhance Single View of Customer | 1
RTR-17: See Current RTR Status for a Tenant | 1
Maintain Tasks & RTR | 7.5
RTR-16: Close Tasks when RTR is Completed | 0.5
RTR-31: Close Incomplete RTR if a Tenant Vacates or an Opportunity is Lost | 5
RTR-21: Data Extracts - Permitted Occupiers to be Cleaned up in Salesforce | 2 | Cannot provide list without active tenancy status being updated
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Shaun Barrett Reply: Ok thanks
Note on A13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Filter: RTR record Status = ‘Completed’ AND Time Limited = True AND current date >= Follow Up Start Date Display: Tenant Unit Record Owner Flag Follow Up Start Date Expiry Date Date Next RTR Due Follow Up Status Last Follow Up Date