## Tenancy Data
QUBE | Salesforce |  | Note | Action | Other systems impacted by data field
Unit Lease Start date | Opportunity | Move_In_Date__c | The unit lease start date is not published in Qube API. Request made to MRI to add to API. Currently integration is using Parent tenancy start date as the Tenancy start date in Salesforce | MRI to publish unit lease start date in API-Change Request raised. Integration will be updated when this data is available in API. Until then use the Parent Tenant start date in integration. JIRA CJR-481 CJR-475 CJR-419 | None
| Contract/Tenancy | Latest_Contract_Start_Date__c
Unit Lease end date | Opportunity | Tenancy_End_Date__c | The unit lease end date is not published in Qube API. Request made to MRI to add to API. Currently integration is using Parent tenancy end date to pass to salesforce but this will always be blank (not completed in Qube until Tenant has left the tenancy). This is causing issues in Salesforce as tenancy end date must be populated on The Opportunity in order for the stage to be moved to COMPLETED-WON. | Remove the tenancy end date from the Qube to Salesforce Integration. This field will be blank on opportunities created in Salesforce via GREP for tenancies that originated in Qube. JG confirms that this ill not impact on ability to set the stage to COMPLETED-WON as the stage is populated by Integration and not workflow. CJR-549 | None
Qube Tenancy reference | Opportunity | PMS_Reference__c | Data must exist in Salesforce on the Tenancy for the integration of data to pass across systems. Data is populated on Opportunity when Lease journey is undertaken in Salesforce and will populate on opportunity from the tenancy when SVOT changes are in place. | Currently Data migration has not populated PMS reference on the Opportunity (just the Tenancy). JIRA ticket raised for data Migration: CJR -520 We may need to bulk import the PMS reference on to any existing legacy opportunities to align all data and keep it consistent. | AXIS, Proactis
Contract/Tenancy
Tenancy name (parent record) | Opportunity | Name | Opportunity name in Salesforce (entered manually by user) is passed to Qube using the Lead tenant name only. The Opportunity name in Salesforce is then updated/overwritten with the revised name using the following format: GREP User Title] + OccupantName + <EntityListing><UnitReference><entry><Description> when the data passes back form Qube to SF via GREP. Users in Qube will manually amend the tenancy name where there has been a Change of Sharer. This update will again pass back to salesforce and be updated on the Opportunity. With SVOT changes, the name on the opportunity will be updated to reflect changes made in Qube. | Raise as a backlog item for future consideration. Tenancy name from SF to Qube should include all tenant name and this would avoid the need for users to manually amend it in Qube and pass it back to Salesforce | None
Unit Tenure Type | Opportunity | Agreement_Type__c | Converted using GREP Mapping Qube Tenure Type> SF Agreement Type. Currently the mapping is not 1:1 and some new Agreement Types are required in Salesforce. For some tenancies, the absence of Agreement Type in Salesforce means that the incorrect tenure Type is created in Qube and user has to manually amend the tenure Type in Qube (e.g. DMR) | Sprint 3 or BAU change- add additional Agreement Types to salesforce and update GREP mapping to reflect all Agreement types. Change required to pass Qube Tenure Type to Salesforce (new field) on unit so that users can identify the type of tenure without having to create Agreement Types to achieve 1:1 mapping. Change Request Ticket already raised CJR-429 | AXIS, Evolution
Child Occupier type | Contract/Tenancy | RecordTypeId | Send "Residential Tenancy". An issue if Commercial tenancies are created in Qube and passed to Salesforce. This can occur if tenancies are created outside the control of the Commercial team (e.g. Development, Com Lets etc) as these will not go through the Salesforce journey. | Commercial Leases created in Qube should not created a tenancy in Salesforce-just an opportunity. Commercial = Comm Lease, Comm-Let, Comm Lic. JIRA-CJR-505 | AXIS, Evolution, Spike
| OpportunityContactRole | Role
Child tenant status | Contract/Tenancy | Status | If Contract does not already exist send "Draft" otherwise send "Activated" |  | AXIS, Evolution
| Contract/Tenancy | Tenancy_Status__c | The Tenant status (active, inactive) is managed via GREP Tenant Status Table. Tenant status should only pass to Salesforce for tenancies created in Qube when they are initially created in Salesforce. Where a tenancy is created in Salesforce and passed to Qube, changes in tenant status should NOT be fed back to Salesforce as this is updating and overwriting active/inactive statuses for tenants that have ben manually updated on active renewal opportunities. | Update Integration . CJR-419 .
| OpportunityContactRole | Active__c
Child Tenant start date | ContractContactRole | Start_Date__c | Individual tenant start date |  | AXIS, Evolution, Spike
Child Tenant end date | ContractContactRole | End_Date__c | Individual tenant end date |  | AXIS, Evolution, Spike
Child Tenant Date of Death | OpportunityContactRole | Reason_for_Removal__c | Individual tenant date of death |  | None

## Tenant Data
QUBE | Salesforce |  | Rules | Other systems impacted by data field
Child Tenant First Name | Account/Contact | FirstName | All tenant records should be created as contacts in Salesforce as a first step. These pass to Qube from salesforce where the TENANCY is part of the on- line leasing journey. For tenancies that are not part of the on line leasing journey the tenant record is manually created in QUBE and the Salesforce contact id is manually inserted on the Qube CHILD tenant record so that the Qube and Salesforce tenant records can be linked. Any changes made to this master tenant data in Qube is interfaced back to Salesforce. Consider business process change whereby Tenant Master data is updated only in Salesforce and passes to Qube. | AXIS, Evolution, Proactis, Spike
Child tenant Surname | Account/Contact | LastName
Child Tenant Telephone 1 | Account/Contact | Phone
Child tenant Mobile | Account/Contact | MobilePhone
Child Tenant e mail | Account/Contact | PersonEmail
| Account/Contact | Id