## Instructions
Welcome to the Project Kick-off Checklist Template
A few key notes before you start working on this template:
1. The intention for this checklist is to serve as a guide for the tasks that need to be completed when a project kicks off. Each project should have a completed checklist saved in the Project Documents library on SharePoint.
2. You can filter on Project Size to exclude tasks that do not need to be actioned on small engagements. When starting a small engagement, filter for "All Sizes" on the "Project Size" column.
3. Tasks are labelled as "Mandatory" or "Optional". Manadatory tasks are tasks that need to be completed, however, "Optional" tasks have been added but can be excluded if it's not being used or not applicable to your project.
Should you not complete a "Mandatory" task, it is encouraged to add a short reason in the Notes/Comments column for future reference.
4. Some columns have comments with instructions or additional information. These are marked with a purple flag in the corner.
5. The Status column's drop down is controlled by the list on the "Lists" tab. To add/ remove items from the drop down, make the changes on the "Lists" tab.
6. Links to the relevant Template / URL have been included but are very "general". You can update these links to the project-specific links as you go.
7. Checklist fields on PW can be found under Settings - Additional, as shown below.
8. When uploading the checklist to SharePoint, label the document as Project Kick-off Checklist under the Project Document Type meta data field.
Here's a link to the available User Guides:
Application |  | URL | User Guide
Open Box CRM - MS Dynamics 365 |  | Open Box CRM - Dynamics 365 | CRM User Guide
Project Works |  | Project Works | PW Cheat Sheet

## Kick-off Checklist
Project Size | Requirement Level | Status | Task | Application | Template / URL | Division/Area/Role Specific | Additional Information | Notes / Comments | Phase
All Size | Optional | N/A | Confirm licensing & toolkit for MRI |  |  | ES | Access is generally sorted out in this phase |  | Sales (incl. in SOW)
All Size | Mandatory | Done | Confirm the resource allocation for project | Head of Division / Head of Ops - conversation |  |  | This is a conversation with the head of division / head of opps at the moment, but any existing skills matrix may be used |  | Sales
All Size | Mandatory | Done | Upload signed SOW to Legal Records site on SharePoint | SharePoint | Open Box SharePoint - Legal Records |  | Signed SOW required to close the deal as "Won" on CRM. |  | Delivery
All Size | Mandatory | Done | Copy SOW URL from Legal Records to CRM | OB CRM | Open Box CRM - Dynamics 365 |  |  |  | Delivery
All Size | Mandatory | Done | Mark the opportunity as Deal Won in CRM | OB CRM | Open Box CRM - Dynamics 365 |  | Update the probability to 100% in CRM before marking the opportunity as "Deal Won". Pushes opportunity to Project Works as a new project. Extensions are not pushed to PW (contract renewal season) |  | Delivery
All Size | Mandatory | Done | Confirm that all details in PW are correct | Project Works (PW) | Project Works |  | PM, division, billing contact, etc. When saving details, mark the Project Kickoff Checklist Completed field as No until this is completed and updated at the end of the checklist. |  | Delivery
All Size | Mandatory | Done | Validate revenue Forecasts on PW | Project Works (PW) | Project Works |  | Confirm that what we pushed from CRM is accurate |  | Delivery
All Size | Mandatory | Done | Create a Budget Breakdown in PW | Project Works (PW) | Project Works |  | Set "Division" & "Accounting Code (GL)" on budget lines |  | Delivery
All Size | Mandatory | Done | Set Division / Tracking Category in Budget Breakdown on PW | Project Works (PW) | Project Works |  | When creating budget lines on PW, the Division should be set on each budget line as this pulls through to the invoices monthly. |  | Delivery
All Size | Mandatory | Done | Create Timecodes in PW | Project Works (PW) | Project Works |  |  |  | Delivery
All Size | Mandatory | Done | Update Resourcing Forecasts (Excel, PW, etc.) used by the team/division | Team Specific Resource Forecasting |  |  |  |  | Delivery
Large | Optional | N/A | Add Budget Hrs / Expected (hrs) in PW | Project Works (PW) | Project Works |  | Estimated hours can be added on a timecode level. This is helpful when tracking estimates vs. actuals |  | Delivery
All Size | Mandatory | N/A | Update Sales Management App with contracted hours (Contracted) | Sales Manager App | Opem Box Sales Manager (Webview) |  | Mandatory for contracted projects, but N/A on non-contracted projects. Can be added as an app in MS Teams. Tracks contracted information which feeds into Power BI Time-Analysis reports for PMs & overarching report for Polly. If in doubt whether to capture hours in the App, chat to Andrew Pollock (Polly) to confirm. |  | Delivery
All Size | Mandatory | Done | Move project folder from Sales Documents library to Project Documents library | SharePoint | Open Box SharePoint - Home Page |  | If this is a new client, submit a ticket to infra to request a new client site (they have a pre-defined structure in place). Check if there is a folder - for consistency, give it the same name as the project in PW. Check if there is content in the Sales Projects Site - move this over to Client site once created |  | Delivery
All Size | Mandatory | Done | Give the team / resource access to the client site & project folder | SharePoint | Open Box SharePoint - Home Page |  |  |  | Delivery
Large | Optional | Done | Setup group comms (group chat) & welcome the team | Teams / Slack / Other |  |  | Naming convention for group chat names: "Client Name - "Project Name" [External] "Client Name" - "Project Name" |  | Delivery
Large | Optional | N/A | Client-specific Power BI report requests | Power BI | Power BI | Custom / D&A | Reach out to Data & Analytics with client specific Power BI report requests. Not used often, but could be beneficial if visuals are required for reporting. |  | Delivery
Large | Optional | Done | Schedule a client meet & greet to align on expectations & requirements (New Clients) | Outlook / MS Teams |  |  | RACI Template? We need to align how we are going to work together and establish rapport. |  | Delivery
Large | Optional | Done | Have an internal kick-off call | Outlook / MS Teams | Internal Kick-Off Guide Template |  | Align how we are going to work together. Discuss timecodes, roles, time logging, ceremonies, timelines, AKA brief the team on the project details, etc. |  | Delivery
Large | Optional | Done | Have an external kick-off call with client / broader stakeholders | Outlook / MS Teams | External Project Kick-Off Template |  | For any new client this is a must to establish good rapport & for existing clients it's optional. Optional - Introduction to the project & team template |  | Delivery
All Size | Mandatory | Done | Work management tool access & configuration | Devops / Jira / Monday.com / Asana / Service Now / ConnectWise |  | Client Specific | If a tool is in place, we require access for the team. If there's no tool in place, request a new DevOps instance from Infrastructure for internal management |  | Analysis / Delivery Phase (Sprint 0)
All Size | Optional | N/A | Hosting platform |  |  | Custom / Dev | Confirm with client how they want to do this |  | Analysis / Delivery Phase (Sprint 0)
All Size | Optional | N/A | Access to integration points |  |  | Custom / Dev |  |  | Analysis / Delivery Phase (Sprint 0)
All Size | Optional | N/A | Confirm existing Dev & Test MRI environments |  |  | ES | Confirm with client if they have dev & test environments in MRI that we can use |  | Delivery
All Size | Optional | Done | External SharePoint / document sharing site requirements |  |  |  | Confirm with the client if they have an external site where project related documents should be shared |  | Delivery
All Size | Mandatory | Done | Save Project Kick-Off Checklist in the project folder on SharePoint | SharePoint | Open Box SharePoint - Home Page |  |  |  | Delivery
All Size | Mandatory | Done | Update Checklist Complete field on PW | Project Works (PW) | Project Works |  |  |  | Delivery
All Size | Mandatory | Done | Copy Checklist URL from project folder to PW | Project Works (PW) | Project Works |  |  |  | Delivery
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: General Templates & URLs included, but can be updated with project-specific links
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This space can be used to comment on why certain checklist items were not actioned (i.e. a mandatory items not done) or just some additional insight for future reference

## Lists
Status
To Do
In Progress
Done
N/A