## Automation Questionnaire (hidden)
High Level Description | High level description of the process
|  |  |  | Risk | Complexity | Value
|  | Please select an option | Details | 1 | 1 | 1
Frequency | How often is this process performed? | 1. Low - quarterly or annually |  |  |  | 1
Volume | How high is the volume of records, data or iterations to be processed? E.g. ten reports per month, hundreds of invoices per day, thousands of transactions per file | 1. Tens of records |  |  | 1 | 1
Time | How much time does the process take on average each time it's performed? | 1. An hour or less |  | 1 | 1 | 1
Headcount | How many Full Time Equivalent people does this process take to execute in total? | 1. 1-2 FTEs |  |  |  | 1
Seniority | What's the seniority of the typical FTE working on this process? | 1. Junior |  | 1 | 1 | 1
Scope | How broad is the geographical scope of the process? | 1. Country-specific |  | 1 | 1 | 1
Cost of delays | How critical is it that the process is completed accurately and on time? | 1. Low - process currently completed as time allows |  | 1 |  | 1
Input type | What is the typical format of the data or information that forms the input into the process? | 1. Fully digital/structured e.g. PDF, Excel, report |  | 1 | 1
Document Scanning | Will the input need to be read via Optical Character Recognition or AI? | 1. No |  |  | 1
Input quality | What level of validation would need to be performed on the input data prior to use? | 1. Basic - Required fields and formats |  |  | 1
Process Documentation | How well documented is the current process? Are there clear SOPs or does the process knowledge reside in the heads of a small number of individuals? | 1. Well documented/Clear SOPs |  | 1 | 1
Human intervention | How likely is it for the process to include decision points that cannot be mapped and need to be handed off to a human to make a judgement call? E.g. free text that can't be mapped to a code | 1. Unlikely |  | 1 | 1
Number of systems | How many systems or sites are involved in the end-to-end process (not counting tools like Excel). | 1. 1 system |  | 1 | 1
System access | What is the nature of the systems involved and how are they accessed? | 1. SaaS/External |  | 1 | 1
Test Data Availability | What sort of test data will be available? Is there a test environment that mirrors live? Any privacy or data sharing concerns that would impact the ability to use live data? | 1. Test environment and/or live data |  | 1 | 1
System Change Landscape | How frequently are the applications involved in the process undergoing change? | 1. System is essentially stable |  | 1
Stakeholder Availability | How available are service leads, process owners and SMEs likely to be? Consider other commitments like ongoing high priority projects in their service line. | 1. Time has been committed |  | 1
Client Impact | What is the likely positive impact this automation will have on client satisfaction, retention or new client acquisition? | 1. Low |  |  |  | 1
Staff Retention | What is the likely positive impact this automation will have on staff satisfaction or staff retention? | 1. Low |  |  |  | 1
Risk Reduction | What is the likely positive impact this automation will have on reducing operational risk, fraud loss, regulatory risk or penalties and fees? | 1. Low |  |  |  | 1
Other Considerations | Any other considerations that would affect scoring
|  |  | Score | 12 | 12 | 10
|  |  | Minimum (Excl Other) | 12 | 12 | 10
|  |  | Max (Excl Other) | 36 | 36 | 30
|  |  | Bucket size | 5 | 5 | 4

## HLQ (hidden)
| High Level Quote |  |  |  | Currency | USD
| Complexity: |  | 1 |  | Risk: | 1
| Phase |  | Recommended Duration (w) | Quoted Duration (w) | Cost From | Cost To
| Analysis |  | 2 | 2 | 5200 | 6200
| Build |  | 2 | 2 | 13400 | 16100
| UAT |  | 2 | 2 | 7200 | 8600
| Support |  | 0 | 0 | 0 | 0
| Total |  |  |  | 25800 | 30900
High Level Scope
Item |  | Name |  |  | Description
1
2
3
4
5
6
7
Assumptions
| Item |  | Name |  | Description
1 |  | Frequency & Volume
2 |  | Scope
3 |  | Pre-requisites
4 |  | Dependencies
5 |  | Risks
6 |  | Exclusions

## ROI (hidden)
Cost Benefit Analysis |  | Currency | USD |  | Benefit Calculations
Year 1 Benefit |  | Year 1 Costs |  |  | Process Hours Recovered
Bottom Line Savings | 25000 | Total Capital Cost |  | 30900 | Current Process Effort (h) | 8 | (average hours to run the process each time)
Reinvested Capacity | 27000 | Year 1 Operating Cost |  | 14400 | Volume p.m. | 20 | (average times per month the process is run)
Increased Revenue | 0 | Other Annual Costs |  | 0 | Automation Coverage | 70% | (percentage of the process that can be automated)
Total Annual Benefit | 52000 | Total Year 1 Cost |  | 45300 | Hours Recovered p.m. | 112 | (total hours recovered by automation per month)
[5 empty] | Hours Recovered p.a. | 1344 | (total hours recovered by automation per annum)
Years of Operation | 0 |  |  |  | FTEs Recovered p.a. | 1.1062 | (=hours recovered / effective hours p.a.)
Ongoing Benefit |  | Ongoing Costs |  |  | Current FTE Costs
Ongoing Annual Benefit | 47000 | Ongoing Annual Cost |  | 14400 | Annual Salary | 30000 | (average salary of FTE currently performing process)
Total Benefit | 52000 | Total Cost of Ownership |  | 45300 | Overhead multiplier | 1.5 | (estimate of overheads - benefits, infrastructure, etc.)
[5 empty] | Annual Cost to Company | 45000
Return on Investment |  |  |  |  | Effective working days p.a. | 216 | (accounting for leave, illness, holidays, etc.)
ROI vs Capital Investment | 21100 | 68.28% |  |  | Working hours per day | 7.5
Capital Payback Month | 7.1308 |  |  |  | Efficiency multiplier | 75% | (accounting for admin, meetings, breaks, etc.)
ROI vs Total Cost of Ownership | 6700 | 14.79% |  |  | Effective hours p.a. | 1215 | (total hours of effective processing per FTE)
[5 empty] | Cost per effective hour | 37.037
Bottom Line Savings
[5 empty] | Number of FTEs to be reduced | 0 | (if objective is to reduce headcount)
[5 empty] | FTE cost reduction | 0 | (=FTE reduction x annual cost to company)
[5 empty] | Avoided penalty costs | 0 | (if objective includes improving accuracy/reducing operational risk)
[5 empty] | New Hires avoided | 1 | (if automation avoids cost of hiring additional FTEs)
[5 empty] | Recruitment cost - new hire | 5000
[5 empty] | Annual salary - new hire | 20000 | (may be different from FTE as new hire could be part time)
[5 empty] | Licensing or Software Savings | 0 | (if objective includes removing current technical solution or reducing licenses)
[5 empty] | Any other savings | 0
[5 empty] | Bottom Line Savings - Year 1 | 25000
[5 empty] | Annual Savings thereafter | 20000 | (excluding one-off recruitment cost)
Reinvested Capacity
[5 empty] | Number of FTEs to be reinvested | 0.6 | (if objective is to free up capacity for other value add work)
[5 empty] | Effective hours reinvested p.a. | 729 | (FTEs x annual effective hours)
[5 empty] | Value of reinvested capacity | 27000 | (hours x cost per effective hour)
Increased Revenue
[5 empty] | Estimated annual revenue increase | 0 | (if objective includes increasing fee income, sales, etc.)

## 2 Week Sprint (hidden)
Sprint Duration | 2 | weeks |  |  | Team Composition |  | Hourly Rate | Hourly Rate
FTE Hours per Sprint | 80 | hours |  |  | BA | 1 | 83 | 107
Standups | 2.5 | hours |  |  | PM | 1 | 104 | 135
Planning | 0.5 | hours |  |  | DEV | 1 | 70 | 90
Review | 0 | hours |  |  | QA | 1 | 70 | 90
Retro | 0.5 | hours |  |  | Weighted AVG |  | 81.75 | 105.5
Deployments | 0 | hours |  |  | Blended Rate |  | 76 | 100 |  | Review blended rate with role specific rates when we carry out the next few estimates
Total overheads | 3.5 | hours
Overhead % | 4.375%
Model Project |  | DEV |  | QA |  | BA |  | PM |  | Grand Total |  |  |  | Weekly Cost
Phase | Duration (w) | % Allocation | Total Hours | % Allocation | Total Hours | % Allocation | Total Hours | % Allocation | Total Hours | % Allocation | Total Hours | GBP | USD | GBP | USD
Analysis | 2 | 10% | 8 | 0% | 0 | 50% | 40 | 5% | 4 | 17.81% | 52 | 3952 | 5200 | 1976 | 2600
Build | 2 | 80% | 64 | 40% | 32 | 20% | 16 | 10% | 8 | 41.1% | 120 | 9120 | 12000 | 5092 | 6700
Sprint Overheads |  | 4.375% | 3.5 | 4.375% | 3.5 | 4.375% | 3.5 | 4.375% | 3.5 | 4.795% | 14 | 1064 | 1400 | Included in Build Phase
UAT | 2 | 40% | 32 | 20% | 16 | 20% | 16 | 10% | 8 | 24.66% | 72 | 5472 | 7200 | 2736 | 3600
Support | 1 | 40% | 16 | 20% | 8 | 20% | 8 | 5% | 2 | 11.64% | 34 | 2584 | 3400 | 2584 | 3400
Total | 7 |  | 123.5 |  | 59.5 |  | 83.5 |  | 25.5 | 100% | 292 | 22192 | 29200
Duration (w)
Complexity | Analysis | Build & Test | UAT | Support
1 | 4 | 2 | 2 | 2
2 | 4 | 4 | 2 | 2
3 | 6 | 6 | 2 | 2
4 | 6 | 8 | 2 | 2
5 | 8 | 10 | 2 | 2
Duration (w)
Risk Modifier | Analysis | Build & Test | UAT | Support | Contingency
1 | -2 | 0 | 0 | -2 | 20%
2 | -1 | 0 | 0 | -1 | 25%
3 | 0 | 0 | 0 | 0 | 30%
4 | 1 | 0 | 1 | 1 | 35%
5 | 2 | 0 | 1 | 2 | 40%
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Used for all cost calculations.
Note on E25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Minimum UAT duration is 2 weeks as 1 week has proven impratical for typical projects.

## Lookups (hidden)
Frequency
1. Low - quarterly or annually | Sprint Timeboxing (SCRUM recommended maximum)
2. Medium - monthly or weekly | Standups | 15 | mins per day
3. High - daily | Planning | 1 | hours per 4 weeks
| Review | 0 | hours per 4 weeks
Volume | Retro | 1 | hours per 4 weeks
1. Tens of records
2. Hundreds of records
3. Thousands of records
Time
1. An hour or less
2. Several hours
3. Several days
Scope
1. Country-specific
2. Region-specific (e.g. EMEA/APAC/NA)
3. Global
Headcount
1. 1-2 FTEs
2. 2-5 FTEs
3. 6+ FTEs
Seniority
1. Junior
2. Mid-Level
3. Senior
Cost of delays
1. Low - process currently completed as time allows
2. Medium - business impact increases with delays
3. High - process is time sensitive/business critical
Input type
1. Fully digital/structured e.g. PDF, Excel, report
2. Somewhat structured or digital but needs work
3. Paper-based or in unstructured/unstandardised
Document Scanning
1. No
2. Yes, with only one layout
3. Yes, with multiple layouts
Input quality
1. Basic - Required fields and formats
2. Medium - Simple logic or lookups
3. High - Complex logic or lookups
Process Documentation
1. Well documented/Clear SOPs
2. Documented with some gaps
3. Poorly or un-documented
Human intervention
1. Unlikely
2. Somewhat likely
3. Highly likely
Stakeholder Availability
1. Time has been committed
2. Somewhat available with notice
3. Limited Availability
Number of systems
1. 1 system
2. 2-3 systems
3. 4+ systems
System access
1. SaaS/External
2. VPN/Inside Network
3. Citrix
Test Data Availability
1. Test environment and/or live data
2. Test environment and/or live-like data
3. No test environment/test data only
System Change Landscape
1. System is essentially stable
2. System undergoes regular maintenance
3. Enhancements are in progress
Client Impact/Staff Retention/Risk Reduction
1. Low
2. Medium
3. High

## Custom Automation HLQ (hidden)
Instructions
1. This template should only be used to calculate a high level quote (HLQ) for an automation solution that does not utilise Blue Prism / UiPath.
2. Review HLQ variables, notably the Blended Project Rate/Hour.
Project Contingency is applied to all phases.
3. Only white cells should be edited.
> High Level Quote Variables
Billing
Currency |  | USD
Blended Project Rate/Hour |  | 100
Team Assumptions
Projected Work Output
Analysis Hours/BA/Week |  | 32 | 80% allocation to project during analysis phase
Functional Development Hours/Dev/Week |  | 32 | 80% allocation to project during build phase
Team Composition |  | 4
BA |  | 1
Developer |  | 1
QA |  | 1
PM |  | 1
Project Contingency (Range Driver) |  | 25% | Applied to all project phases
1. Analysis |  | Hours | Cost
High Level Quote |  | 40 | 4000
Analysis Tasks
Documentation |  | 40
Analysis Documentation |  | 36
Client Communication |  | 4
2. Development and Testing |  | Hours | Cost
High Level Quote |  | 114 | 11400
Build Tasks
Project Onboarding |  | 8 | Team familiarization (BA Handover Session, Documentation review), Application Access Testing & Troubleshooting, etc.
Framework & Foundation |  | 8
Client Demo (Mid Projet) |  | 8
QA Planning |  | 8 | Test Plan/Cases, Scenario Analysis
Creation of Test Data |  | 8
Functional Development |  | 30
Process 1
Tasks |  | 2
Tasks |  | 2
Tasks |  | 2
Tasks |  | 2
Tasks |  | 2
Tasks |  | 2
Tasks |  | 2
Process 2 |  | 2
Tasks |  | 2
Tasks |  | 2
Tasks |  | 2
Tasks |  | 2
Tasks |  | 2
Tasks |  | 2
Tasks |  | 2
Quality Assurance |  | 16 | 53% Dev/QA ratio
Process 1 Testing |  | 8
Process 2 Testing |  | 8
Build Overheads |  | 28
Calculated Build Duration (Weeks) |  | 1.6
Team Meetings (Hours/Person/Day) | 0.5 | 16
BA Support | 15% | 7
Project Management | 10% | 5
3. User Acceptance Testing |  | Hours | Cost
High Level Quote |  | 72.5 | 7250
UAT Tasks | Variables
Staging |  | 69.5
UAT Duration (weeks) | 2
Environment Configuration |  | 2
Deployments & Smoke Test |  | 2
UAT User Guide |  | 4
UAT User Guide Walkthrough |  | 1
UAT Register |  | 0.5
Issue Investigation & Resolution |  | 40
Client and Internal Management |  | 20
Production |  | 3
Environment Configuration |  | 1
Deployments & Smoke Test |  | 1
User Guide |  | 1
4. Go Live Support |  | Hours | Cost
High Level Quote |  | 30 | 3000
Go Live Support Tasks | Variables
Support Duration (weeks) | 1
Issue Resolution |  | 20
Client Management |  | 10
Total Project Cost |  | Hours | Cost
High Level Quote |  | 256.5 | 25650
Phase Cost and Timelines
Phase |  | Recommended Duration (w) | Quoted Duration (w) | Cost From | Cost To
Analysis |  | 1.4 | 1.4 | 4000 | 5000
Build |  | 1.6 | 1.6 | 11400 | 14250
UAT |  | 2 | 2 | 7250 | 9062.5
Support |  | 1 | 1 | 3000 | 3750
Total |  | 6 | 6 | 25650 | 32062.5
[5 empty] | Lower | 28000 | 25% range driver
[5 empty] | Upper | 36000
[5 empty] | Mid | 32000
[5 empty] | Mid vs. Cost To | -62.5
Note on F114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does not affect cost.

## Delivery Cost Estimate (hidden)
Instructions
1. This template should be used to calculate a final delivery cost for an automation solution.
2. By default, all High Level Quote lines will be populated with the upper bound hours estimate from the HLQ sheet.
Where the Custom Automation HLQ sheet was used, all High Level Quote lines will need to be manually updated.
3. Review Project variables, notably the Blended Project Rate/Hour which should match that used for the HLQ.
4. Only white cells should be edited.
> Project Variables
Billing
Currency |  |  | USD
Blended Project Rate/Hour |  |  | 100
Range Driver |  |  | 25% | Only required when using this template to calculate delivery cost during sales phase (e.g. Statement of Work)
Team Assumptions
Projected Work Output
Functional Development Hours/Dev/Week |  |  | 32 | 80% allocation to project during build phase
Team Composition |  |  | 4
BA |  |  | 1
Developer |  |  | 1
QA |  |  | 1
PM |  |  | 1
1. Analysis |  |  | Hours | Cost | Difference | Util %
High Level Quote |  |  | 62 | 6200
Estimate |  |  | 80 | 8000 | 1800 | 129%
Actuals |  |  |  | 0 | -8000 | 0%
Analysis Tasks
Documentation |  |  | 80
Business Process Definition |  |  | 20
Functional Requirements Definition |  |  | 20
Solution Design Document |  |  | 30
Client Communication |  |  | 10
2. Build |  |  | Hours | Cost | Difference | Util %
High Level Quote |  |  | 161 | 16100
Estimate |  |  | 179 | 17900 | 1800 | 111.2%
Actuals |  |  |  | 0 | -17900 | 0%
Build Tasks
Project Onboarding |  |  | 29
Team Familiarization (Hours/Person) |  | 4 | 16 | BA Handover Session, Documentation review, etc.
DevOps Setup |  |  | 1
Application Access Testing & Troubleshooting |  |  | 4
Client Demonstration (Mid Project) |  |  | 8
Framework & Foundation |  |  | 3
Technical Consulting (Consultant / Infra / Lead Dev) |  |  | 1
Process Setup |  |  | 1
Environment Setup/Configuration |  |  | 1
QA Planning |  |  | 20
Test Plan/Cases |  |  | 8
Creation of test data |  |  | 8
Preparation of production ready data |  |  | 4
Functional Development |  |  | 31
Process 1
Process Design Document |  |  | 1
Object Design Document |  |  | 1
Initiation |  |  | 10
Step 1 |  |  | 1
Step 2 |  |  | 1
Completion |  |  | 1
Alerts |  |  | 1
Process 2 |  |  | 1
Process Design Document |  |  | 1
Object Design Document |  |  | 1
Initiation |  |  | 1
Step 1 |  |  | 1
Step 2 |  |  | 1
Completion |  |  | 1
Alerts |  |  | 1
Process 3
Process Design Document |  |  | 1
Object Design Document |  |  | 1
Initiation |  |  | 1
Step 1 |  |  | 1
Step 2 |  |  | 1
Completion |  |  | 1
Alerts |  |  | 1
Quality Assurance |  |  | 35 | 113% Dev/QA ratio
Process 1 Testing |  |  | 5
Process 2 Testing |  |  | 25
Process 3 Testing |  |  | 5
Build Overheads |  |  | 61
Calculated Build Duration (Weeks) |  |  | 2.2
Number of Sprints | Calculated | 2 | 2 | Override calculated number of sprints if required
Per Sprint Overheads |  |  | 14
Standups (Hours/Person/Day) |  | 0.25 | 10
Planning (Hours/Person) |  | 0.5 | 2
Retro (Hours/Person) |  | 0.5 | 2
General Overheads |  |  | 30 | Affects build cost, not duration
Bug Fixing (% Functional Dev) |  | 10% | 3
Bug Fixing (% QA) |  | 10% | 4
BA Support |  | 15% | 10
Client Reporting (PM Reviews, Other Reporting) |  | 5% | 3
General Team Management |  | 10% | 7
Code Reviews, Mentorship & Developer Leadership (% Functional Dev) |  | 10% | 3
Contingencies |  |  | 3 | Affects build cost and duration
Unanticipated Complexity |  | 5% | 3
3. UAT |  |  | Hours | Cost | Difference | Util %
High Level Quote |  |  | 86 | 8600
Estimate |  |  | 93.5 | 9350 | 750 | 108.7%
Actuals |  |  |  | 0 | -9350 | 0%
UAT Tasks |  | Variables
Staging |  |  | 25.5
Environment Configuration |  |  | 16 | Including Application Access Testing & Troubleshooting
Deployments & Smoke Test (multiple deployments) |  |  | 4
UAT User Guide |  |  | 4
User Guide walkthrough |  |  | 1
UAT Register |  |  | 0.5
UAT Support |  |  | 60
UAT Duration (weeks) |  | 2
Issue Investigation & Resolution |  |  | 40
Client and Internal Management |  |  | 20
Production |  |  | 8
Environment Configuration |  |  | 1 | Including Application Access Testing & Troubleshooting
Deployments & Smoke Test |  |  | 1
Controller Configuration Document |  |  | 4
Application Access Testing & Troubleshooting |  |  | 1
Production User Guide |  |  | 1
4. Support |  |  | Hours | Cost | Difference | Util %
High Level Quote |  |  | 0 | 0
Estimate |  |  | 24 | 2400 | 2400 | 0%
Actuals |  |  |  | 0 | -2400 | 0%
Go Live Support Tasks |  | Variables
Support Duration (weeks) |  | 1
Issue Investigation & Resolution |  |  | 20
Client Management |  |  | 4
Total Project Cost |  |  | Hours | Cost | Difference | Util %
High Level Quote |  |  | 309 | 30900
Estimate |  |  | 376.5 | 37650 | 6750 | 121.8%
Actuals |  |  | 0 | 0 | -37650 | 0%
Phase Cost and Timelines
Phase |  |  | Calculated Duration (w) | SDD Duration (w) | Calculated Cost | SDD Cost
Analysis |  |  | - | - | 8000 | 8000
Build |  |  | 4 | 4 | 17900 | 17900
UAT |  |  | 2 | 2 | 9350 | 9350
Support |  |  | 1 | 1 | 2400 | 2400
Total |  |  | 7 | 7 | 37650 | 37650
[6 empty] | Lower | 33000 | 25% range driver
[6 empty] | Upper | 42250
[6 empty] | Mid | 37625
[6 empty] | Mid vs. SDD cost | -25
Note on F164: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Solution Design Document

## Effort Estimate
Phase | Task |  | Hours | % | Notes | Rate | 120
Pre Refresh |  |  | 8 |  | 1 week | Contingency | 10%
| Planning with Grainger across all connected systems | 4 |  |  |  | Range Driver | 30%
| Identify all Salesforce integrations/applications that require post refresh action | 4
| Task 3 | [8 empty] | Dev Hours | Lower Bound | Upper Bound
[7 empty] | Lower bound | Upper Bound | Email Alerts - Logic Apps | 8 | 0 | 0
Refresh |  |  | 2 |  | 3 weeks | Hours | 29.7 | 38.61 | Default Tags - Custom Web | 12 | 0 | 0
| Refresh SIT and UAT sandboxes (templates, monitoring progress, activation) | 2 | 1 |  |  | Cost | 3564 | 4633.2 | Wachlist - Custom Web | 4 | 0 | 0
| Task 2 | [8 empty] | 24 | 0 | 0
Task 3
Task 4
Project Admin Phase |  |  | 2
| Team familiarization | 0
| Project Management | 2
| Playbook document creation | 4
Post Refresh |  |  | 14
| Obfuscation of customer emails (and other PII data if required) - SIT & UAT | 2
| Update of endpoints for HomeLet, RightMove, Grainger Website API - SIT & UAT | 2
| Smoke testing - SIT & UAT | 6
| Assitance with Grainger integration setup (Conga, AdobeSign, GREP, Letting portal etc.) | 4
27
0
Assupmtions
Exclusions
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove if Analysis estimate
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For example: - There will only be 1 environment - Produciton. This may impact support and live use. - This will be a supervised solution (ie user will need to be logged in) - Project will be billed T&M @ a rate of xxx - Client will add a user with the appropriate licenses in Azure AD - (Power Automate RPA) - Licensing is $40 p/m per environment (Power Automate with RPA) - Production support xxx - A new account will be set up for the Automation to access xxxx
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For example: - There will only be 1 environment - Produciton. This may impact support and live use. - This will be a supervised solution (ie user will need to be logged in) - Project will be billed T&M @ a rate of xxx - Client will add a user with the appropriate licenses in Azure AD - (Power Automate RPA) - Licensing is $40 p/m per environment (Power Automate with RPA) - Production support xxx - A new account will be set up for the Automation to access xxxx

## Project PTA Tasks (hidden)
Phase | Section | Task
Delivery | Definition | BPD
FRD
SDD
| Pre-Build | Onboarding (BA & Dev handovers etc)
Framework & Foundation
QA Planning
| Build | BA Assistance
Deployments
Development
Code Reviews
Documentation
Testing
UAT Feedback
| Go Live Support / Hypercare | Investigation
Issue Resolution
Program Management | Client Reporting | Weekly PM Review
Other Reporting
| Team Management | Standup
Spring Planning
Sprint Retro
Backlog Grooming
General Project Management