## System Schedule
System Environment Refresh: UAT
[18 empty] | UAT | [6 empty] | SIT
[8 empty] | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-24 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-08
Order | System | Supplier/ Third Party | Contact | Grainger | Cost (£) | Time required | Date confirmed | [5 empty] | Week 1 |  |  |  |  | Week 2 | [5 empty] | Week 3 |  |  |  |  | Week 4 | [5 empty] | Notes
1 | Salesforce | Openbox | Sam Duncan | Jaic George | 6240 | 44-52 hours | 2024-06-17 | Analysis |  |  |  |  | X | X | X | X | X | ü | ü | ü |  |  | UAT End to end testing | [5 empty] | SIT End to end testing | X | X | X | X
2 | GREP | Codification |  | Jaic George | n/a |  |  | X | X | X | X | X | X | X | X | X | X | X | ? | X | X | X |  | X |  | X | X | X |  | X | X | X | X |  | Draw down from monthly support agreement
2 | Qube | N/a | N/a | Kyle Duggan | n/a | 2-3 hours | 2024-06-18 | X | X | X | X | X | X | X | X | X | X | X | ü | X | X | X |  | X |  | X | X | X |  | X | X | X | X
2 | Proactis | Codification |  | Jaic George | n/a |  | 2024-06-18 | X | X | X | X | X | X | X | X | X | X | X | ? | X | X | X |  | X |  | X | X | X |  | X | X | X | X
3 | GraingerApp | Spike | Dan Clapson | Jaic George | n/a | 1-2 hours | 2024-06-14 | X | X | X | X | X | X | X | X | X |  | X | X | X | X | X |  |  |  | X | X | X |  | X | X | X | X
3 | Axis | Axis |  | Jaic George |  | 1-2 hours | 2024-06-18 | X | X | X | X | X | X | X | X | X | X | X | X | X |  | X |  | X |  | X | X | X |  | X | X | X | X
4 | Evolution | MRI Evolution | Averil Milton | Janine Bainbridge | RPS | 2 days | 24/06 & 25/06 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  | X | X | X |  | X | X | X | X |  | Attached to RPS Agreement
6240
Analysis/ identify requirements
Alignment of Environment
Notes:
All refresh and integrations of environments need to be checked they align to other systems.
Can we ensure that what is refreshed in Salesforce is passed to Proactis (TB).

## Detailed Cutover Timeline (hidden)
Detailed Cutover Timeline:
w/c 10th June
Full week | Salesforce | OpenBox: Anaysis, review of current status and requirements required (SIT&UAT) | UAT Environment not available
CHANGE FREEZE IN PLACE
w/c 17th June
17th June | Salesforce | OpenBox: Implementation and alignment (SIT & UAT) | UAT Environment not available