## 2025 Effort Estimate
Phase | Task |  | Hours | % | Notes | Rate | 126
Pre-Refresh Analysis |  |  | 13 |  | 1 week | Contingency | 10%
| Planning with Grainger across all connected systems | 2 |  |  |  | Range Driver | 30%
| Identify all Salesforce integrations/applications that require post refresh action & document refresh steps | 4
| Update current Playbook - SIT & UAT | 4 | [9 empty] | Dev Hours | Lower Bound | Upper Bound
| Backup of SIT and UAT configuraiton in version control | 1 |  |  |  |  | Lower bound | Upper Bound |  |  | Email Alerts - Logic Apps | 8 | 0 | 0
| Meetings and alignment | 2 |  |  |  | Hours | 60.5 | 78.65 |  |  | Default Tags - Custom Web | 12 | 0 | 0
Refresh |  |  | 4 |  | 3 weeks? | Cost | 7623 | 9909.9 |  |  | Wachlist - Custom Web | 4 | 0 | 0
| Refresh UAT sandboxes (templates, monitoring progress, activation) | 2 | [9 empty] | 24 | 0 | 0
| Refresh SIT sandboxes (templates, monitoring progress, activation) | 2 |  |  |  | Internal Version
[6 empty] | Phase | Hours Lower Bound | Hours Upper Bound | Lower Bound | Upper Bound
Project Admin Phase |  |  | 8 |  |  | Pre-Refresh Analysis | 14.3 | 18.59 | 1801.8 | 2342.34
| Team familiarization | 0 |  |  |  | Refresh | 4.4 | 5.72 | 554.4 | 720.72
| Project Management | 2 |  |  |  | Project Admin Phase | 8.8 | 11.44 | 1108.8 | 1441.44
| Client Meetings and alignment | 6 |  |  | over 3 weeks | Post Refresh Updates | 11 | 14.3 | 1386 | 1801.8
[6 empty] | End-to-end Testing | 22 | 28.6 | 2772 | 3603.6
Post Refresh Updates |  |  | 10 |  |  | Total | 60.5 | 78.65 | 7623 | 9909.9
| Obfuscation of customer emails (and other PII data if required) - SIT & UAT | 4
| Update of endpoints for HomeLet, RightMove, Grainger Website API - SIT & UAT | 2
| Assitance with Grainger integration setup (Conga, AdobeSign, GREP, Letting portal etc.) - SIT | 4 |  |  |  | Client Version
[6 empty] | Phase | Hours Lower Bound | Hours Upper Bound | Lower Bound | Upper Bound
End-to-end Testing |  |  | 20 |  |  | Pre-Refresh Analysis | 14 | 19 | 1764 | 2394
| End-to-end testing - UAT | 10 |  |  |  | Refresh | 4 | 6 | 504 | 756
| End-to-end testing - SIT | 10 |  |  |  | Project Admin Phase | 9 | 11 | 1134 | 1386
[6 empty] | Post Refresh Updates | 11 | 14 | 1386 | 1764
|  |  | 55 |  |  | End-to-end Testing | 22 | 29 | 2772 | 3654
[6 empty] | Total | 60 | 79 | 7560 | 9954
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove if Analysis estimate

## 2025 Timeline
Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28
Analysis
|  |  |  | SIT Refresh (SIT unavailable) | [6 empty] | SIT Available
[11 empty] | UAT Refresh (UAT unavailable) | [9 empty] | UAT available

## 2024 Actuals
Phase | Task |  | Hours | % | Notes | Rate | 120
Pre-Refresh Analysis |  |  | 25 |  | 1 week | Contingency | 10%
| Planning with Grainger across all connected systems | 4 |  |  |  | Range Driver | 30%
| Identify all Salesforce integrations/applications that require post refresh action & document refresh steps | 8
| Playbook document creation | 8 | [9 empty] | Dev Hours | Lower Bound | Upper Bound
| Backup of SIT and UAT configuraiton in version control | 1 |  |  |  |  | Lower bound | Upper Bound |  |  | Email Alerts - Logic Apps | 8 | 0 | 0
| Meetings and alignment | 4 |  |  |  | Hours | 69.3 | 90.09 |  |  | Default Tags - Custom Web | 12 | 0 | 0
Refresh |  |  | 4 |  | 3 weeks | Cost | 8316 | 10810.8 |  |  | Wachlist - Custom Web | 4 | 0 | 0
| Refresh UAT sandboxes (templates, monitoring progress, activation) | 2 | [9 empty] | 24 | 0 | 0
| Refresh SIT sandboxes (templates, monitoring progress, activation) | 2
[6 empty] | Phase | Hours Lower Bound | Hours Upper Bound | Lower Bound | Upper Bound
[6 empty] | Pre-Refresh Analysis | 25 | 28 | 3000 | 3360
[6 empty] | Refresh | 4 | 5 | 480 | 600
[6 empty] | Project Admin Phase | 8 | 9 | 960 | 1080
Project Admin Phase |  |  | 8 |  |  | Post Refresh Updates | 10 | 11 | 1200 | 1320
| Team familiarization | 0 |  |  |  | End-to-end Testing | 16 | 18 | 1920 | 2160
| Project Management | 2 |  |  |  | Total | 63 | 71 | 7560 | 8520
| Client Meetings and alignment | 6
Post Refresh Updates |  |  | 10
| Obfuscation of customer emails (and other PII data if required) - SIT & UAT | 4
| Update of endpoints for HomeLet, RightMove, Grainger Website API - SIT & UAT | 2
| Assitance with Grainger integration setup (Conga, AdobeSign, GREP, Letting portal etc.) | 4
End-to-end Testing |  |  | 16
| End-to-end testing - UAT | 10
| End-to-end testing - SIT | 6
63
0
Assupmtions
Note on H3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove if Analysis estimate
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For example: - There will only be 1 environment - Produciton. This may impact support and live use. - This will be a supervised solution (ie user will need to be logged in) - Project will be billed T&M @ a rate of xxx - Client will add a user with the appropriate licenses in Azure AD - (Power Automate RPA) - Licensing is $40 p/m per environment (Power Automate with RPA) - Production support xxx - A new account will be set up for the Automation to access xxxx