| Project |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Change of Sharer Process – Granger plc |  |  |  |  |  |  |
| Request Date | 28th March 2024 |  | ROM Date |  | 24th April 2024 |  |
| Background & Context |  |  |  |  |  |  |
| Occupancy of a unit may change during the lease term, or on renewal. This Change of Sharer process is currently manged by the Renewals Team entirely offline and often requires tenants to complete multiple forms with duplicate information. Grainger have identified that moving this process into Salesforce would make the time-consuming process more efficient as well as improve customer experience. |  |  |  |  |  |  |
| Summary of Proposed Changes |  |  |  |  |  |  |
| - Create a new opportunity workflow within Salesforce for the change of sharer process. The workflow will be a subset of the new lease opportunity process, for example reference checks are only required for any new tenant(s) and no holding deposit is paid. - Enable the Renewals Team to process a change of sharer mid-lease term, creating a change of sharer opportunity that is a child of the original lease opportunity. - Generate and email a single form to the lead tenant to complete details of all vacating & new tenants. - Generate a new tenancy agreement for new and remaining tenants to sign digitally. - Automatically generate a new tenancy in Salesforce with the updated contact roles. - Incorporate the change of sharer process into the renewal opportunity workflow, enabling the Renewals Team to process a change of sharer on lease renewal (where required). |  |  |  |  |  |  |
| Assumptions |  |  |  |  |  |  |
| - Any new or enhanced integration between Salesforce and other applications that may be required (e.g., generating a new lease and transferring the deposit in Qube) will be developed by Grainger. - The existing reference check functionality can be used without any modifications. |  |  |  |  |  |  |
| Exclusions & Limitations |  |  |  |  |  |  |
| - There will be a single workflow for mid-lease changes & a single process for changes on renewal. |  |  |  |  |  |  |
| Project Phase |  | Estimated Effort |  | Estimated Cost (excl. VAT) |  | Estimated Duration |
| Analysis & Solution Architecture billed on a Time & Materials (T&M) basis @ £150/hour. |  | 80–120 hours |  | £12 000 - £18 000 |  | 4 – 5 weeks |
| Delivery billed @ £18 900 per sprint. |  | 2-3 sprints |  | £37 800 - £56 700 |  | 6 - 9 weeks |
| UAT billed on a T&M basis @ £150/hour. |  | 40 hours |  | £3 150 |  | 2 weeks |
| Support billed on a T&M basis @ £150/hour. |  | 20 hours |  | £1 600 |  | 2 weeks |
| Total |  |  |  | £54 550 - £79 450 |  | 14-18 weeks |
| Project |  |  |  |  |  |  |
| Customer Renewals Journey – Granger plc |  |  |  |  |  |  |
| Request Date | 28th March 2024 |  | ROM Date |  | 19th April 2024 |  |
| Background & Context |  |  |  |  |  |  |
| The existing customer journey to renew a lease is often a poor experience. The intended functionality only works 30% time; many renewing customers receive new tenancy agreements via emails with new lease wording. Additionally, the current process does not facilitate interaction, for example when negotiating renewal terms. Grainger have identified that enhancing this process will improve customer experience. |  |  |  |  |  |  |
| Summary of Proposed Changes |  |  |  |  |  |  |
| - Enable the Renewals team to email offer details to the lead tenant for a renewal opportunity. - A link in the email will enable the tenant to access a secure portal and see the details of the offer to renew. - The tenant will be able to: - Indicate their intention to not renew, thereby notifying the Property Manager and Renewals Team. - Reject the offer and make a counteroffer, requesting different terms. The renewals opportunity would be automatically updated with the counteroffer and the Renewals Team will be alerted. - Accept the offer, signing the new tenancy agreement online. - Send reminders and chaser emails. |  |  |  |  |  |  |
| Assumptions |  |  |  |  |  |  |
| - xxx |  |  |  |  |  |  |
| Exclusions & Limitations |  |  |  |  |  |  |
| - New or enhanced integration between Salesforce and other applications, including / excluding the Grainger Tenant Portal. - Modifications to the renewal payment processing and collections functionality already in Salesforce. |  |  |  |  |  |  |
| Project Phase |  | Estimated Effort |  | Estimated Cost (excl. VAT) |  | Estimated Duration |
| Analysis & Solution Architecture billed on a Time & Materials (T&M) basis @ £150/hour. |  | 80–120 hours |  | £12 000 - £18 000 |  | 4 – 5 weeks |
| Delivery billed @ £18 900 per sprint. |  | 2-3 sprints |  | £37 800 - £56 700 |  | 6 - 9 weeks |
| UAT billed on a T&M basis @ £150/hour. |  | 40 hours |  | £3 150 |  | 2 weeks |
| Support billed on a T&M basis @ £150/hour. |  | 20 hours |  | £1 600 |  | 2 weeks |
| Total |  |  |  | £54 550 - £79 450 |  | 14-18 weeks |

Terms and Conditions:

- This is not a quote but an indication of cost. The estimates and proposed changes in this document were made prior to any detailed analysis and are subject to change on further analysis. The final estimated cost and timeline will be delivered on completion of the project’s analysis phase / sprint zero. Regular updates regarding any significant changes in cost or scope will be delivered to Grainger plc as and when they occur.

- Cost estimates are based on billing rates as at the ROM date, which are subject to change.

| Project |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Salesforce Renewals Journey – Granger plc |  |  |  |  |  |  |
| Request Date | 28th March 2024 |  | ROM Date |  | 1st April 2024 |  |
| Background & Context |  |  |  |  |  |  |
| Summary of Proposed Changes |  |  |  |  |  |  |
| Assumptions |  |  |  |  |  |  |
| Exclusions & Limitations |  |  |  |  |  |  |
| References |  |  |  |  |  |  |
| - New Project Discussion/High Level Scoping Teams meeting on 28th March 2024. |  |  |  |  |  |  |
| Project Phase |  | Estimated Effort |  | Estimated Cost (excl. VAT) |  | Estimated Duration |
| Analysis & Solution Architecture billed on a Time & Materials (T&M) basis @ £150/hour. |  | 80–120 hours |  | £12 000 - £18 000 |  | 4 – 5 weeks |
| Delivery billed @ £18 900 per sprint. |  | 2-3 sprints |  | £37 800 - £56 700 |  | 6 - 9 weeks |
| UAT billed on a T&M basis @ £150/hour. |  | 40 hours |  | £3 150 |  | 2 weeks |
| Support billed on a T&M basis @ £150/hour. |  | 20 hours |  | £1 600 |  | 2 weeks |
| Total |  |  |  | £54 550 - £79 450 |  | 14-18 weeks |