## SOW
Cost Per Sprint | 24720 | [6 empty] | Team Composition | Allocation
Hour Rate | 103 | [6 empty] | Dev Senior | 100%
|  | Phase | Duration (weeks) | Lower | Upper | Lower Bound | Upper Bound | Dev Junior | 50%
|  | Discovery (60-80 hours) | 3 weeks | 60 | 80 | 6180 | 8240 | QA | 25%
|  | Sprint 0 (20 hours) | 2 weeks | 20 | 20 | 2060 | 2060 | BA | 12.5%
|  | Build: 1 - 3 Sprints | 3-9 weeks | 1 | 3 | 24720 | 74160 | PM | 13%
|  | UAT | 2 weeks | 40 | 40 | 4120 | 4120 | Total FTEs | 2.005
|  | Production Deployment & Post Go-Live Support | 2 weeks | 20 | 20 | 2060 | 3600 | SOW FTE | 2
|  | User guide updates | Done in parallel with sprints |  |  | 1750 | 1750
|  | Total | 12 - 18 weeks |  |  | 40890 | 93930

## Sheet1
Story Points
FormAssembly or REST API | If FormAssembly, we can do the work, if REST API then Code/Codification/3rd party will need to do the work
Create EOT for unit (and EoT for pakring if applicable) | Specify template, all tasks and dates will then be created via triggers/flows
Effort | 4 | 5 | 8 | 8
Depends on whether we have to FormAssembly or not.
Adjusting the EOT templates (data only, no config)
Effort | 2 | 3 | 5 | 5
Either Apex triggers to validate based on permission sets, or custom permissions to drive button visibility |  |  | 8 | 8
Would need to adjust EoT template so that permissions can be specified on the template
|  |  | 8 | 8
1. FormAssembly with various other Salesforce emails
Chaser emails etc.
New field
GREP Integration
Adjust EoT template to remove task |  |  | 5 | 8
Customise close task flow to include email comms sent to tennat
Maybe new custom fields
"No Works" will require some adjustment to trigger that calculates overall timeline
|  |  | 8 | 13
Custom object to hold metadata on files
Need to decide whether files are stored in Salesforce or S3/shared folder (apex heap size implications for files sent to tenants via emails from Salesforce)
Works should be tracked as a Work Order |  |  | 8 | 13
EOT can be completed before the void works are done, void works shouldn't be part of EoT tasks
Who updates the work order with ETA etc.?
GREP work |  |  | 0 | 0
Who marks the tasks as done?
Should be work order
Dependent on how #7 is handled |  |  | 5 | 8
Should be done with a Case |  |  | 8 | 13