## High Level Proposal
Rates
Cost per sprint | 21600
Project Rate | 120
Consultant Rate | 155
|  | Phase | Duration (weeks) | Min Hours | Max hours | Lower Bound Cost Rates | Upper Bound Rates
|  | Sprint 0 | 6 weeks (100 - 130 hours) | 100 | 130 | 15500 | 20150
|  | Release 1: 1 - 2 Sprints | 3 - 6 weeks | 1 | 2 | 21600 | 43200
|  | UAT & Production Deployment (20-30 hours) | 1 week | 20 | 40 | 2400 | 4800
|  | Post Go-Live Support | 2 weeks | 20 | 20 | 2400 | 2400
|  | User guide creation/training | Parallel with project (40 hours) | 40 | 40 | 4800 | 4800
|  | Total Cost for Release 1 |  | 181 | 232 | 46700 | 75350
Team Composition | Allocation
Team cost / sprint
Dev Senior | 100%
Dev Junior | 0%
QA | 25%
BA | 12.5%
PM | 13%
Total FTEs | 1.505
Team FTE | 1.5

## Detail
|  |  |  | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | Sprint 23 | Sprint 24 | Sprint 25 | Sprint 26 | Sprint 27 | Sprint 28 | Sprint 29 | Sprint 30 | Sprint 31 | Sprint 32 | Sprint 33
Scheduling
Velocity
| Total Velocity Done |  |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total Backlog Size |  |  | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
For Bars | Optimistic Forecast |  |  | 0 | 25 | 50 | 75 | 100 | 125 | 150 | 175 | 200 | 225 | 250 | 275 | 300 | 325 | 350 | 375 | 400 | 425 | 450 | 475 | 500 | 525 | 550 | 575 | 600 | 625 | 650 | 675 | 700 | 725 | 750 | 775 | 800 | 825
| Likely Forecast |  |  | 0 | 20 | 40 | 60 | 80 | 100 | 120 | 140 | 160 | 180 | 200 | 220 | 240 | 260 | 280 | 300 | 320 | 340 | 360 | 380 | 400 | 420 | 440 | 460 | 480 | 500 | 520 | 540 | 560 | 580 | 600 | 620 | 640 | 660
| Pessimistic Forecast |  |  | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450 | 465 | 480 | 495
For T&M | Costing
| Team Sprint Cost (Actual) |  |  |  | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400
| Cumulative Team Cost (Actual) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Cumulative Team Cost (Forecast) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600
Team Metrics
Optimistic Velocity ( Best Velocity in last 3 sprints) | 25
Likely Velocity (Avg Velocity over last 3 sprints) | 20
Pessimistic Velocity (Worst Velocity in last 3 sprints) | 15
Team Composition | Hourly Rate | Allocation | Cost Per Sprint
Team cost / sprint |  |  | #REF!
Dev Senior |  | 100%
Dev Junior |  | 50%
QA |  | 25%
BA |  | 12.5%
PM |  | 13%
Total FTEs |  | 2.005

## Post Sprint 0 Cost Summary
Cost per sprint | #REF!
Day Rate | 780
Hour Rate | 97.5
FTE Rate | 15600 | Phase | Duration (weeks) | Lower Bound | Upper Bound
Sprint 0
Release 1: 2 - 3 Sprints
UAT
Production Deployment & Post Go-Live Support
|  | User guide creation | Done in parallel with sprints
|  | Total Cost for Foundational Changes and Release 1 | 13 - 16 | 0 | 0