## SOW
Rates as per template
Cost per sprint | 23400
Day Rate | 780
Hour Rate | 97.5
|  | Phase | Duration (weeks) | Min Hours | Max hours | Lower Bound Cost Rates | Upper Bound Rates
|  | Sprint 0 | 3 | 10 | 15 | 975 | 1462.5
|  | Release 1: 1 - 2 Sprints | 3-6 | 1 | 2 | 23400 | 46800
|  | Final UAT | 2 | 40 | 60 | 3900 | 5850
|  | 2 weeks Post Go-Live Support |  | 20 | 40 | 1950 | 3900
Sprint Team FTEs | 2
Est Vel | 22.5
Story Points | 35
Est Sprints | 1.5556
|  | Total Cost for RRB |  | 71 | 117 | 30225 | 58012.5

## Detail
|  |  |  | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | Sprint 23 | Sprint 24 | Sprint 25 | Sprint 26 | Sprint 27 | Sprint 28 | Sprint 29 | Sprint 30 | Sprint 31 | Sprint 32 | Sprint 33
Scheduling
Velocity
| Total Velocity Done |  |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total Backlog Size |  |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
For Bars | Optimistic Forecast |  |  | 0 | 22.5 | 45 | 67.5 | 90 | 112.5 | 135 | 157.5 | 180 | 202.5 | 225 | 247.5 | 270 | 292.5 | 315 | 337.5 | 360 | 382.5 | 405 | 427.5 | 450 | 472.5 | 495 | 517.5 | 540 | 562.5 | 585 | 607.5 | 630 | 652.5 | 675 | 697.5 | 720 | 742.5
| Likely Forecast |  |  | 0 | 22.5 | 45 | 67.5 | 90 | 112.5 | 135 | 157.5 | 180 | 202.5 | 225 | 247.5 | 270 | 292.5 | 315 | 337.5 | 360 | 382.5 | 405 | 427.5 | 450 | 472.5 | 495 | 517.5 | 540 | 562.5 | 585 | 607.5 | 630 | 652.5 | 675 | 697.5 | 720 | 742.5
| Pessimistic Forecast |  |  | 0 | 22.5 | 45 | 67.5 | 90 | 112.5 | 135 | 157.5 | 180 | 202.5 | 225 | 247.5 | 270 | 292.5 | 315 | 337.5 | 360 | 382.5 | 405 | 427.5 | 450 | 472.5 | 495 | 517.5 | 540 | 562.5 | 585 | 607.5 | 630 | 652.5 | 675 | 697.5 | 720 | 742.5
For T&M | Costing
| Team Sprint Cost (Actual) |  |  |  | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400
| Cumulative Team Cost (Actual) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Cumulative Team Cost (Forecast) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600
Team Metrics
Optimistic Velocity ( Best Velocity in last 3 sprints) | 22.5
Likely Velocity (Avg Velocity over last 3 sprints) | 22.5
Pessimistic Velocity (Worst Velocity in last 3 sprints) | 22.5
Team Composition | Hourly Rate | Allocation | Cost Per Sprint
Team cost / sprint
Dev Senior |  | 100%
Dev Junior |  | 50%
QA |  | 25%
BA |  | 12.5%
PM |  | 13%
Total FTEs |  | 2.005

## Post Sprint 0 Cost Summary
Cost per sprint | 0
Day Rate | 780
Hour Rate | 97.5
FTE Rate | 15600 | Phase | Duration (weeks) | Lower Bound | Upper Bound
Sprint 0
Release 1: 2 - 3 Sprints
UAT
Production Deployment & Post Go-Live Support
|  | User guide creation | Done in parallel with sprints
|  | Total Cost for Foundational Changes and Release 1 | 13 - 16 | 0 | 0