## Proposal v1.1 Estimate
Rates (£) |  |  | Points |  | Sprint Team | [5 empty] | Key
Currency | £ |  |  |  | Role | # People | Allocation | FTE | Split | Target | Enter value
Sprint 0 Rate per Hour (T&M) | 163 |  | Unanticipated Scope |  | Dev Senior | 1 | 100% | 1 | 50% |  | Default value across projects
Project Rate per Hour | 102.375 | 105% | Unanticipated Complexity |  | Dev Junior | 1 | 0% | 0 |  |  | Calculated (formula)
Weeks per Sprint | 3 |  | Total Points | 60 | QA | 1 | 40% | 0.4 | 20%
[5 empty] | Jacob | 1 | 10% | 0.1 | 25% |  | People involved in Estimate
UAT & Production Support |  |  | Build - Sprints |  | BA | 1 | 30% | 0.3 |  |  | Sam Duncan
UAT Weeks | 2 |  | Optimistic Sprint # | 3 | Architect | 1 | 10% | 0.1 |  |  | Shaun Barrett
Prod Support Weeks | 2 |  | Pessimistic Sprint # | 4 | PM | 1 | 10% | 0.1 | 5% |  | Nikki Papenfus
Team Size (FTEs) - UAT | 0.5 |  | Team Size (FTEs) | 2 | Team Size |  |  | 2 | 100% | 0% | Jacob
Cost per Week (£) | 2047.5 |  | Cost per Sprint (£) | 24570
Velocity
Notes |  |  |  |  | Range | Points per Dev per 3-week Sprint |  |  | Points per Sprint
1 Release, must have functionality only; target cost 100-140k |  |  |  |  | Optimistic | 1 Senior Dev FTE |  | 20 | 20
[6 empty] | 1 Junior Dev FTE |  | 0
[5 empty] | Pessimistic | % of Optimistic |  | 75% | 15
Internal
Project Phase | Min Effort | Max Effort | Lower Bound (£) | Upper Bound (£) | Sprint 0 |  |  |  | Consultancy (Min)
Consultancy (Hours) | 80 | 100 | 13040 | 16300 | Weeks (Min) |  | 3
Sprint 0 | 80 | 100 | 13040 | 16300 | BA Allocation (Min) |  | 30%
Build (Sprints) | 3 | 4 | 73710 | 98280 | BA Allocation (Max) |  | 45% | Pax: | Backlog (Hrs) |  | 24 | pax
Final UAT (Weeks) 0,5 FTE | 2 | 2 | 4095 | 4095 | Client Meetings (hrs/week) |  | 3 | 4 | Client Meetings (Hrs) |  | 5 | 4
Prod Deployment & Support (Weeks) 0,25 FTE | 2 | 2 | 2047.5 | 2047.5 | Internal Meetings (hrs/week) |  | 1 | 3 | Internal Meetings (Hrs) |  | 4 | 3
User Guide (Hours) | 12.01 | 12.01 | 1957.63 | 1957.63 | Total Hours (Min) |  | 81 |  | Document (Hrs) |  | 24
Total |  |  | 107890.13 | 138980.13 | Total Hours (Max) |  | 99 |  | Total Hours (min) |  | 80
External Quote |  |  |  |  | Timelines | [5 empty] | MOSCOW Requirements - Points
| Duration (Weeks) |  | Lower Bound (£) | Upper Bound (£) | Target Start Date |  |  | 2025-11-01 |  |  | Rent Challenge | 25
Consultancy | 4 | 4 | 13040 | 16300 | Estimated End Date | [5 empty] | ASB | 35
Sprint 0 | 3 | 3 | 13040 | 16300 | Release 1 | Lower Bound |  | Upper Bound |  |  | Pets
Build | 9 | 12 | 73710 | 98280 | Consultancy / Sprint 0 | 2025-12-19 |  | 2025-12-19 |  |  | 10% | 6
Final UAT | 2 | 2 | 4095 | 4095 | Xmas Break (days) | 14 |  | 14 |  |  | Total | 66
Prod Deployment & Support | 2 | 2 | 2047.5 | 2047.5 | Build | 2026-03-06 |  | 2026-03-27 |  |  | Points Available - Min Sprint | 60
User Guide | 0 | 0 | 1957.63 | 1957.63 | UAT/Go Live | 2026-03-20 |  | 2026-04-10 |  |  | Points Available - Max Sprint | 80
Total | 20 | 23 | 107890.13 | 138980.13 | Support | 2026-04-03 |  | 2026-04-24
Xmas | 2 | 2
Months Duration | 5.0769 | 5.7692
Formulas:
FTE = K32+D32*7+[FTE, row above]
FTE = [FTE, row above]+D33*7
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider the extent of discovery already completed, and knowledge of the client's business & Org.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider extent of custom component development, use of 3rd party apps, 3rd party integrations.
Note on B11: Nikki Papenfus: Seems high for support. Should we allow for different FTEs for UAT & support?
Note on I15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 point story = 5 days to dev, QA, fix bugs & deploy
Note on K15: Nikki Papenfus: TO BE DECIDED SVOT project: Average points delivered by 1 Dev FTE in a 3 week sprint = 16.4 points

## Proposal v1.1_Features
Epic | Feature | Scope Notes | Points | User Story A/Cs | #
General Case Management | Tenancy Review Email Cases | Update the existing case type layout to align with new standards. Add KPI indicator? | out of scope
General Case Management | Email Theading | Thread responses to case emails back onto the case. [existing] Notify case owner? | 3 | The (email) communication can be issued via the ‘system’ and replies from complainants will be received back within the system also (two-way communication). All communications to and from the complainant are registered against the ASB case file and/or the customer account (provided they are a Grainger resident) The ‘system’ will integrate with Microsoft Outlook ensuring that any communications received or issued via outlook are automatically logged against the customer and/or unit in the ASB case file | 14, 25
Rent Challenge | Formal Rent Challenge Case | - Page layout for record type - Formula fields - Linked to tenancy review. - Stages / progress bar - Upload files - Email from case. - Validations: Required information captured at certain stages. - Save & calculate reporting metrics. | 13 | The new Challenge Case is linked to Rent Increase process and specifically the Rent Review in progress The case includes relevant data fields to include the capture of rent requested and achieved, dates of appeal, hearing, decision, and the outcome details with details of any decision made. Any word, PDF, Photos or other document types are added to the case folder. Emails sent to third parties are sent from the case task, and replies are saved back onto the case Evidence and data fields to record dates/times of the formal challenge Appeal Date, FFT Hearing Date, Date of Decision, Rent Achieved, Date for new rent to be charged Rent Data to include Rent Applied, Rent Achieved, Rent Loss, Time taken by FTT to process, decision made won/lost, and lessons learned A progression bar on each task to show each stage of the appeal process | 1, 2, 3, 6
Rent Challenge | Notify Stakeholders of Formal Rent Challenge | - Notify stakeholders on case creation (TBD task or email) - Notify stakeholders once decision made (TBD task or email - 2x templates challenge won/lost) | scope down to standard | When a Formal Rent Challenge case is created, the system alerts CC, TMT and any other stakeholders to ensure rent increases are placed on hold. When a Formal Rent Challenge decision has been made, the system alerts CC, TMT and any other stakeholders to ensure rent increases are taken off hold and the Rent Review Process is fully completed in line with the new rent amount and chargeable date. | 5, 8
Rent Challenge | Integrate Rent Challenge Case & Tenancy Review Opportunity | - Create from tenancy review opp & prepopulate information from opp. - Add related list of cases to TR opportunity record layout. - New validations on TR opp if there is a linked case. - EXCLUDE: Auto update the Tenancy Review opportunity when a decision is made? E.g. update start date of new contract, update rent amount; create a new primary offer - May need to save additional data for reporting purposes | 5
Rent Challenge | Generate Reply Form & Written Submisstion | - Generate 2 x forms / documents. - Capture form content via 2 x screenflow? - 2x email templates available for users to select? | out of scope | Standard templates that can be completed by TMT to return the (Reply Form) property information to FFT once an appeal has been received Standard templates that can be completed by TMT to return the (written representation) the evidence to support how the rent increase was calculated using comparable evidence, local geographical benefits and the service/amenities provided by Grainger All emails/communication should be sent/received and saved against the case record. | 6
Rent Challenge | KPI Indicator | - Colour-coded KPI tracking status - Will likey be multiple KPIs depending on the case stage. | 3 | Where a KPI target is due, or has been missed, the task bar should show a traffic light status to make it easily visible for users where tasks are due/overdue | 6
Rent Challenge | Reporting & Dashboard | 6 Reports 1x Operational Dashboard with filters | 5 | Dashboards and reports to show metrics for the following: 1.% of rents challenged 2.% increase in rent of rents that are challenged 3.Number of challenges won and lost (and the % level of rent increase of these) Percentage of appeals won/lost - split by region and building to show comparisons against each FTT office 4.Time taken for FTT hearing decision (from date on section 13 notice to FTT decision date) / Average times to process appeals through the FTT (spike for cases outside if these timescales) 5.Time taken for implementation of new rent (if different from above due to hardship) 6.Rent lost due to time delay on FTT decision / Average Rent loss for FTT time taken to process - split by region and building to show comparisons against each FTT office | 9
ASB | Create New Incident Case | - Screen flow to create new incident case: Select if ASB or not. - If ASB: step by step question and answer set to evaluate case severity - Follow up questions depend on the answers selected. - Display suggested severity level > user can manually update. - Create case with the applicable record type. | out of scope | • Users are prompted to answer ‘Was the incident a result of ASB’ when creating a task and are provided with Yes or No options: • If Yes – the system routes the incident into the ASB process workflow • If No – the system will generate a Near Miss or Injury workflow to record incidents without the requirements below. • The system presents a clear, step by step question and answer set to evaluate case severity • When the user answers questions and certain answers are selected, the system dynamically adjusters or filters subsequent questions to maintain relevance • When all questions are answered, the system suggests a severity level • If the user disagrees they can manually adjust the severity level before submitting the ASB case | 1, 3
ASB | Incident Cases [Near Miss & Injury] | - Page layout for record type - Two different Incident Types with fields conditionally displayed depending on type? - Upload files - Email from case. - Validations: Required information captured at certain stages. - Save & calculate reporting metrics. | out of scope | As a User I want to classify incidents by Near Miss or Accident during reporting, so that I can accurately assess severity and determine the most appropriate response actions The system displays a set of standard date-related questions (e.g., "When did the incident occur?") Dates are required fields and validated for format (e.g., DD/MM/YYYY) - Near Miss [Link to ‘Incident – Near Miss’] Person at Risk [Drop Down] Location of Incident [Drop Down] Cause of Near Miss [Drop Down] Description [Free Text Box] “Describe what happened and how. If witnesses, please provide details.” - Accident [Link to ‘Incident – Injury’] What caused the Injury? [Drop Down] Person involved [Drop Down] Name of Person Injured [Free Text Box] Location of Incident [Drop Down] Type of Treatment Required [Drop Down] Description [Free Text Box] “Describe what happened and how. If witnesses, please provide details.” The system has comment fields to allow users to record details and updates for each ASB task Users can edit or add new entries with time and date stamps and user stamp The system allows for documents to be uploaded against the task including as minimum the most common file types (pdf, doc, docx, word etc) The system allows for the video and audio files to be saved against the task including as minimum the most common file types (mp4, avi, mp3 etc) The system allows for images to be saved against the task including, as minimum the most common file types (jpg, png, bmp, gif etc) Uploaded documents, videos, images are listed in the task in date logged order and are viewable/downloadable File size and type restrictions are clearly stated | 3, 4, 5, 7
ASB | ASB Possession Cases | - Page layout for record type - Formula fields - Stages / progress bar - Instructional text is for each stage explaining what information should be entered. - Conditional display of fields based on stage? - Upload files (including video, audio, images) - Evidence files cannot be deleted - TBD if possible? - Email from case. - Add tasks - Validations: Required information captured at certain stages. - Save & calculate reporting metrics. - Strict access control on who can see what. e.g. by case record type. - Flag sensitive cases to be hidden from general users. | 13 | • Instructional text is clearly displayed at each step of the task creation for the user to follow steps/actions • Text explains what type of information should be entered The system has comment fields to allow users to record details and updates for each ASB task Users can edit or add new entries with time and date stamps and user stamp The system allows for documents to be uploaded against the task including as minimum the most common file types (pdf, doc, docx, word etc) The system allows for the video and audio files to be saved against the task including as minimum the most common file types (mp4, avi, mp3 etc) The system allows for images to be saved against the task including, as minimum the most common file types (jpg, png, bmp, gif etc) Uploaded documents, videos, images are listed in the task in date logged order and are viewable/downloadable File size and type restrictions are clearly stated The ASB incident types for selection should include: Personal ASB (harassment or targeting specific individuals/groups); Nuisance ASB (causing trouble to community, loud music or public disturbances) ; Vehicle-related ASB (abandoned cars/reckless driving); Trespassing (unauthorised entry onto private property); Animal-related issues (aggressive or uncontrolled pets); Drug paraphernalia (illegal substances, presence of needles or drug related litter) ; Aggressive or violent behaviour – physical threats or actions Category selection: Users can select one or more ASB incident types from the predefined list when submitting a report Clear definitions: Each category includes a short description or example to help users make an informed choice Validation: At least one category must be selected to submit the incident report Each incident must be classified using one of the following mandatory severity levels: Fundamental (single low ASB incident - verbal warning); 1st Stage (single significant ASB - 1st formal letter); 2nd Stage (reoccurring incidents - 2nd formal letter) ; Final Stage (a serious incident or where ongoing incidents move to a legal stage) Severity selection • Users must select a severity level from a dropdown menu when submitting an ASB incident • The selection is mandatory and required to proceed The system displays a set of standard date-related questions (e.g., "When did the incident occur?") Dates are required fields and validated for format (e.g., DD/MM/YYYY) Anti-Social Behaviour: Person at Risk [Drop Down] Location of Incident [Drop Down] ASB Category [Drop Down] Description [Free Text Box] Escalation stages - Fundamental: Allows the user to add information regarding the initial conversation with the perpetrator, and any follow up actions required Allows the user to add information should they think the perpetrator has stopped ASB behaviour Allows the user to move the task to the next stage (Stage 1) or skip to the final stage (Final Stage) Stage 1 – Formal warning (Letter 1) Allows the user to add information on the actions taken and ongoing incidents that happen Allows the user to move the task to the next stage (Stage 2) or skip to the Final stage (Final Stage) Stage 2 – Escalated warning letter (Letter 2) Allows the user to add information on the actions taken and ongoing incidents that happen Allows the user to move the task to the next stage (Final Stage) Final Stage: Allows the user to complete a solicitor instruction template so that we provide all of the detail required to solicitors Allows the user to add information to the system to confirm legal information including dates of service for legal notices, court dates and solicitor details Allows the user to add information on the outcome from the legal proceedings and any actions required Allows the user to confirm a recovery date When I am viewing an ASB case, the system displays the ASB case stage (workflow stage) including: ASB incident logged, investigation pending / being investigated / Response issued case closed / reopened) Case status shall include stages such as: New, In Review, Action Taken, Escalated, Closed. • Access to case data is restricted based on user roles • Grainger colleagues’ data visibility is scoped by site, portfolio, or cluster. • Different ASB case types have defined visibility rules per role • Reports include actionable insights and lessons learned summaries • Track service of notice so that when a notice is being served a user can log it in the system entering notice type, service date, expiry date and reason for service (ie Rent arrears, ASB, refurb etc) • When a notice is served user can specify via selection whether prepared internally or via a solicitor, providing the relevant solicitor details • The system can be updated with notes, updates, timestamps on events and communications • When a court hearing is scheduled, dates can be added into the system including court hearing date, location, case reference • Correspondence can be attached to the task • When a baliff date is set, the system allows input of scheduled baliff date and any associated information (baliff contact details) • I can select the relevant status for the stage of legal service (ie notice served awaiting expiry, notice being prepared awaiting service, court hearing pending etc) | 2, 3, 4, 5, 7, 8, 9, 13, 19, 22, 24
ASB | Update Tenancy from Case | - Flag eviction notice & reasons on tenancy. - See related list of cases on a tenancy (where reporter or perpetrators) - See related list of cases on an account (where reporter or perpetrators TBD) | 2
ASB | Evidence & Note Timeline | For ASB & Incident Cases: - Users see a user-friendly timeline of all case notes & evidence (files, videos, photos). - All evidence files are timestamped and cannot be edited or deleted. - Notes/comments can be added & edited with date/time & user stamped. | scope down to standard | • The system accepts various media types from multiple sources (see earlier user story) • The Grainger resident app connects securely to the system, allowing residents to submit evidence confidently • All submissions via the app maintain security and confidentiality standards • Every piece of evidence or case note uploaded is automatically timestamped • Timestamps are visible for tracking and audit purposes • Once evidence is uploaded, it is locked to prevent alteration or deletion, ensuring data integrity • The system provides a timeline view of all case notes and evidence entries. • The timeline is easy to navigate and understand The system has comment fields to allow users to record details and updates for each ASB task Users can edit or add new entries with time and date stamps and user stamp | 4, 15
ASB | Link Multiple Reporters & Perpetrators to a Case | - 'Reports' sub-object to the case? - Roll up count of number of reports on a case. - TBD: Multiple perpetrators can be linked to the same case. TBD if requires a record or just a list of account / contacts | 5 | • Users can add multiple reporters to an existing ASB case • Each reporter has an independent workflow and response tracking • Multiple perpetrators can be linked to the same case • Reports and dashboards display the number of reporters associated with each case • System prevents creation of duplicate cases by linking new reports to existing cases where appropriate | 20
ASB | Identify Duplicate Incidents | - Alert user to potentially related ABS incidents based on reporter / tenant / unit / tenancy. - User must review duplicates before proceeding. - User is prompted to check for duplicates after 3rd party initially creates the case. | 3 | • The system will link related incidents accordingly based on customer/unit for comprehensive case tracking When I enter the any of the: complainant / alleged perpetrator / property address into the system – the system will alert me to any potential duplicates The system will display a ‘potential duplication’ alert message on the screen and I cannot proceed without reviewing the duplicates Existing records matching complainant and or alleged perpetrator and or unit address are displayed to me clearly for review as well as case raised date / task creator or owner • I am asked to review the duplicate records and given the choice as to whether I want to switch to a pre existing ASB case or continue to create a brand new record • System prevents creation of duplicate cases by linking new reports to existing cases where appropriate • Within the system, when the Grainger user selects a customer OR a unit – any Incidents previously logged relating to either entity or those (customer/unit) should be displayed • The Grainger user can select the ‘incident’ reference number to review the complete issue • Sensitive cases are hidden from general users and only visible to management • The Grainger user can mark whether a linked incident should be included in another ASB investigation | 1, 12, 22
ASB | Send Notifications to ASB Incident Reporters | - Send automated notifications to the reporter(s) (tenant/staff/3rd party) - Sent via the reporter’s preferred contact method (i.e. email or SMS). - Capture preferred contact method on an account? - 2-5 x automated notifications: Sent on case creation & completion [TBD]. - Send seperate emails if there are multiple reporters. - 3 x email templates that the user can select. [new reporter on existing case, stage update, letters sent] - Send seperate emails if there are multiple reporters (be able to select the recipient) | scope down to standard | Acknowledgement on Submission: When a reporter submits an ASB incident, they receive an automated acknowledgement confirming the incident has been logged. The message includes a reference number and a brief explanation of next steps. Notification on Resolution: When the incident task is marked as completed/closed in the system, the reporter receives a second notification. The message clearly states the outcome and indicates that the case has been closed. Delivery Channels: Notifications are sent via the reporter’s preferred contact method (i.e. email or SMS), as specified during submission. Resident correspondence (acknowledgement, stage updates, formal letters, outcomes) are generated and sent from the system Selectable templates for different stages of communication with complainants including: • Initial acknowledgement with ASB policy or guidance for residents attached • Case update templates • Final outcome template The templates issued will link to stages of the ASB workflow • The (email) communication can be issued via the ‘system’ and replies from complainants will be received back within the system also (two-way communication) • All communications to and from the complainant are registered against the ASB case file and/or the customer account (provided they are a Grainger resident) • The Grainger user can select the relevant template from within the system • The Grainger user can select the relevant Grainger resident (where relevant) from the system – to whom the communication is to be sent to • The ‘system’ will integrate with Microsoft Outlook ensuring that any communications received or issued via outlook are automatically logged against the customer and/or unit in the ASB case file • Each reporter has an independent workflow and response tracking | 6, 11, 14,20
ASB | Send Notifications to Grainger Stakeholders | - Send automated notification emails on creation of ASB or incident case to stakeholders (manager / director / H&S Team) or once severity has been assigned. [2 templates?] - Recipients depend on severity of case and record type. | scope down to standard | Automated notifications • Upon submission, the system sends an automated notification to the relevant (Manager and/or Director), based on the selected severity • Notifications must include: incident details, severity classification and time and date stamp Escalation visibility: All incidents marked as ‘Final Stage’ must also trigger a high priority alert to the Department Head/Manager/Director Notification format: Notifications are sent via email • The same data is viewable on a dashboard either within source system or i.e. Power BI Audit Trail: All notifications logged in the system have a timestamp as to when they were sent and to whom for traceability purposes | 8
ASB | Generate & Send ASB Documents | - Generate 4x documents: Formal Warning Letter 1; Escalated Warning Letter 2; Solicitor instruction template; S8 Notice. - Documents are partly pre-populated & partly editable. - Send doucument from case; document & email linked to case. - Capture / default a deletion date on each document. | out of scope | Escalation stages - Stage 1 – Formal warning (Letter 1) Allows the user to select pre-formatted Letter 1 template The system presents the template in an editable format The system pre populates (merge fields) such as Dear (resident name) Allows the user to edit any part of the template if required Stage 2 – Escalated warning letter (Letter 2) Allows the user to select pre-formatted Letter 2 template The system presents the template in an editable format The system prepopulates (merge fields) such as Dear (resident name) Allows the user to edit any part of the template if required • The system generates a precedent section 8 notice in the latest form with drop down boxes to select the relevant grounds, allowing the selection of multiple grounds where appropriate. • Within the Section 8 form, free-text entry is available for additional details as needed • The system allows for documents created and stored there to have a deletion date specified and this is either autodeleted or prompts the responsible person to review and delete or reset date as appropriate. • Documents have specified deletion dates • Access to stored documents is limited to those with a legitimate business need to access them. | 9, 16
ASB | Tenants & 3rd Parties Submit Incident or ASB Case | - Customer, contractor, colleague, member of public or other relevant party reports ASB or incident case via: - Internal webform (staff/employee)?? - Public-facing Form Assembly form - Tenant can access FA form via mobile app > creates a new case > flag to manual review. - User can send email to tenant/3rd party with a link to complete form > update case. - Able to upload files, photos on Form Assembly. TBD is this possible? | out of scope | The system shall accept a reported case of ASB from employees, residents, and 3rd parties including: internal webform (staff/employee), public facing web form and/or resident app, input manually into system (entered manually by staff) ASB reports submitted via the app are automatically routed into the central ASB system Each case reported t shall generate a unique case ID and timestamp for tracking and audit purposes The Case ID is visible to system users The system shall capture structured information including: Nature of the complaint (i.e. noise, harassment, substance misuse etc.; Location (property/unit/address); Parties involved (complainant and alleged perpetrator); Date and time of the incident; Supporting evidence (photos, videos, witness accounts); Mandatory fields must be completed before submission File types and size limits are enforced for media uploads and error messages clearly displayed to the system user where an upload has failed or is not possible | 11
ASB | ABS Tasks | - Automated task generation depending on the nature of the ASB incident | out of scope | • The system has automated task and workflow generation and automatically creates follow up tasks depending on the nature of the ASB incident | 18
ASB | Merge Duplicate Incidents | If there is an existing case for the same incident: - Ability to merge existing case details into existing case: E.g. create a new report record on an existing case (copy files, data across) and close current case? | out of scope
ASB | Link Incidents | If there is a seperate, but related case: - The user can link the cases. - Related list of linked cases visible both ways. | out of scope
ASB | KPI Tracking Status | SLAs related to severity. - Colour-coded SLA tracking [formula fields]. '- Additional (?) SLAs for turnaround time on each Stage - Each stage has associated start date & due date. - Users can extend the ‘due date’ & provide a reason. - Calculate colour-coded flags. - User can see next actions & due date to complete each stage. - See where any actions/tasks are overdue. - When an ASB case is created or 3rd party case is reviewed: Auto-assign case based on severity. | 5 | Built in SLA’s should reflect the severity level of the task in the same way they do on any normal maintenance job: - Low severity = Standard SLA (i.e. 5 working days) - High severity = Urgent SLA (i.e. 24–48 hours) - Severe = Critical SLA (immediate action required) Internal severity level determines who a task is assigned to: - Low severity → RSA (Resident Support Advisor/CST) - High severity → RSM (Resident Services Manager/Portfolio Manager) - Severe → Senior Management or Legal Escalation logic shall route high-risk or persistent ASB cases to senior teams or legal advisors • Each ‘stage’ of the workflow is timebound with an associated ‘start’ and ‘due date’. • As a user I can see what my next required actions are on my ASB cases and by what date they are due • The system will flag to me the business where any stages/actions/tasks are overdue • As a user I can extend the ‘due date’ by providing a ‘reason’ and the reasons must be selectable from a drop-down list. • Extension reasons are logged for audit and reporting purposes | 13, 20
ASB | ASB - Reporting & Dashboards | Reporting on ASBs & Incidents - Number of incidents / ASBs by portfolio, incident category, severity level, case status, dates/months - Cases with highest severity. - Number of new, open, closed and escalated cases in the month - Portfolio comparisons = OUT OF SCOPE - KPIs: Overdue stages - Display open, closed cases, response times - Overdue tasks - Filter by date range, portfolio, severity, etc TBD = The system cannot provide drilled-down information to non-reporters to ensure private information is secure (GDPR , etc.) | 5 | A dashboard that allows reporting of numbers by: portfolio, incident category, severity level, case status, dates/months A drill through option to see case by case updates Ability to click on summary numbers to drill into individual case records A high-level report that allows monthly operational reporting including: number of new, open, closed and escalated cases in the month, portfolio comparisons The system can generate an pdf or excel summary suitable for export All data shown is filterable by date range / portfolio / severity •The system to link to [Power BI] with a dedicated dashboard of real-time key KPIs allowing users to drill down to specific details* allowing quick identification of repeat offenders. •Display open, closed cases, response times •*The system cannot provide drilled-down information to non-reporters to ensure private information is secure (GDPR , etc.) •The user can filter reports by date range, location, property and other relevant criteria • Reports and dashboards display the number of reporters associated with each case • The system will flag to me the business where any stages/actions/tasks are overdue | 10, 17, 20
ASB | Print Case Details | The system presents a report in a printable format detailing times, notes and actions taken | out of scope | When ready to instruct solicitors, I would like the system to produce a report of the incident timeline with dates and notes so that this report can be used as evidence on a possession hearing. • The system presents a report in a printable format detailing times, notes and actions taken | 26
ASB | Anonymise data |  | out of scope | • The system enables ASB data to be collected and anonymised to meet any reporting requirements to local or central government.
Pet | Create Pet Application Case | - Create pet application case from new lease opp: Pre-populate with unit, account, etc. - User creates existing tenant's pet case from verbal request. - Auto-assign each case to the appropriate property team or customer service group based on the resident’s building, unit, or tenancy profile. | 3 | As part of the leasing journey, the applicant should have access to a link to complete an online form for a pet request. As a Lettings User I want to create a new case to manage the application request for a new pet. As a mid-term customer I would like to apply for a pet in person speaking to Front desk As a management user I want to create a new case to manage the application request for a new pet if requested by a resident, or where we identify and unregistered pet within the building I want to send a link, or complete the form in person with the applicant detailing the pets they are requesting The system must automatically route each pet registration request to the appropriate property team or customer service group based on the resident’s building, unit, or tenancy profile. This ensures that the correct team is responsible for reviewing and processing the application without delay. | 1, 8
Pet | Pet Application Cases | - Page layouts for 2 record types: new and existing tenants - Stages / progress bar - Link to customer, tenancy & to new lease opp (if applicable) - Capture multiple pets (maintain pet register below) - Upload files (documents, photos) to case and/or individual pet record. - Email from case. - See block / floor capacity traffic light indicator. - Validation (e.g. file type & expiration date validations). - Existing tenants: See all existing pets already in the unit (from the pet register) | 13 | I want the case to be linked to the customer object and linked to the application/lettings journey 13- Documents and photos relating to the pet can be stored against the customer record and the pet Case The system must maintain timestamped logs of all actions taken within the pet registration platform. This includes every submission, update, approval, rejection, and document upload, with each entry clearly recording the date, time, and user responsible. These logs ensure full traceability and support internal audits. The system must support integration with a document storage platform such as SharePoint or AWS S3. This will allow secure upload and retrieval of pet-related documents, including vaccination records, insurance certificates, and policy acknowledgements, with appropriate access controls and retention policies. The system must ensure full compliance with the UK General Data Protection Regulation (UK GDPR), including secure handling, storage, and processing of all personal and pet-related data. Data must only be retained for as long as necessary and must be stored in a manner that protects against unauthorised access or loss. Access to the system must be governed by strict role-based permissions. Frontline teams should have read and write access to pet records relevant to their site. Management users must have administrative privileges, including the ability to override decisions and update policies. Once a resident submits a pet registration request, the system must issue an acknowledgement within five business days. This acknowledgement should confirm receipt of the application and outline the next steps in the review process. | 12, 15
Pet | Maintain Pet Register | - Pet register records: [new object?] - Link each pet to an account & tenancy & unit & pet application case (optional) - Ability to indicate where tenant has declared not having pets. - Ability to indicate where there is a decision not to charge. - Each record has docs linked e.g. vet vaccine records. - Each record can have comms & tasks associated (activity timeline) - Able to see/access approval / rejection history - from linked cas? - Able to see/access history of pet rent. | 5 | A current list should be accessible with data fields to record pet detail and any pet collar reference numbers for lost pets The system must include a centralised digital pet register that consolidates all pet-related data across the portfolio. The system must include the ability to mark a unit as having “no pets declared.” This status should be clearly recorded and visible in the register to support accurate record-keeping and compliance monitoring. The system must provide access to a full audit trail of all pet registrations, including timestamps, user actions, and document history. The Compliance Officer must be able to filter records by site, approval status, or document type, and export data for audit or regulatory purposes. Any missing or expired documentation must be clearly flagged. In such cases, the system must allow for a “no charge” status to be recorded, along with a reason and reference to the relevant legal or policy exemption A complete change history must be retained for each pet record. This includes changes to pet status, updates to submitted documents, approvals or denials, and any charges applied. The history should be accessible to authorised staff and presented in a clear, chronological format. | 7, 10, 11, 31
Pet | Search / View Pet Register | - Dashboard or Custom List View - Search pet register by site, tenant name, unit number, pet type, approval status - Able to export pet register | 5 | This register should be fully searchable by key fields such as tenant name, unit number, pet type, and approval status, allowing onsite teams to quickly locate and review relevant records.
Pet | Integrate Pet Application Cases with New Lease Opportunity. | - See if unit / building allows pets on opp. - See block / floor capacity traffic light indicator on opp. - Update case & pet register from opp: - If unit is changed: Update unit & delete/nullify any existing approval? - Close case & update pet register status if opp close/lost. - Update pet register status once opp goes to Audit or Closed Won; link case / pet register to tenancy. - New lease opportunity requires extra validations if there is a linked pet case. | 5 | • The System displays if the apartment is pet friendly • The system displays if the building is at capacity for pets on the floor, or whole building - The system will show user a list of banned/prohibited pets
Pet | Manage Pet Policies | - Manage buildings, floors & units that allow pets. - Pets not allowed in listed buildings. - Maintain list of banned pets [general policies] - Configure global pet policies [text] (general, listed buidings, etc.) & block-level overrides. - TBD: Save a history of policy verions, date/user stamp, description of update; effective date. | out of scope | The pet register should allow the user to set limits against each site by selecting pet friendly apartments on each floor. A limit threshold should be set preventing too many pets being allowed by floor and at a building level 1- each unit/floor/building should allow the user to set limits against each site by selecting pet friendly apartments on each floor. Property-specific pet policies (e.g., pets not allowed in listed buildings) Tenancy type or unit size (e.g., max 2 pets for 1-bed units) Lease restrictions or local council limitations pet policy associated with each property. For example, pets may not be permitted in listed buildings or heritage properties due to structural or conservation restrictions For instance, a one-bedroom flat may be limited to a maximum of two pets, while larger units may allow more. These thresholds should be customisable at the scheme or unit level. The system must allow landlords or administrators to configure a global pet policy that applies across all sites by default. This policy should support rules such as restrictions on exotic pets, specific breed limitations, and a maximum number of pets per unit. In addition to the global policy, site- or scheme-level overrides must be supported, enabling local managers to tailor rules based on building-specific needs or insurance requirements. The system must maintain full version control of all pet policies, including a history of changes, effective dates, and archived versions for audit purposes. If a property is exempt from the standard pet policy — for example, due to listed building or heritage status — it must be clearly flagged in the system, and this exemption should be visible to both staff and residents. Only authorised users, such as landlords or regional managers, should be able to create or modify pet policies. All changes must be logged with user identification, timestamps, and a description of the update. Traffic Light KPIs Update against the floor/Unit to show if at maximum capacity The traffic light system is intended to provide a clear, visual representation of pet density within a building, block, or floor. It helps onsite teams monitor how many pets are currently registered in a given area and whether that number is approaching or exceeding recommended thresholds. A green status indicates that the number of registered pets is within acceptable limits for the building or floor, based on internal policy or capacity guidelines. This suggests that there is still room for additional pet registrations without concern. An amber status means that the number of pets is nearing the upper threshold. While still within limits, it signals that the site team should monitor new registrations closely and may wish to review any pending applications more carefully. A red status shows that the number of pets has reached or exceeded the defined limit for that area. In this case, new pet registrations may be paused or subject to additional review, and the site team may need to assess the impact on shared spaces, maintenance, and resident wellbeing. | 2, 7, 10, 14, 20
Pet | Manage & See Pet Capacity | - Manage pet capacity (%): By floor & by building/block - Calculate capacity by floor & by building/block - Traffic light indicator of pet density / see if at limit or approaching limits - Pet limits by unit type or tenancy type (1 bed vs 2 bed) - Ability to override at unit-level & block-level. - Calculate # pets allowed per unit based on block / floor / unit type. | out of scope
Pet | Update Unit & Tenancy | - See a view / related list of current pets on a unit? - See a related list of current & previous pets on a tenancy. | 1
Pet | Tenant Completes Online Form | - Send email with link to form [2-3 templates - new lease, existing tenant request for pet, unregistered pet identified in bldg] OR Resident can initiate process by completing Form Assembly form accessed from the App [Grainger] - Form Assembly form for tenant to request one or more pets [Grainger] - Updates or creates pet case & associated pet register records? - Auto-assign new cases & send notification email. - See & acknowledge applicable pet policy & save version accepted. TBD - OTP verification - Upload photo / documents | 5 | • The online form allows the capture of dynamic pet information • The online form includes pets not acceptable • The online form returns the data into a Pet Register • The online form has a clause to indemnify Grainger against refusal (Can GPLC do this?) As part of the leasing journey, the applicant should have a clear guidance on the pet application process with a caveat that pets may be refused where buildings are at the maximum pet allowance During the pet registration process, residents must digitally acknowledge and accept the policy, with the system recording the date, time, and version of the policy accepted. Consent tracking must be embedded into the system, ensuring that residents explicitly agree to data usage terms before submitting pet information 'From the App, the resident should have access to a link to complete an online form for a pet request 1- The app should have a form link available to open and complete a form assembly application. 2- The online form allows the capture of dynamic pet information 3- The online form includes pets not acceptable 4- The online form returns the data into the customer object. 5- The online form has a clause to indemnify Grainger against refusal 6- The request for a pet application should alert the management team of a new request, and a new S/F case should be created for the management team to progress | 3, 14, 16
Pet | Automated Approval/Rejection | - Some level of auto-approval / auto-rejection of a new case (or after pet details are entered): - E.g. Listed building = no pets - Auto-approve caged pets? - Tenant receives automated approval/rejection response (same as manual rejection/approval). - Includes applicable explanation. - A user can re-open a rejected case & override / approve on an exception basis. | out of scope | Automated rules based on: Property-specific pet policies (e.g., pets not allowed in listed buildings) Tenancy type or unit size (e.g., max 2 pets for 1-bed units) Lease restrictions or local council limitations Manual override with justification field for exceptional cases The system must apply automated approval logic based on a set of predefined rules aligned with property-specific policies and tenancy conditions. These rules should be configurable and enforced consistently across the platform to ensure compliance and reduce manual processing. Approval decisions must take into account the pet policy associated with each property. For example, pets may not be permitted in listed buildings or heritage properties due to structural or conservation restrictions. The system should automatically reject applications that conflict with such rules, providing a clear explanation to the resident. Tenancy type and unit size must also be factored into the approval logic. For instance, a one-bedroom flat may be limited to a maximum of two pets, while larger units may allow more. These thresholds should be customisable at the scheme or unit level. In addition, the system must consider any lease-specific clauses or local authority regulations that may restrict pet ownership. Where such restrictions apply, the system should validate the application against these terms before proceeding. For exceptional cases, the system must allow a manual override by authorised staff. When an override is applied, the user must be required to enter a justification, which will be recorded in the audit log for transparency and future reference. | 10
Pet | User Approves/Rejects Pet Application | - Approve/reject applications: TBD if full approval request process is required or just an audit trail of the user who approved/reason/etc? - Assign case in 'Pending Approval' to PM/RST for approval - Update pet register & case status on approval/rejection. - Approve/reject permissions - Notify tenant of outcome | 2 | • The Acceptance or Rejection decision is recorded with clear reasons to the decision • The system responds to the applicant with the outcome and reason notes • Where rejected - the comms include guidance on how to appeal/complain • The system updates the lettings process on the decision | 4, 6
Pet | Manage Rejections | New lease rejections: - Above email has a link to a FA Form [Grainger to dev] that allows tenant to proceed without pet or cancel the new lease application. - On cancelling: Close Lost the new lease opp; create a task for the opp owner / lettings team to re-market the unit. - On proceding without a pet: Notify new lease opp owner? New lease approval: Notify new lease opp owner & update opp status?? | out of scope | Rejection 2- Rejection - The system responds to the applicant with the outcome and reason notes, the comms include guidance on how to appeal/complain 3- Rejection – within the Form Assembly response the customer has an option to proceed without a pet, or cancel the application process 4- Rejection – if the cancelation option is chosen, the application is updated with a task for the lettings team to re-market the property 5- Rejection – If rejected the pet case is updated and the pet details are kept on record, but added with a status of rejected
Pet | Email Templates | Add email templates for manual comms: - 3-4 email templates - approve/reject for existing/new tenants - Make default email templates availble: Acknowledgement of case email template - pet removed templates x 2 | 3
Pet | Calculate Pet Rent | - Building/Block: Configure pet rent by builing, or global pet rent with exceptions? - Calculate pet rent based on the number and type of pets registered, as well as any site-specific pricing rules or exemptions. - Existing tenant with existing pets: Calculate total for all pets. - New lease: Display pet rent on new lease opportunity. | 3 | The system requires an additional monthly charge item for a Separate Pet Rent in addition to the Unit Rent and Parking/Garage Rent. The system must automatically apply pet rent in accordance with the terms of each resident’s tenancy agreement. This calculation should take into account the number and type of pets registered, as well as any site-specific pricing rules or exemptions. Once applied, the charges must be seamlessly integrated with the organisation’s finance systems — such as MRI, Yardi, or Salesforce — to support accurate invoicing, payment tracking, and financial reconciliation. The system must allow leasing operatives to manually add a separate rent charge specifically for pets to a resident’s account. This charge must be configurable based on the number and type of pets, and it should be linked to the relevant tenancy record. The system must also check whether the tenancy agreement permits the application of pet rent and whether any exemptions apply, such as those related to incoming legislation. Once added, the pet rent charge must be clearly itemised on the resident’s rent statement and visible in both the finance system and the resident portal. The system must support recurring charges, with the ability to set start and end dates, and must allow for adjustments or removal if the pet is no longer present or if the resident becomes exempt. All actions taken by the leasing operative must be logged in the audit trail, including the reason for the charge and any supporting notes. The system must also generate alerts for any inconsistencies, such as duplicate charges or missing documentation. All actions taken by the leasing operative must be logged in the audit trail, including the reason for the charge and any supporting notes. | 13, 32
Pet | Create Pet Licence Contract | - Create a residential contract for a pet licence? - Linked to the case and/or opportunity? - Link the contract to the new/exisiting residential tenancy. - Different logic for new/existing tenant? - Activate the contract when the case / new lease opportunity is complete? - Different logic for new/existing tenant. - Update pet register with confirmed/active status on activating the contract? - Close case at some point in the process. Existing tenants with existing pet: - Cancel the existing pet licence contract & create new one with total rent? Ability to end pet rent without removing the pet (e.g. tenant becomes exempt): Manually capture end date on contract & create a task for credit control. | out of scope
Pet | Tenant Signs Pet Licence | - Generate pet licence document for tenant to sign via Adobe sign - Generate Pet Policy document to send?? - Chaser emails - for new lease only or 2 templates (new & existing tenants)? | out of scope | Approved 6- Comms are sent to the applicant to confirm with the pet policy, site rules and a form to sign accepting T&C’s [new leases] The Tenancy Progression does not complete unless the T&C’s are returned 7- The case is automatically closed when the customer signs the T&C’s accepting the policy and site rules. 8- If the T&C’s are not signed within 48 hours a follow up chaser is sent to the resident Lettings Process TPT update system and send out Docs including Pet Policy for signature as part of TA The TA needs to have a Separate line Item for Ret Rent on the TA Additionally, the system must support digital signature functionality, allowing residents to formally acknowledge pet policies and related agreements in a legally compliant manner. | 4, 16
Pet | SLAs | - Save key dates on pet application case - Calculate KPI indicators [different timeframes for new & existing tenants]: - Acknowledgement of pet request timeframe - Decision timeframe - Send alert (email) if case approaching SLA. - Reassign case if overdue SLA. - Manage escalation path? | scope down to standard | Once a request is submitted, SLA timers must be activated to track progress against defined service levels. The first timer should monitor the acknowledgement period, ensuring that the resident receives confirmation of receipt within five business days. A second timer should track the decision period, requiring that a final outcome — either approval or rejection — is issued within ten business days. These timers must operate in real time and be visible to staff via the operations dashboard. If a request is approaching or has exceeded its SLA, the system must generate an alert and escalate the case to a designated manager or senior team member for immediate attention. 1- Rule: Automatic allocation of cases to relevant property or customer service teams. 2- KPI: Acknowledgement of a request should be within 5 business days (mid term application) 3- KPI: Decision: within 10 business days (mid term application) 4- Rile: Alert notifications for pending requests breaching SLA. 5- Escalation routing for overdue approvals with a data stamp of person approving A final decision — whether approval or rejection — must be made within ten business days of submission. The system should automatically track these timeframes and monitor all pending requests against the defined service level agreements. If a request approaches or exceeds the SLA threshold, the system must trigger an alert notification to the relevant site or management team. These alerts should be visible on the operations dashboard and, where appropriate, sent via email or internal messaging tools. For any requests that remain unresolved beyond the ten-day decision window, the system must initiate an escalation process. This should route the case to a designated senior team member or manager for urgent review, ensuring timely resolution and accountability. | 8, 9
Pet | Remove Pet from a Tenancy | - Create a case [new record type] - User can send a link to a FA form for tenants to enter info OR user enters the details. - TBD : Display all existing pets linked to the tenancy & the tenant can select the one(s) to remove. - OTP verification. - Tenant can access a link to the form from MyGrainger app -> auto create the case. - If other pets remain: Calculated the revised pet rent. - TBD See other pets linked to the tenancy on the case. - Auto update pet register (status). Manual - Case has a step/stage for credit control to end/update pet rent in Qube. - Manual: End the pet licence contract. - If other pets remain: - Manual? Create a new pet licence contract with the reduced pet rent amount? - Generate new pet licence contract for signing? Send via Adobe Sign. - Chaser email? - On completion of case: Send automated email to tenant notifying them pet removed from register & pet rent stopped or reduced with effect from [date]. [2 templates] | 5 | When a resident reports that a pet has been sold, rehomed, or has sadly passed away, the system must allow for an update to be made to the pet register. This update should be initiated either by the resident through the self-service portal or by site staff following direct notification. The pet’s status should be changed from “Active” to either “Removed – Rehomed” or “Removed – Deceased”, depending on the reason provided. The system must retain a record of the pet’s registration history, including the date of removal, the reason, and the user who made the change. This ensures a full audit trail is maintained for compliance and reporting purposes. Once a pet is marked as removed, it should no longer count towards the unit’s active pet total, and any associated alerts (such as maintenance warnings or pet rent reminders) should be deactivated. However, the historical record should remain accessible to authorised staff for reference. If the resident wishes to register a new pet in place of the one removed, the standard registration process should apply, including policy acceptance and document submission. Once a pet is marked as removed, it should no longer count towards the unit’s active pet total, and any associated alerts (such as maintenance warnings or pet rent reminders) should be deactivated. However, the historical record should remain accessible to authorised staff for reference. If the resident wishes to register a new pet in place of the one removed, the standard registration process should apply, including policy acceptance and document submission. | 23
Pet | Operations Dashboard | Site-related pet activity, including: - Number of pets, - Pending approvals - cases approaching / exceding SLAs - Any missing or expired documentation - Policy breaches (pets in units /buidings not allowed pets; too many pets per unit) - Pets not being charged rent. - See pet capacity by block & floor & if at limit or approaching limit. - See which floors & units allow pets (& are available / not over capacity) [traffic light indicator] - Filter dashboard by block, unit type, or pet type - Link to load dashboard from a new lease opportunity or case. - SF limitations - we can't filter by each block? More than 50. | 5 | As a Lettings User/Property Manager I want to see a Dashboard and Report on the system what units are available/ acceptable for pets at unit and block level Acceptance 1-The System displays if the apartment is pet friendly 2-The system displays if the building is at capacity for pets on the floor, or whole building 3-The system will show user a list of banned/ prohibited pets 4- A pet Register/Dashboard should show a full list of pets and capacity percentage with availability for remaining pet acceptance The operations dashboard must display a real-time summary of pet-related activity across the site. This includes the number of active pets, pending approvals, expired documents, and any policy breaches. The data must be filterable by date range, unit type, or pet type, and exportable for reporting purposes. The system must identify residents with registered pets who are not currently being charged pet rent and flag these cases for review. The register must be accessible via the operations dashboard, providing real-time visibility to authorised staff. This ensures that teams can monitor pet registrations, track compliance, and respond to queries or incidents efficiently. | 30, 31
Pet | Reminders for Updated Pet Docs | - Save expiration date for each pet documents. - Business rules on which pets require which docments. - Pet- and tenancy-level documents: Vet certificates per pet; insurance per tenancy? - Calculate traffic light indicator for docs missing, overdue, or expiring soon. - Automated reminder emails to tenants to send docs. [2 email templates?] - Tenant will be able to reply to the email with docs attached? Thread it onto the pet registe record? Notify a user/create a task? OR gets a link to a form assembly site that they can upload docs to? Create a linked task for a user to review? | out of scope | the system should issue annual renewal prompts to residents. These reminders should request updated documentation, such as valid pet insurance or veterinary health certificates, and ensure continued compliance with pet policy requirements. All uploaded documents — such as insurance policies or vaccination records — must be stored securely, with expiry tracking in place to prompt renewal or removal when documents become outdated. The system should support integration with secure document storage platforms and enforce access controls based on user roles. Automated reminder notifications must be built into the system. These should alert residents when key actions are due, such as insurance policy expiry. Notifications should be delivered via email or app alerts, depending on resident preferences. Any missing or expired documentation must be clearly flagged. The system must automatically track expiry dates for pet-related documents such as insurance or vet certificates. Residents must receive reminders in advance of expiry, with clear instructions for uploading updated documents. If no action is taken, the system must flag the record for follow-up by the site team. | 24, 26, 29
Pet | EOT | On confirmation of actual move out: • Update status on pet register. = task for user • Update pet licence status. | 2 |  | 23
Pet | Trigger Survey | Once a pet registration request has been approved or denied, the system should prompt the resident to complete a short feedback survey. | out of scope | Once a pet registration request has been approved or denied, the system should prompt the resident to complete a short feedback survey. This will help monitor resident sentiment and identify opportunities to improve the process over time | 17

## Proposal v1_Estimate
Rates (£) |  |  | Points |  | Sprint Team | [5 empty] | Key
Currency | £ |  | Estimated Feature Points |  | Role | # People | Allocation | FTE | Split | Target | Enter value
Sprint 0 Rate per Hour (T&M) | 163 |  | Unanticipated Scope |  | Dev Senior | 1 | 100% | 1 | 57.14% |  | Default value across projects
Project Rate per Hour | 102.3769 |  | Unanticipated Complexity |  | Dev Junior | 1 | 100% | 1 |  |  | Calculated (formula)
Weeks per Sprint | 3 |  | Total Points | 0 | QA | 1 | 50% | 0.5 | 14.29%
[5 empty] | Jacob | 1 | 30% | 0.3 | 8.571% |  | People involved in Estimate
UAT & Production Support |  |  | Build - Sprints |  | BA | 1 | 35% | 0.35 | 15.71% |  | Sam Duncan
UAT Weeks - 2 releases |  |  | Optimistic Sprint # | 5 | Architect | 1 | 20% | 0.2 |  |  | Shaun Barrett
Prod Support Weeks - 2 releases |  |  | Pessimistic Sprint # | 8 | PM | 1 | 15% | 0.15 | 4.286% |  | Nikki Papenfus
Team Size (FTEs) | 0.5 |  | Team Size (FTEs) | 3.5 | Team Size |  |  | 3.5 | 100% | 0% | Jacob
Cost per Week (£) | 2047.539 |  | Cost per Sprint (£) | 42998.319
|  |  |  | 105% | Velocity
Notes |  |  |  |  | Range | Points per Dev per 3-week Sprint |  |  | Points per Sprint
Requirements provided; 2 releases |  |  |  |  | Optimistic | 1 Senior Dev FTE |  |  | 0
1 Junior Dev FTE
[5 empty] | Pessimistic | % of Optimistic |  |  | 0
Internal - Pets & ASB
Project Phase | Min Effort | Max Effort | Lower Bound (£) | Upper Bound (£) | Sprint 0
Consultancy Pets & ASB 1 (Hours) - 4 weeks | 100 | 200 | 16300 | 32600 | Weeks (Min)
Sprint 0 - Pets and Asb (Hours) - 3 weeks | 50 | 60 | 8150 | 9780 | Weeks (Max)
Build (Sprints) | 3 | 5 | 128994.957 | 214991.595 | BA Allocation
Final UAT (Weeks) | 3 | 3 | 6142.617 | 6142.617 | Client Meetings (hours per week)
Prod Deployment & Support (Weeks) | 2 | 2 | 4095.078 | 4095.078 | Internal Design Meetings (hours per week)
User Guide(s) (Hours) | 16 | 20 | 2608 | 3260 | Total Hours (Min) |  |  |  | 0
Total |  |  | 166290.652 | 270869.29 | Total Hours (Max) |  |  |  | 0
Internal - RRB |  |  |  |  | Timelines
Project Phase | Min Effort | Max Effort | Lower Bound () | Upper Bound () | Target Start Date |  |  | 2025-11-01
Consultancy 2 RRB Formal Challenge (Hours) - 4 weeks | 50 | 100 | 8150 | 16300 | Estimated End Date
Sprint 0 (Hours) - 3 weeks | 50 | 60 | 8150 | 9780 | Release 1 | Lower Bound |  | Upper Bound
Build (Sprints) | 2 | 3 | 85996.638 | 128994.957 | Consultancy / Sprint 0 | 2025-12-19 |  | 2025-12-19
Final UAT (Weeks) | 3 | 3 | 6142.617 | 6142.617 | Build | 2026-02-20 |  | 2026-04-03
Prod Deployment & Support (Weeks) | 2 | 2 | 4095.078 | 4095.078 | UAT/Go Live | 2026-03-13 |  | 2026-04-24
User Guide(s) (Hours) | 8 | 12 | 1304 | 1956 | Support | 2026-03-27 |  | 2026-05-08
Total |  |  | 113838.333 | 167268.652 | Release 2
[5 empty] | Build | 2026-04-03 |  | 2026-06-05
External Quote - Pets & ASB |  |  |  |  | UAT/Go Live | 2026-04-24 |  | 2026-06-26
Project Phase | Duration (Weeks) |  | Lower Bound (£) | Upper Bound (£) | Support | 2026-05-08 |  | 2026-07-10
Consultancy | 4 | 4 | 16300 | 32600
Sprint 0 | 3 | 3 | 8150 | 9780
Build | 9 | 15 | 128994.957 | 214991.595
Final UAT | 3 | 3 | 6142.617 | 6142.617
Prod Deployment & Support | 2 | 2 | 4095.078 | 4095.078
User Guide | 0 | 0 | 2608 | 3260
Total | 21 | 27 | 166290.652 | 270869.29
External Quote - RRB
| Duration (Weeks) |  | Lower Bound (£) | Upper Bound (£)
Consultancy | 4 | 4 | 8150 | 16300
Sprint 0 | 3 | 3 | 8150 | 9780
Build | 6 | 9 | 85996.638 | 128994.957
Final UAT | 3 | 3 | 6142.617 | 6142.617
Prod Deployment & Support | 2 | 2 | 4095.078 | 4095.078
User Guide | 0 | 0 | 1304 | 1956
Total | 18 | 21 | 113838.333 | 167268.652
| 27 | 36 | 280128.985 | 438137.942
|  |  | 99750 | 141800 | 3.0898 | [5 empty] | 8.3077
Formulas:
FTE = [FTE, row above]+D42*7
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider the extent of discovery already completed, and knowledge of the client's business & Org.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider extent of custom component development, use of 3rd party apps, 3rd party integrations.
Note on B11: Nikki Papenfus: Seems high for support. Should we allow for different FTEs for UAT & support?
Note on I15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 point story = 5 days to dev, QA, fix bugs & deploy
Note on K15: Nikki Papenfus: TO BE DECIDED SVOT project: Average points delivered by 1 Dev FTE in a 3 week sprint = 16.4 points

## Proposal v1_Features
Epic | Feature | Scope Notes | Points | User Story A/Cs | #
General Case Management | Tenancy Review Email Cases | Update the existing case type layout to align with new standards. Add KPI indicator? | 3
General Case Management | Email Theading | Thread responses to case emails back onto the case. Notify case owner? | 3 | The (email) communication can be issued via the ‘system’ and replies from complainants will be received back within the system also (two-way communication). All communications to and from the complainant are registered against the ASB case file and/or the customer account (provided they are a Grainger resident) The ‘system’ will integrate with Microsoft Outlook ensuring that any communications received or issued via outlook are automatically logged against the customer and/or unit in the ASB case file | 14, 25
Rent Challenge | Formal Rent Challenge Case | - Page layout for record type - Formula fields - Linked to tenancy review. - Stages / progress bar - Upload files - Email from case. - Validations: Required information captured at certain stages. - Save & calculate reporting metrics. | 13 | The new Challenge Case is linked to Rent Increase process and specifically the Rent Review in progress The case includes relevant data fields to include the capture of rent requested and achieved, dates of appeal, hearing, decision, and the outcome details with details of any decision made. Any word, PDF, Photos or other document types are added to the case folder. Emails sent to third parties are sent from the case task, and replies are saved back onto the case Evidence and data fields to record dates/times of the formal challenge Appeal Date, FFT Hearing Date, Date of Decision, Rent Achieved, Date for new rent to be charged Rent Data to include Rent Applied, Rent Achieved, Rent Loss, Time taken by FTT to process, decision made won/lost, and lessons learned A progression bar on each task to show each stage of the appeal process | 1, 2, 3, 6
Rent Challenge | Notify Stakeholders of Formal Rent Challenge | - Notify stakeholders on case creation (TBD task or email) - Notify stakeholders once decision made (TBD task or email - 2x templates challenge won/lost) | 5 | When a Formal Rent Challenge case is created, the system alerts CC, TMT and any other stakeholders to ensure rent increases are placed on hold. When a Formal Rent Challenge decision has been made, the system alerts CC, TMT and any other stakeholders to ensure rent increases are taken off hold and the Rent Review Process is fully completed in line with the new rent amount and chargeable date. | 5, 8
Rent Challenge | Integrate Rent Challenge Case & Tenancy Review Opportunity | - Create from tenancy review opp & prepopulate information from opp. - Add related list of cases to TR opportunity record layout. - New validations on TR opp if there is a linked case. - Auto update the Tenancy Review opportunity when a decision is made? - E.g. update start date of new contract, updat rent amount; create a new primary offer - May need to save additional data for reporting purposes | 8
Rent Challenge | Generate Reply Form & Written Submisstion | - Generate 2 x forms / documents. - Capture form content via 2 x screenflow? - 2x email templates available for users to select? | 13 | Standard templates that can be completed by TMT to return the (Reply Form) property information to FFT once an appeal has been received Standard templates that can be completed by TMT to return the (written representation) the evidence to support how the rent increase was calculated using comparable evidence, local geographical benefits and the service/amenities provided by Grainger All emails/communication should be sent/received and saved against the case record. | 6
Rent Challenge | KPI Indicator | - Colour-coded KPI tracking status - Will likey be multiple KPIs depending on the case stage. | 3 | Where a KPI target is due, or has been missed, the task bar should show a traffic light status to make it easily visible for users where tasks are due/overdue | 6
Rent Challenge | Reporting & Dashboard | 6 Reports 1x Operational Dashboard with filters | 8 | Dashboards and reports to show metrics for the following: 1.% of rents challenged 2.% increase in rent of rents that are challenged 3.Number of challenges won and lost (and the % level of rent increase of these) Percentage of appeals won/lost - split by region and building to show comparisons against each FTT office 4.Time taken for FTT hearing decision (from date on section 13 notice to FTT decision date) / Average times to process appeals through the FTT (spike for cases outside if these timescales) 5.Time taken for implementation of new rent (if different from above due to hardship) 6.Rent lost due to time delay on FTT decision / Average Rent loss for FTT time taken to process - split by region and building to show comparisons against each FTT office | 9
ASB | Create New Incident Case | - Screen flow to create new incident case: Select if ASB or not. - If ASB: step by step question and answer set to evaluate case severity - Follow up questions depende on the answers selected. - Display suggested severity level > user can manually update. - Create case with the applicable record type. | 3 | • Users are prompted to answer ‘Was the incident a result of ASB’ when creating a task and are provided with Yes or No options: • If Yes – the system routes the incident into the ASB process workflow • If No – the system will generate a Near Miss or Injury workflow to record incidents without the requirements below. • The system presents a clear, step by step question and answer set to evaluate case severity • When the user answers questions and certain answers are selected, the system dynamically adjusters or filters subsequent questions to maintain relevance • When all questions are answered, the system suggests a severity level • If the user disagrees they can manually adjust the severity level before submitting the ASB case | 1, 3
ASB | Incident Cases [Near Miss & Injury] | - Page layout for record type - Two different Incident Types with fields conditionally displayed depending on type? - Upload files - Email from case. - Validations: Required information captured at certain stages. - Save & calculate reporting metrics. | out of scope | As a User I want to classify incidents by Near Miss or Accident during reporting, so that I can accurately assess severity and determine the most appropriate response actions The system displays a set of standard date-related questions (e.g., "When did the incident occur?") Dates are required fields and validated for format (e.g., DD/MM/YYYY) - Near Miss [Link to ‘Incident – Near Miss’] Person at Risk [Drop Down] Location of Incident [Drop Down] Cause of Near Miss [Drop Down] Description [Free Text Box] “Describe what happened and how. If witnesses, please provide details.” - Accident [Link to ‘Incident – Injury’] What caused the Injury? [Drop Down] Person involved [Drop Down] Name of Person Injured [Free Text Box] Location of Incident [Drop Down] Type of Treatment Required [Drop Down] Description [Free Text Box] “Describe what happened and how. If witnesses, please provide details.” The system has comment fields to allow users to record details and updates for each ASB task Users can edit or add new entries with time and date stamps and user stamp The system allows for documents to be uploaded against the task including as minimum the most common file types (pdf, doc, docx, word etc) The system allows for the video and audio files to be saved against the task including as minimum the most common file types (mp4, avi, mp3 etc) The system allows for images to be saved against the task including, as minimum the most common file types (jpg, png, bmp, gif etc) Uploaded documents, videos, images are listed in the task in date logged order and are viewable/downloadable File size and type restrictions are clearly stated | 3, 4, 5, 7
ASB | ASB Possession Cases | - Page layout for record type - Formula fields - Stages / progress bar - Instructional text is for each stage explaining what information should be entered. - Conditional display of fields based on stage? - Upload files (including video, audio, images) - Evidence files cannot be deleted - TBD if possible? - Email from case. - Add tasks - Validations: Required information captured at certain stages. - Save & calculate reporting metrics. - Strict access control on who can see what. e.g. by case record type. - Flag sensitive cases to be hidden from general users. | 13 | • Instructional text is clearly displayed at each step of the task creation for the user to follow steps/actions • Text explains what type of information should be entered The system has comment fields to allow users to record details and updates for each ASB task Users can edit or add new entries with time and date stamps and user stamp The system allows for documents to be uploaded against the task including as minimum the most common file types (pdf, doc, docx, word etc) The system allows for the video and audio files to be saved against the task including as minimum the most common file types (mp4, avi, mp3 etc) The system allows for images to be saved against the task including, as minimum the most common file types (jpg, png, bmp, gif etc) Uploaded documents, videos, images are listed in the task in date logged order and are viewable/downloadable File size and type restrictions are clearly stated The ASB incident types for selection should include: Personal ASB (harassment or targeting specific individuals/groups); Nuisance ASB (causing trouble to community, loud music or public disturbances) ; Vehicle-related ASB (abandoned cars/reckless driving); Trespassing (unauthorised entry onto private property); Animal-related issues (aggressive or uncontrolled pets); Drug paraphernalia (illegal substances, presence of needles or drug related litter) ; Aggressive or violent behaviour – physical threats or actions Category selection: Users can select one or more ASB incident types from the predefined list when submitting a report Clear definitions: Each category includes a short description or example to help users make an informed choice Validation: At least one category must be selected to submit the incident report Each incident must be classified using one of the following mandatory severity levels: Fundamental (single low ASB incident - verbal warning); 1st Stage (single significant ASB - 1st formal letter); 2nd Stage (reoccurring incidents - 2nd formal letter) ; Final Stage (a serious incident or where ongoing incidents move to a legal stage) Severity selection • Users must select a severity level from a dropdown menu when submitting an ASB incident • The selection is mandatory and required to proceed The system displays a set of standard date-related questions (e.g., "When did the incident occur?") Dates are required fields and validated for format (e.g., DD/MM/YYYY) Anti-Social Behaviour: Person at Risk [Drop Down] Location of Incident [Drop Down] ASB Category [Drop Down] Description [Free Text Box] Escalation stages - Fundamental: Allows the user to add information regarding the initial conversation with the perpetrator, and any follow up actions required Allows the user to add information should they think the perpetrator has stopped ASB behaviour Allows the user to move the task to the next stage (Stage 1) or skip to the final stage (Final Stage) Stage 1 – Formal warning (Letter 1) Allows the user to add information on the actions taken and ongoing incidents that happen Allows the user to move the task to the next stage (Stage 2) or skip to the Final stage (Final Stage) Stage 2 – Escalated warning letter (Letter 2) Allows the user to add information on the actions taken and ongoing incidents that happen Allows the user to move the task to the next stage (Final Stage) Final Stage: Allows the user to complete a solicitor instruction template so that we provide all of the detail required to solicitors Allows the user to add information to the system to confirm legal information including dates of service for legal notices, court dates and solicitor details Allows the user to add information on the outcome from the legal proceedings and any actions required Allows the user to confirm a recovery date When I am viewing an ASB case, the system displays the ASB case stage (workflow stage) including: ASB incident logged, investigation pending / being investigated / Response issued case closed / reopened) Case status shall include stages such as: New, In Review, Action Taken, Escalated, Closed. • Access to case data is restricted based on user roles • Grainger colleagues’ data visibility is scoped by site, portfolio, or cluster. • Different ASB case types have defined visibility rules per role • Reports include actionable insights and lessons learned summaries • Track service of notice so that when a notice is being served a user can log it in the system entering notice type, service date, expiry date and reason for service (ie Rent arrears, ASB, refurb etc) • When a notice is served user can specify via selection whether prepared internally or via a solicitor, providing the relevant solicitor details • The system can be updated with notes, updates, timestamps on events and communications • When a court hearing is scheduled, dates can be added into the system including court hearing date, location, case reference • Correspondence can be attached to the task • When a baliff date is set, the system allows input of scheduled baliff date and any associated information (baliff contact details) • I can select the relevant status for the stage of legal service (ie notice served awaiting expiry, notice being prepared awaiting service, court hearing pending etc) | 2, 3, 4, 5, 7, 8, 9, 13, 19, 22, 24
ASB | Update Tenancy from Case | - Flag eviction notice & reasons on tenancy. - See related list of cases on a tenancy (where reporter or perpetrators) - See related list of cases on an account (where reporter or perpetrators) | 2
ASB | Evidence & Note Timeline | For ASB & Incident Cases: - Users see a user-friendly timeline of all case notes & evidence (files, videos, photos). - All evidence files are timestamped and cannot be edited or deleted. - Notes/comments can be added & edited with date/time & user stamped. | 3 | • The system accepts various media types from multiple sources (see earlier user story) • The Grainger resident app connects securely to the system, allowing residents to submit evidence confidently • All submissions via the app maintain security and confidentiality standards • Every piece of evidence or case note uploaded is automatically timestamped • Timestamps are visible for tracking and audit purposes • Once evidence is uploaded, it is locked to prevent alteration or deletion, ensuring data integrity • The system provides a timeline view of all case notes and evidence entries. • The timeline is easy to navigate and understand The system has comment fields to allow users to record details and updates for each ASB task Users can edit or add new entries with time and date stamps and user stamp | 4, 15
ASB | Link Multiple Reporters & Perpetrators to a Case | - 'Reports' sub-object to the case? - Roll up count of number of reports on a case. - Multiple perpetrators can be linked to the same case. TBD if requires a record or just a list of account / contacts | 3 | • Users can add multiple reporters to an existing ASB case • Each reporter has an independent workflow and response tracking • Multiple perpetrators can be linked to the same case • Reports and dashboards display the number of reporters associated with each case • System prevents creation of duplicate cases by linking new reports to existing cases where appropriate | 20
ASB | Identify Duplicate & Linked Incidents | - Alert user to potentially related ABS incidents based on reporter / tenant / unit / tenancy. - User must review duplicates before proceeding. - User is prompted to check for duplicates after 3rd party initially creates the case. If there is an existing case for the same incident: - Ability to merge existing case details into existing case: E.g. create a new report record on an existing case (copy files, data across) and close current case? If there is a seperate, but related case: - The user can link the cases. - Related list of linked cases visible both ways. | 5 | • The system will link related incidents accordingly based on customer/unit for comprehensive case tracking When I enter the any of the: complainant / alleged perpetrator / property address into the system – the system will alert me to any potential duplicates The system will display a ‘potential duplication’ alert message on the screen and I cannot proceed without reviewing the duplicates Existing records matching complainant and or alleged perpetrator and or unit address are displayed to me clearly for review as well as case raised date / task creator or owner • I am asked to review the duplicate records and given the choice as to whether I want to switch to a pre existing ASB case or continue to create a brand new record • System prevents creation of duplicate cases by linking new reports to existing cases where appropriate • Within the system, when the Grainger user selects a customer OR a unit – any Incidents previously logged relating to either entity or those (customer/unit) should be displayed • The Grainger user can select the ‘incident’ reference number to review the complete issue • Sensitive cases are hidden from general users and only visible to management • The Grainger user can mark whether a linked incident should be included in another ASB investigation | 1, 12, 22
ASB | Send Notifications to ASB Incident Reporters | - Send automated notifications to the reporter(s) (tenant/staff/3rd party) - Sent via the reporter’s preferred contact method (i.e. email or SMS). - Capture preferred contact method on an account? - 2-5 x automated notifications: Sent on case creation & completion [TBD]. - Send seperate emails if there are multiple reporters. - 3 x email templates that the user can select. [new reporter on existing case, stage update, letters sent] - Send seperate emails if there are multiple reporters (be able to select the recipient) | 5 | Acknowledgement on Submission: When a reporter submits an ASB incident, they receive an automated acknowledgement confirming the incident has been logged. The message includes a reference number and a brief explanation of next steps. Notification on Resolution: When the incident task is marked as completed/closed in the system, the reporter receives a second notification. The message clearly states the outcome and indicates that the case has been closed. Delivery Channels: Notifications are sent via the reporter’s preferred contact method (i.e. email or SMS), as specified during submission. Resident correspondence (acknowledgement, stage updates, formal letters, outcomes) are generated and sent from the system Selectable templates for different stages of communication with complainants including: • Initial acknowledgement with ASB policy or guidance for residents attached • Case update templates • Final outcome template The templates issued will link to stages of the ASB workflow • The (email) communication can be issued via the ‘system’ and replies from complainants will be received back within the system also (two-way communication) • All communications to and from the complainant are registered against the ASB case file and/or the customer account (provided they are a Grainger resident) • The Grainger user can select the relevant template from within the system • The Grainger user can select the relevant Grainger resident (where relevant) from the system – to whom the communication is to be sent to • The ‘system’ will integrate with Microsoft Outlook ensuring that any communications received or issued via outlook are automatically logged against the customer and/or unit in the ASB case file • Each reporter has an independent workflow and response tracking | 6, 11, 14,20
ASB | Send Notifications to Grainger Stakeholders | - Send automated notification emails on creation of ASB or incident case to stakeholders (manager / director / H&S Team) or once severity has been assigned. [2 templates?] - Recipients depend on severity of case and record type. | 3 | Automated notifications • Upon submission, the system sends an automated notification to the relevant (Manager and/or Director), based on the selected severity • Notifications must include: incident details, severity classification and time and date stamp Escalation visibility: All incidents marked as ‘Final Stage’ must also trigger a high priority alert to the Department Head/Manager/Director Notification format: Notifications are sent via email • The same data is viewable on a dashboard either within source system or i.e. Power BI Audit Trail: All notifications logged in the system have a timestamp as to when they were sent and to whom for traceability purposes | 8
ASB | Generate & Send ASB Documents | - Generate 4x documents: Formal Warning Letter 1; Escalated Warning Letter 2; Solicitor instruction template; S8 Notice. - Documents are partly pre-populated & partly editable. - Send doucument from case; document & email linked to case. - Capture / default a deletion date on each document. | 21 | Escalation stages - Stage 1 – Formal warning (Letter 1) Allows the user to select pre-formatted Letter 1 template The system presents the template in an editable format The system pre populates (merge fields) such as Dear (resident name) Allows the user to edit any part of the template if required Stage 2 – Escalated warning letter (Letter 2) Allows the user to select pre-formatted Letter 2 template The system presents the template in an editable format The system prepopulates (merge fields) such as Dear (resident name) Allows the user to edit any part of the template if required • The system generates a precedent section 8 notice in the latest form with drop down boxes to select the relevant grounds, allowing the selection of multiple grounds where appropriate. • Within the Section 8 form, free-text entry is available for additional details as needed • The system allows for documents created and stored there to have a deletion date specified and this is either autodeleted or prompts the responsible person to review and delete or reset date as appropriate. • Documents have specified deletion dates • Access to stored documents is limited to those with a legitimate business need to access them. | 9, 16
ASB | Tenants & 3rd Parties Submit Incident or ASB Case | - Customer, contractor, colleague, member of public or other relevant party reports ASB or incident case via: - Internal webform (staff/employee)?? - Public-facing Form Assembly form - Tenant can access FA form via mobile app > creates a new case > flag to manual review. - User can send email to tenant/3rd party with a link to complete form > update case. - Able to upload files, photos on Form Assembly. TBD is this possible? | 5 | The system shall accept a reported case of ASB from employees, residents, and 3rd parties including: internal webform (staff/employee), public facing web form and/or resident app, input manually into system (entered manually by staff) ASB reports submitted via the app are automatically routed into the central ASB system Each case reported t shall generate a unique case ID and timestamp for tracking and audit purposes The Case ID is visible to system users The system shall capture structured information including: Nature of the complaint (i.e. noise, harassment, substance misuse etc.; Location (property/unit/address); Parties involved (complainant and alleged perpetrator); Date and time of the incident; Supporting evidence (photos, videos, witness accounts); Mandatory fields must be completed before submission File types and size limits are enforced for media uploads and error messages clearly displayed to the system user where an upload has failed or is not possible | 11
ASB | ABS Tasks | - Automated task generation depending on the nature of the ASB incident | 3 | • The system has automated task and workflow generation and automatically creates follow up tasks depending on the nature of the ASB incident | 18
ASB | KPI Tracking Status (ASB Only) | SLAs related to severity. - Colour-coded SLA tracking [formula fields]. - Different SLAs for ASBs & indicidents. TBD '- Additional (?) SLAs for turnaround time on each Stage - Each stage has associated start date & due date. - Users can extend the ‘due date’ & provide a reason. - Calculate colour-coded flags. - User can see next actions & due date to complete each stage. - See where any actions/tasks are overdue. - When an ASB case is created or 3rd party case is reviewed: Auto-assign case based on severity. | 5 | Built in SLA’s should reflect the severity level of the task in the same way they do on any normal maintenance job: - Low severity = Standard SLA (i.e. 5 working days) - High severity = Urgent SLA (i.e. 24–48 hours) - Severe = Critical SLA (immediate action required) Internal severity level determines who a task is assigned to: - Low severity → RSA (Resident Support Advisor/CST) - High severity → RSM (Resident Services Manager/Portfolio Manager) - Severe → Senior Management or Legal Escalation logic shall route high-risk or persistent ASB cases to senior teams or legal advisors • Each ‘stage’ of the workflow is timebound with an associated ‘start’ and ‘due date’. • As a user I can see what my next required actions are on my ASB cases and by what date they are due • The system will flag to me the business where any stages/actions/tasks are overdue • As a user I can extend the ‘due date’ by providing a ‘reason’ and the reasons must be selectable from a drop-down list. • Extension reasons are logged for audit and reporting purposes | 13, 20
ASB | ASB - Reporting & Dashboards | Reporting on ASBs & Incidents - Number of incidents / ASBs by portfolio, incident category, severity level, case status, dates/months - Cases with highest severity. - Number of new, open, closed and escalated cases in the month - Portfolio comparisons - KPIs: Overdue stages - Display open, closed cases, response times - Overdue tasks - Filter by date range, portfolio, severity, etc TBD = The system cannot provide drilled-down information to non-reporters to ensure private information is secure (GDPR , etc.) | 8 | A dashboard that allows reporting of numbers by: portfolio, incident category, severity level, case status, dates/months A drill through option to see case by case updates Ability to click on summary numbers to drill into individual case records A high-level report that allows monthly operational reporting including: number of new, open, closed and escalated cases in the month, portfolio comparisons The system can generate an pdf or excel summary suitable for export All data shown is filterable by date range / portfolio / severity •The system to link to [Power BI] with a dedicated dashboard of real-time key KPIs allowing users to drill down to specific details* allowing quick identification of repeat offenders. •Display open, closed cases, response times •*The system cannot provide drilled-down information to non-reporters to ensure private information is secure (GDPR , etc.) •The user can filter reports by date range, location, property and other relevant criteria • Reports and dashboards display the number of reporters associated with each case • The system will flag to me the business where any stages/actions/tasks are overdue | 10, 17, 20
ASB | Print Case Details | The system presents a report in a printable format detailing times, notes and actions taken | 2 | When ready to instruct solicitors, I would like the system to produce a report of the incident timeline with dates and notes so that this report can be used as evidence on a possession hearing. • The system presents a report in a printable format detailing times, notes and actions taken | 26
ASB | Anonymise data |  | Scope out? | • The system enables ASB data to be collected and anonymised to meet any reporting requirements to local or central government.
Pet | Create Pet Application Case | - Create pet application case from new lease opp: Pre-populate with unit, account, etc. - User creates existing tenant's pet case from verbal request. - Auto-assign each case to the appropriate property team or customer service group based on the resident’s building, unit, or tenancy profile. | 3 | As part of the leasing journey, the applicant should have access to a link to complete an online form for a pet request. As a Lettings User I want to create a new case to manage the application request for a new pet. As a mid-term customer I would like to apply for a pet in person speaking to Front desk As a management user I want to create a new case to manage the application request for a new pet if requested by a resident, or where we identify and unregistered pet within the building I want to send a link, or complete the form in person with the applicant detailing the pets they are requesting The system must automatically route each pet registration request to the appropriate property team or customer service group based on the resident’s building, unit, or tenancy profile. This ensures that the correct team is responsible for reviewing and processing the application without delay. | 1, 8
Pet | Pet Application Cases | - Page layouts for 2 record types: new and existing tenants - Stages / progress bar - Link to customer, tenancy & to new lease opp (if applicable) - Capture multiple pets (maintain pet register below) - Upload files (documents, photos) to case and/or individual pet record. - Email from case. - See block / floor capacity traffic light indicator. - Validation (e.g. file type & expiration date validations). - Make default email templates availble: Acknowledgement of case email template. - Existing tenants: See all existing pets already in the unit (from the pet register) | 13 | I want the case to be linked to the customer object and linked to the application/lettings journey 13- Documents and photos relating to the pet can be stored against the customer record and the pet Case The system must maintain timestamped logs of all actions taken within the pet registration platform. This includes every submission, update, approval, rejection, and document upload, with each entry clearly recording the date, time, and user responsible. These logs ensure full traceability and support internal audits. The system must support integration with a document storage platform such as SharePoint or AWS S3. This will allow secure upload and retrieval of pet-related documents, including vaccination records, insurance certificates, and policy acknowledgements, with appropriate access controls and retention policies. The system must ensure full compliance with the UK General Data Protection Regulation (UK GDPR), including secure handling, storage, and processing of all personal and pet-related data. Data must only be retained for as long as necessary and must be stored in a manner that protects against unauthorised access or loss. Access to the system must be governed by strict role-based permissions. Frontline teams should have read and write access to pet records relevant to their site. Management users must have administrative privileges, including the ability to override decisions and update policies. Once a resident submits a pet registration request, the system must issue an acknowledgement within five business days. This acknowledgement should confirm receipt of the application and outline the next steps in the review process. | 12, 15
Pet | Maintain Pet Register | - Pet register records: [new object?] - Link each pet to an account & tenancy & unit & pet application case (optional) - Ability to indicate where tenant has declared not having pets. - Ability to indicate where there is a decision not to charge. - Each record has docs linked e.g. vet vaccine records. - Each record can have comms & tasks associated (activity timeline) - Able to see/access approval / rejection history - from linked cas? - Able to see/access history of pet rent. | 5 | A current list should be accessible with data fields to record pet detail and any pet collar reference numbers for lost pets The system must include a centralised digital pet register that consolidates all pet-related data across the portfolio. The system must include the ability to mark a unit as having “no pets declared.” This status should be clearly recorded and visible in the register to support accurate record-keeping and compliance monitoring. The system must provide access to a full audit trail of all pet registrations, including timestamps, user actions, and document history. The Compliance Officer must be able to filter records by site, approval status, or document type, and export data for audit or regulatory purposes. Any missing or expired documentation must be clearly flagged. In such cases, the system must allow for a “no charge” status to be recorded, along with a reason and reference to the relevant legal or policy exemption A complete change history must be retained for each pet record. This includes changes to pet status, updates to submitted documents, approvals or denials, and any charges applied. The history should be accessible to authorised staff and presented in a clear, chronological format. | 7, 10, 11, 31
Pet | Search / View Pet Register | - Dashboard or Custom List View - Search pet register by site, tenant name, unit number, pet type, approval status - Able to export pet register | 5 | This register should be fully searchable by key fields such as tenant name, unit number, pet type, and approval status, allowing onsite teams to quickly locate and review relevant records.
Pet | Integrate Pet Application Cases with New Lease Opportunity. | - See if unit / building allows pets on opp. - See block / floor capacity traffic light indicator on opp. - Update case & pet register from opp: - If unit is changed: Update unit & delete/nullify any existing approval? - Close case & update pet register status if opp close/lost. - Update pet register status once opp goes to Audit or Closed Won; link case / pet register to tenancy. - New lease opportunity requires extra validations if there is a linked pet case. | 5 | • The System displays if the apartment is pet friendly • The system displays if the building is at capacity for pets on the floor, or whole building - The system will show user a list of banned/prohibited pets
Pet | Manage & See Pet Capacity & Policies | - Manage buildings, floors(??) & units that allow pets. - Pets not allowed in listed buildings. - Pet limits by unit type or tenancy type (1 bed vs 2 bed) - Ability to override at unit-level & block-level. - Manage pet capacity (%): By floor & by building/block - Calculate capacity by floor & by building/block - Traffic light indicator of pet density / see if at limit or approaching limits - Maintain list of banned pets [general policies] - Configure global pet policies [text] (general, listed buidings, etc.) & block-level overrides. - Save a history of policy verions, date/user stamp, description of update; effective date. | 5 | The pet register should allow the user to set limits against each site by selecting pet friendly apartments on each floor. A limit threshold should be set preventing too many pets being allowed by floor and at a building level 1- each unit/floor/building should allow the user to set limits against each site by selecting pet friendly apartments on each floor. Property-specific pet policies (e.g., pets not allowed in listed buildings) Tenancy type or unit size (e.g., max 2 pets for 1-bed units) Lease restrictions or local council limitations pet policy associated with each property. For example, pets may not be permitted in listed buildings or heritage properties due to structural or conservation restrictions For instance, a one-bedroom flat may be limited to a maximum of two pets, while larger units may allow more. These thresholds should be customisable at the scheme or unit level. The system must allow landlords or administrators to configure a global pet policy that applies across all sites by default. This policy should support rules such as restrictions on exotic pets, specific breed limitations, and a maximum number of pets per unit. In addition to the global policy, site- or scheme-level overrides must be supported, enabling local managers to tailor rules based on building-specific needs or insurance requirements. The system must maintain full version control of all pet policies, including a history of changes, effective dates, and archived versions for audit purposes. If a property is exempt from the standard pet policy — for example, due to listed building or heritage status — it must be clearly flagged in the system, and this exemption should be visible to both staff and residents. Only authorised users, such as landlords or regional managers, should be able to create or modify pet policies. All changes must be logged with user identification, timestamps, and a description of the update. Traffic Light KPIs Update against the floor/Unit to show if at maximum capacity The traffic light system is intended to provide a clear, visual representation of pet density within a building, block, or floor. It helps onsite teams monitor how many pets are currently registered in a given area and whether that number is approaching or exceeding recommended thresholds. A green status indicates that the number of registered pets is within acceptable limits for the building or floor, based on internal policy or capacity guidelines. This suggests that there is still room for additional pet registrations without concern. An amber status means that the number of pets is nearing the upper threshold. While still within limits, it signals that the site team should monitor new registrations closely and may wish to review any pending applications more carefully. A red status shows that the number of pets has reached or exceeded the defined limit for that area. In this case, new pet registrations may be paused or subject to additional review, and the site team may need to assess the impact on shared spaces, maintenance, and resident wellbeing. | 2, 7, 10, 14, 20
Pet | Update Unit & Tenancy | - See a view / related list of current pets on a unit? - Calculate # pets allowed per unit based on block / floor / unit type. - See a related list of current & previous pets on a tenancy. | 3
Pet | Tenant Completes Online Form [Grainger devs form] | - Send email with link to form [2-3 templates - new lease, existing tenant request for pet, unregistered pet identified in bldg] OR Resident can initiate process by completing Form Assembly form accessed from the App [Grainger] - Form Assembly form for tenant to request one or more pets [Grainger] - Updates or creates pet case & associated pet register records? - Auto-assign new cases & send notification email. - See & acknowledge applicable pet policy & save version accepted. TBD - OTP verification [Grainger?] - Ability to upload photo / documents via FA? | 5 | • The online form allows the capture of dynamic pet information • The online form includes pets not acceptable • The online form returns the data into a Pet Register • The online form has a clause to indemnify Grainger against refusal (Can GPLC do this?) As part of the leasing journey, the applicant should have a clear guidance on the pet application process with a caveat that pets may be refused where buildings are at the maximum pet allowance During the pet registration process, residents must digitally acknowledge and accept the policy, with the system recording the date, time, and version of the policy accepted. Consent tracking must be embedded into the system, ensuring that residents explicitly agree to data usage terms before submitting pet information 'From the App, the resident should have access to a link to complete an online form for a pet request 1- The app should have a form link available to open and complete a form assembly application. 2- The online form allows the capture of dynamic pet information 3- The online form includes pets not acceptable 4- The online form returns the data into the customer object. 5- The online form has a clause to indemnify Grainger against refusal 6- The request for a pet application should alert the management team of a new request, and a new S/F case should be created for the management team to progress | 3, 14, 16
Pet | Automated Approval/Rejection | - Some level of auto-approval / auto-rejection of a new case (or after pet details are entered): - E.g. Listed building = no pets - Auto-approve caged pets? - Tenant receives automated approval/rejection response (same as manual rejection/approval). - Includes applicable explanation. - A user can re-open a rejected case & override / approve on an exception basis. | 5 | Automated rules based on: Property-specific pet policies (e.g., pets not allowed in listed buildings) Tenancy type or unit size (e.g., max 2 pets for 1-bed units) Lease restrictions or local council limitations Manual override with justification field for exceptional cases The system must apply automated approval logic based on a set of predefined rules aligned with property-specific policies and tenancy conditions. These rules should be configurable and enforced consistently across the platform to ensure compliance and reduce manual processing. Approval decisions must take into account the pet policy associated with each property. For example, pets may not be permitted in listed buildings or heritage properties due to structural or conservation restrictions. The system should automatically reject applications that conflict with such rules, providing a clear explanation to the resident. Tenancy type and unit size must also be factored into the approval logic. For instance, a one-bedroom flat may be limited to a maximum of two pets, while larger units may allow more. These thresholds should be customisable at the scheme or unit level. In addition, the system must consider any lease-specific clauses or local authority regulations that may restrict pet ownership. Where such restrictions apply, the system should validate the application against these terms before proceeding. For exceptional cases, the system must allow a manual override by authorised staff. When an override is applied, the user must be required to enter a justification, which will be recorded in the audit log for transparency and future reference. | 10
Pet | User Approves/Rejects Pet Application | - Approve/reject applications: TBD if full approval request process is required or just an audit trail of the user who approved/reason/etc? - Send to PM/RST for approval - Update pet register & case status on approval/rejection. - Notify tenant of outcome [3-4 email templates - approve/reject for existing/new tenants]. New lease rejections: - Above email has a link to a FA Form [Grainger to dev] that allows tenant to proceed without pet or cancel the new lease application. - On cancelling: Close Lost the new lease opp; create a task for the opp owner / lettings team to re-market the unit. - On proceding without a pet: Notify new lease opp owner? New lease approval: Notify new lease opp owner & update opp status?? | 8 | • The Acceptance or Rejection decision is recorded with clear reasons to the decision • The system responds to the applicant with the outcome and reason notes • Where rejected - the comms include guidance on how to appeal/complain • The system updates the lettings process on the decision Rejection 2- Rejection - The system responds to the applicant with the outcome and reason notes, the comms include guidance on how to appeal/complain 3- Rejection – within the Form Assembly response the customer has an option to proceed without a pet, or cancel the application process 4- Rejection – if the cancelation option is chosen, the application is updated with a task for the lettings team to re-market the property 5- Rejection – If rejected the pet case is updated and the pet details are kept on record, but added with a status of rejected | 4, 6
Pet | Calculate Pet Rent & Create Pet Licence Contract | - Building/Block: Configure pet rent by builing, or global pet rent with exceptions? - Calculate pet rent based on the number and type of pets registered, as well as any site-specific pricing rules or exemptions. - Existing tenant with existing pets: Calculate total for all pets. - New lease: Display pet rent on new lease opportunity. - Create a residential contract for a pet licence? - Linked to the case and/or opportunity? - Link the contract to the new/exisiting residential tenancy. - Different logic for new/existing tenant? - Activate the contract when the case / new lease opportunity is complete? - Different logic for new/existing tenant. - Update pet register with confirmed/active status on activating the contract? - Close case at some point in the process. Existing tenants with existing pet: - Cancel the existing pet licence contract & create new one with total rent? Ability to end pet rent without removing the pet (e.g. tenant becomes exempt): Manually capture end date on contract & create a task for credit control. | 13 | The system requires an additional monthly charge item for a Separate Pet Rent in addition to the Unit Rent and Parking/Garage Rent. The system must automatically apply pet rent in accordance with the terms of each resident’s tenancy agreement. This calculation should take into account the number and type of pets registered, as well as any site-specific pricing rules or exemptions. Once applied, the charges must be seamlessly integrated with the organisation’s finance systems — such as MRI, Yardi, or Salesforce — to support accurate invoicing, payment tracking, and financial reconciliation. The system must allow leasing operatives to manually add a separate rent charge specifically for pets to a resident’s account. This charge must be configurable based on the number and type of pets, and it should be linked to the relevant tenancy record. The system must also check whether the tenancy agreement permits the application of pet rent and whether any exemptions apply, such as those related to incoming legislation. Once added, the pet rent charge must be clearly itemised on the resident’s rent statement and visible in both the finance system and the resident portal. The system must support recurring charges, with the ability to set start and end dates, and must allow for adjustments or removal if the pet is no longer present or if the resident becomes exempt. All actions taken by the leasing operative must be logged in the audit trail, including the reason for the charge and any supporting notes. The system must also generate alerts for any inconsistencies, such as duplicate charges or missing documentation. All actions taken by the leasing operative must be logged in the audit trail, including the reason for the charge and any supporting notes. | 13, 32
Pet | Tenant Signs Pet Licence | - Generate pet licence document for tenant to sign via Adobe sign - Generate Pet Policy document to send?? - Chaser emails - for new lease only or 2 templates (new & existing tenants)? | 5 | Approved 6- Comms are sent to the applicant to confirm with the pet policy, site rules and a form to sign accepting T&C’s [new leases] The Tenancy Progression does not complete unless the T&C’s are returned 7- The case is automatically closed when the customer signs the T&C’s accepting the policy and site rules. 8- If the T&C’s are not signed within 48 hours a follow up chaser is sent to the resident Lettings Process TPT update system and send out Docs including Pet Policy for signature as part of TA The TA needs to have a Separate line Item for Ret Rent on the TA Additionally, the system must support digital signature functionality, allowing residents to formally acknowledge pet policies and related agreements in a legally compliant manner. | 4, 16
Pet | SLAs | - Save key dates on pet application case - Calculate KPI indicators [different timeframes for new & existing tenants]: - Acknowledgement of pet request timeframe - Decision timeframe - Send alert (email) if case approaching SLA. - Reassign case if overdue SLA. - Manage escalation path? | 5 | Once a request is submitted, SLA timers must be activated to track progress against defined service levels. The first timer should monitor the acknowledgement period, ensuring that the resident receives confirmation of receipt within five business days. A second timer should track the decision period, requiring that a final outcome — either approval or rejection — is issued within ten business days. These timers must operate in real time and be visible to staff via the operations dashboard. If a request is approaching or has exceeded its SLA, the system must generate an alert and escalate the case to a designated manager or senior team member for immediate attention. 1- Rule: Automatic allocation of cases to relevant property or customer service teams. 2- KPI: Acknowledgement of a request should be within 5 business days (mid term application) 3- KPI: Decision: within 10 business days (mid term application) 4- Rile: Alert notifications for pending requests breaching SLA. 5- Escalation routing for overdue approvals with a data stamp of person approving A final decision — whether approval or rejection — must be made within ten business days of submission. The system should automatically track these timeframes and monitor all pending requests against the defined service level agreements. If a request approaches or exceeds the SLA threshold, the system must trigger an alert notification to the relevant site or management team. These alerts should be visible on the operations dashboard and, where appropriate, sent via email or internal messaging tools. For any requests that remain unresolved beyond the ten-day decision window, the system must initiate an escalation process. This should route the case to a designated senior team member or manager for urgent review, ensuring timely resolution and accountability. | 8, 9
Pet | Remove Pet from a Tenancy | - Create a case [new record type] - User can send a link to a FA form for tenants to enter info OR user enters the details. - Display all existing pets linked to the tenancy & the tenant can select the one(s) to remove. - OTP verification. - Tenant can access a link to the form from MyGrainger app -> auto create the case. - If other pets remain: Calculated the revised pet rent. - See other pets linked to the tenancy on the case. - Auto update pet register (status). - Case has a step/stage for credit control to end/update pet rent in Qube. - End the pet licence contract. - If other pets remain: - Create a new pet licence contract with the reduced pet rent amount? - Generate new pet licence contract for signing? Send via Adobe Sign. - Chaser email? - On completion of case: Send automated email to tenant notifying them pet removed from register & pet rent stopped or reduced with effect from [date]. [2 templates] | 13 | When a resident reports that a pet has been sold, rehomed, or has sadly passed away, the system must allow for an update to be made to the pet register. This update should be initiated either by the resident through the self-service portal or by site staff following direct notification. The pet’s status should be changed from “Active” to either “Removed – Rehomed” or “Removed – Deceased”, depending on the reason provided. The system must retain a record of the pet’s registration history, including the date of removal, the reason, and the user who made the change. This ensures a full audit trail is maintained for compliance and reporting purposes. Once a pet is marked as removed, it should no longer count towards the unit’s active pet total, and any associated alerts (such as maintenance warnings or pet rent reminders) should be deactivated. However, the historical record should remain accessible to authorised staff for reference. If the resident wishes to register a new pet in place of the one removed, the standard registration process should apply, including policy acceptance and document submission. Once a pet is marked as removed, it should no longer count towards the unit’s active pet total, and any associated alerts (such as maintenance warnings or pet rent reminders) should be deactivated. However, the historical record should remain accessible to authorised staff for reference. If the resident wishes to register a new pet in place of the one removed, the standard registration process should apply, including policy acceptance and document submission. | 23
Pet | Operations Dashboard | Site-related pet activity, including: - Number of pets, - Pending approvals - cases approaching / exceding SLAs - Any missing or expired documentation - Policy breaches (pets in units /buidings not allowed pets; too many pets per unit) - Pets not being charged rent. - See pet capacity by block & floor & if at limit or approaching limit. - See which floors & units allow pets (& are available / not over capacity) [traffic light indicator] - Filter dashboard by block, unit type, or pet type - Link to load dashboard from a new lease opportunity or case. - SF limitations - we can't filter by each block? More than 50. | 13 | As a Lettings User/Property Manager I want to see a Dashboard and Report on the system what units are available/ acceptable for pets at unit and block level Acceptance 1-The System displays if the apartment is pet friendly 2-The system displays if the building is at capacity for pets on the floor, or whole building 3-The system will show user a list of banned/ prohibited pets 4- A pet Register/Dashboard should show a full list of pets and capacity percentage with availability for remaining pet acceptance The operations dashboard must display a real-time summary of pet-related activity across the site. This includes the number of active pets, pending approvals, expired documents, and any policy breaches. The data must be filterable by date range, unit type, or pet type, and exportable for reporting purposes. The system must identify residents with registered pets who are not currently being charged pet rent and flag these cases for review. The register must be accessible via the operations dashboard, providing real-time visibility to authorised staff. This ensures that teams can monitor pet registrations, track compliance, and respond to queries or incidents efficiently. | 30, 31
Pet | Reminders for Updated Pet Docs | - Save expiration date for each pet documents. - Business rules on which pets require which docments. - Pet- and tenancy-level documents: Vet certificates per pet; insurance per tenancy? - Calculate traffic light indicator for docs missing, overdue, or expiring soon. - Automated reminder emails to tenants to send docs. [2 email templates?] - Tenant will be able to reply to the email with docs attached? Thread it onto the pet registe record? Notify a user/create a task? OR gets a link to a form assembly site that they can upload docs to? Create a linked task for a user to review? | 8 | the system should issue annual renewal prompts to residents. These reminders should request updated documentation, such as valid pet insurance or veterinary health certificates, and ensure continued compliance with pet policy requirements. All uploaded documents — such as insurance policies or vaccination records — must be stored securely, with expiry tracking in place to prompt renewal or removal when documents become outdated. The system should support integration with secure document storage platforms and enforce access controls based on user roles. Automated reminder notifications must be built into the system. These should alert residents when key actions are due, such as insurance policy expiry. Notifications should be delivered via email or app alerts, depending on resident preferences. Any missing or expired documentation must be clearly flagged. The system must automatically track expiry dates for pet-related documents such as insurance or vet certificates. Residents must receive reminders in advance of expiry, with clear instructions for uploading updated documents. If no action is taken, the system must flag the record for follow-up by the site team. | 24, 26, 29
Pet | EOT | On confirmation of actual move out: • Update status on pet register. • Update pet licence status. | 3 |  | 23
Pet | Trigger Survey | Once a pet registration request has been approved or denied, the system should prompt the resident to complete a short feedback survey. | Assume excluded | Once a pet registration request has been approved or denied, the system should prompt the resident to complete a short feedback survey. This will help monitor resident sentiment and identify opportunities to improve the process over time | 17

## Timeline to Deliver Proposal
| Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
| 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08
Meetings | 2025-09-22: ASB and Rent Challenge - Scope Discussion; 2025-09-23: RRB: Qube and Integration - Scope discussion
Leave | 2025-09-24: Sam; 2025-09-26: Sam; 2025-09-29: Sam; 2025-09-30: Sam; 2025-10-01: Sam; 2025-10-02: Sam; 2025-10-03: Sam
Deliver Proposal

## ROM Estimate
Rates
Cost per sprint | 28800
Project Rate | 120
Consultant Rate | 155
|  |  | Phase | Duration (weeks) | Min Hours | Max hours | Lower Bound Cost Rates | Upper Bound Rates
|  |  | Requirements Analysis | 6 weeks (150-200 hours) | 150 | 200 | 23250 | 31000
|  |  | Sprint 0 | 4 weeks (60 - 80 hours) | 60 | 80 | 9300 | 12400
|  |  | Release 1: 2 - 3 Sprints | 6-9 weeks | 2 | 3 | 57600 | 86400
|  |  | UAT & Production Deployment (20-30 hours) | 1 week | 20 | 40 | 2400 | 4800
|  |  | Post Go-Live Support | 2 weeks | 20 | 20 | 2400 | 2400
|  |  | User guide creation/training | Parallel with project (40 hours) | 40 | 40 | 4800 | 4800
|  |  | Total Cost for Release 1 |  | 292 | 383 | 99750 | 141800
Team Composition | Allocation
Team cost / sprint
Dev Senior | 1
Dev Junior | 0.5
QA | 0.25
BA | 0.125
PM | 0.13
Total FTEs | 2.005
Team FTE | 2
|  | Inlcudes | Pet Registration & Management
Anti-Social Behavior
Rent Challenge Process & Appeal

## SVOT analysis
SVOT Project
Total points delivered | 438.75
Total sprints | 7
Total Dev Hours | 3205.5
Dev hours per point | 7.306
Points delivered by 1 dev FTE in 3 weeks | 16.4249
Team | hours | actual %
snr dev | 1932.75 | 54.89%
jnr dev | 1272.75
qa | 1168.75 | 20.01%
ba & arch | 1268 | 21.71%
pm | 198 | 3.39%
| 5840.25 | 1

## DNU_SOW v1 (hidden)
Key
Enter Value
Do not update (Formula)
Currency | £
Rates & Team |  | Velocity & Duration
Sprint 0 Rate (T&M) | 120 | Estimated Story Points | 110
Project Rate | 97 | Optimistic Velocity | 25
Team Size - Build | 3 | Pesimistic Velocity | 15
Team Size - UAT & Prod Support | 1 | Optimistic Sprint # | 5
Cost Per 3 Week Sprint | 120 | Pesimistic Sprint # | 8
Cost for UAT & Prod (per week) | 3880 | UAT Weeks | 2
|  | Prod Support Weeks | 2
Internal
Project Phase | Lower Bound Effort | Upper Bound Effort | Notes | Lower Bound | Upper Bound
Sprint 0 (hours) | 80 | 100 | 4 weeks | 9600 | 12000
Release 1: 5 to 8 Sprints | 5 | 8 |  | 600 | 960
Final UAT | 2 | 2 |  | 7760 | 7760
Production Deployment & Post Go-Live Support | 2 | 2 |  | 7760 | 7760
User guide creation | 6 | 8 | Done in parallel with sprints | 720 | 960 | `
Total Cost for Release 1 |  |  |  | 26440 | 29440
External
Project Phase | Duration | Lower Bound | Upper Bound
Sprint 0 (hours) |  | 9600 | 12000
Release 1: 5 to 8 Sprints |  | 600 | 960
Final UAT |  | 7760 | 7760
Production Deployment & Post Go-Live Support |  | 7760 | 7760
User guide creation |  | 720 | 960
Total Cost for Release 1 |  | 26440 | 29440
Note on F7: Nikki Papenfus: Need to add a contingency factor - this is a SOW / proposal-level estimate. Add a % for unknown 'must have' requirements, which may vary depending on the extent of discovery already done, knowledge of the client's business & org. Add a % for unanticipated complexity of known features, which may vary depending on extent of custom components, external plug ins, 3rd party integration.
Note on F8: Nikki Papenfus: The veloocity #s should be a formula based on number of developers / dev FTEs
Note on D9: Nikki Papenfus: this should round up to the nearerst 0,5 or 0,25
Note on D11: Nikki Papenfus: this needs to be a formula
Note on E32: Nikki Papenfus: these totals should be a sum of the above in case we change them

## DNU_Team & Velocity v1 (hidden)
Team Composition | Allocation
Architect | 100%
Dev Senior | 100%
Dev Junior | 50%
QA | 25%
BA | 12.5%
PM | 20%
Team Size | 3.075
Velocity | Story Points per Sprint
Optimistic | 25
Pessimistic | 15
Note on B1: Nikki Papenfus: Is this FTE or allocation? If allocation, then the # of resources is mising from the equation
Note on B6: Nikki Papenfus: these inputs need to go on the main page. This will vary based on project complexity / size / etc, e.g. renewals was a 75% BA allocation for the project. Other projects might not be. If this is a formula, then the inputs to the formula should be transparant and editable
Note on B11: Nikki Papenfus: This needs to be a formula based on number of devs. or this need to be the number of points for one dev? Question = do we modify the velocity depending the junior / senior dev mix? Yes - this will be updated per project and taking team into consideration

## Currency (hidden)
Dollar | $
Pound | £
Rand | R