## High Level Proposal
Rates
Cost per sprint | 28800
Project Rate | 120
Consultant Rate | 155
|  |  | Phase | Duration (weeks) | Min Hours | Max hours | Lower Bound Cost Rates | Upper Bound Rates
|  |  | Requirements Analysis | 6 weeks (150-200 hours) | 150 | 200 | 23250 | 31000
|  |  | Sprint 0 | 4 weeks (60 - 80 hours) | 60 | 80 | 9300 | 12400
|  |  | Release 1: 2 - 3 Sprints | 6-9 weeks | 2 | 3 | 57600 | 86400
|  |  | UAT & Production Deployment (20-30 hours) | 1 week | 20 | 40 | 2400 | 4800
|  |  | Post Go-Live Support | 2 weeks | 20 | 20 | 2400 | 2400
|  |  | User guide creation/training | Parallel with project (40 hours) | 40 | 40 | 4800 | 4800
|  |  | Total Cost for Release 1 |  | 292 | 383 | 99750 | 141800
Team Composition | Allocation
Team cost / sprint
Dev Senior | 100%
Dev Junior | 50%
QA | 25%
BA | 12.5%
PM | 13%
Total FTEs | 2.005
Team FTE | 2
|  | Inlcudes | Pet Registration & Management
Anti-Social Behavior
Rent Challenge Process & Appeal

## Detail
|  |  |  | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | Sprint 23 | Sprint 24 | Sprint 25 | Sprint 26 | Sprint 27 | Sprint 28 | Sprint 29 | Sprint 30 | Sprint 31 | Sprint 32 | Sprint 33
Scheduling
Velocity
| Total Velocity Done |  |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total Backlog Size |  |  | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
For Bars | Optimistic Forecast |  |  | 0 | 25 | 50 | 75 | 100 | 125 | 150 | 175 | 200 | 225 | 250 | 275 | 300 | 325 | 350 | 375 | 400 | 425 | 450 | 475 | 500 | 525 | 550 | 575 | 600 | 625 | 650 | 675 | 700 | 725 | 750 | 775 | 800 | 825
| Likely Forecast |  |  | 0 | 20 | 40 | 60 | 80 | 100 | 120 | 140 | 160 | 180 | 200 | 220 | 240 | 260 | 280 | 300 | 320 | 340 | 360 | 380 | 400 | 420 | 440 | 460 | 480 | 500 | 520 | 540 | 560 | 580 | 600 | 620 | 640 | 660
| Pessimistic Forecast |  |  | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450 | 465 | 480 | 495
For T&M | Costing
| Team Sprint Cost (Actual) |  |  |  | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400
| Cumulative Team Cost (Actual) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Cumulative Team Cost (Forecast) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600 | 210600
Team Metrics
Optimistic Velocity ( Best Velocity in last 3 sprints) | 25
Likely Velocity (Avg Velocity over last 3 sprints) | 20
Pessimistic Velocity (Worst Velocity in last 3 sprints) | 15
Team Composition | Hourly Rate | Allocation | Cost Per Sprint
Team cost / sprint |  |  | #REF!
Dev Senior |  | 100%
Dev Junior |  | 50%
QA |  | 25%
BA |  | 12.5%
PM |  | 13%
Total FTEs |  | 2.005

## Post Sprint 0 Cost Summary
Cost per sprint | #REF!
Day Rate | 780
Hour Rate | 97.5
FTE Rate | 15600 | Phase | Duration (weeks) | Lower Bound | Upper Bound
Sprint 0
Release 1: 2 - 3 Sprints
UAT
Production Deployment & Post Go-Live Support
|  | User guide creation | Done in parallel with sprints
|  | Total Cost for Foundational Changes and Release 1 | 13 - 16 | 0 | 0

## Proposal_Cost Summary (hidden)
Features | Notes | Points
EOT Updates | Add/update EOT tasks to end pet license fees in Qube. Link pet licence contract to an EOT on creation. End the pet licence contract on check out (same as resi contract). Auto update pet register?
Tenancy Review Email Cases | Updates to the existing case type layout to align with new standards.
ASB Possession Cases | Validations, colour-coded KPI tracking status
Formal Rent Challenge Cases | - Validated information captured at certain stages. - Formula fields - Colour-coded KPI tracking status - linked to tenancy review. - Create from TR opp & prepopulate information. - add case related list to TR opps - Email from case, replies threaded onto case. - Need notification when tenant replies?
Pet Application Cases | 2 record types: new and existing tenants Send automated emails to tenant on rejection and on approval?
Update New Pet Case from New Lease Opportunity. | E.g. update unit from opp; close case if opp close/lost; update case if closed / won?